## Cover sheet
3GPP TSG-RAN5 Meeting #101 | [10 empty] | R5-236433
Chicago, United States, 13th Nov 2023 - 17th Nov 2023
Agenda Item: | 7.5.2
Source: | China telecom
Title: | UE Conformance - Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 2
Work item code: | ATSSS_Ph2-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
This work item covers the protocol conformance testing for Rel-17 Access Traffic Steering, Switch and Splitting support in 5G and LTE system
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% (+5%) | 0 | 8 (+8)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 5% (+5%) | 0 | 8 (+8)
FR1 |  | 5% (+5%) | 0 | 8 (+8)
FR2 |  | 5% (+5%) | 0 | 8 (+8)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0% |  |  | 0%
Common ICS | 38.508-2 | 0% |  |  | 0% |  |  | 0%
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF. Demod/QSI and RRM test cases | 38.522
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 8 (+8) | 0% | 0 | 8 (+8) | 0% | 0 | 8 (+8)
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-231827 | New WID on UE Conformance - Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 2
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 2 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | ATSSS_Ph2-UEConTest
WP Scope: |  | To define the UE conformance test for Rel-17 ATSSS Ues | [12 empty] | vs Area
WP Resp: |  | Jing zhao |  |  | zhaoj16@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 5% (+5%) | 5% (+5%)
[14 empty] | 12 (+12) | 12 (+12)
[14 empty] | 9.4 (+9.4) | 9.4 (+9.4)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.7 | General and Signaling Test Environment for Rel-17 ATSSS testing | Add changes to default messages | China telecom | RAN5#99 (May-23) |  | zhaoj16@chinatelecom.cn | 0.5 | 0% | 0% |  | 0% | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.508-2 | <Clause> | Introduction of common implementation conformance statements for Rel-17 ATSSS testing | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | China telecom | RAN5#99 (May-23) |  | zhaoj16@chinatelecom.cn | 0.5 | 0% | 0% |  | 0% | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
NAS
TBD |  | 38.523-1 | 10.5 | ATSSS with PDN connection as a user-plane resource | [5 empty] | 0
TBD |  | 38.523-1 | 10.5.1 | UE-requested MA PDU session establishment |  |  | TBD |  |  | TBD
3 | Y | 38.523-1 | 10.5.1.1 | UE-requested MA PDU session establishment / ATSSS / UE establishing a PDN connection as a user-plane resource firstly / Success | ****TP1: [TS 24.193: 5.3.1]**** WITH: UE supporting both S1 mode and N1 mode and is switched on without NR and non-3GPP coverage but with good LTE coverage WHEN: UE is configured to request a new MA PDU session THEN: UE sends a PDN CONNECTIVITY REQUEST message with the request type set to "initial request" and including ATSSS request PCO parameter | China telecom | RAN5#103(May-24) |  | zhaoj16@chinatelecom.cn | 1 | 0% | 0% |  | 0% | 0%
4 | Y | 38.523-1 | 10.5.1.2 | UE-requested MA PDU session establishment / ATSSS / UE establishing a PDN connection as a user-plane resource of an already established MA PDU session / Success | ****TP1: [TS 24.193: 5.3.2]**** WITH: UE in state 5GMM-REGISTERED, and 5GMM-IDLE mode over non 3GPP access without cellular coverage WHEN: UE is configured to request a new MA PDU session THEN: UE include the ATSSS request parameter in the Extended protocol configuration options IE of the PDU SESSION ESTABLISHMENT REQUEST message to indicate its support of establishing a PDN connection as the user plane resource of an MA PDU session ****TP2: [TS 24.193: 5.3.2]**** WITH: UE is registered over non-3GPP access and an MA PDU session has been established successfully on this access WHEN: UE detects a suitable EPC E-UTRAN cell THEN: UE sends a PDN CONNECTIVITY REQUEST message with the request type set to "handover" and including ATSSS request PCO parameter and the PDU session ID of the already established MA PDU session |  | RAN5#103(May-24) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD |  | 38.523-1 | 10.5.2 | Release of user-plane resources |  |  | TBD
5 | Y | 38.523-1 | 10.5.2.1 | UE-requested user-plane resource(s) release/ ATSSS / Accepted | TBD |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
6 | Y | 38.523-1 | 10.5.2.2 | Network-requested user-plane resource(s) release/ ATSSS / Accepted | TBD |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD |  | 38.523-1 | 11.9 | Inter-system mobility with established MA PDU session in 5GS |  |  | TBD
7 | Y | 38.523-1 | 11.9.1 | Inter-system mobility with established MA PDU session in 5GS/ATSSS/Single-registration mode with N26/establishing a PDN connection as the user plane resource of an MA PDU session is supported/Handover from NR/5GC to E-UTRAN/EPC | ****TP1: [TS 24.193: 4.6]**** WITH: UE is registered over 3GPP and non-3GPP access connected to 5GC and UE indicates its support of establishing a PDN connection as the user plane resource of an MA PDU session during the MA PDU session establishment procedure WHEN: UE detects a suitable EPC E-UTRA cell after the serving NGC cell becomes not suitable THEN: UE performs a Inter-system change from N1 mode to S1 mode by initiating and successfully completing a TAU procedure, mapped EPC context used and MA PDU session over non-3GPP access was kept |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
8 | Y | 38.523-1 | 11.9.2 | Inter-system mobility with established MA PDU session in 5GS/ATSSS/Single-registration mode with N26/establishing a PDN connection as the user plane resource of an MA PDU session is not supported/Handover from NR/5GC to E-UTRAN/EPC/ | ****TP1: [TS 24.193: 4.6]**** WITH: UE is registered over 3GPP and non-3GPP access connected to 5GC and UE did not indicate its support of establishing a PDN connection as the user plane resource of an MA PDU session during the MA PDU session establishment procedure WHEN: UE detects a suitable EPC E-UTRA cell after the serving NGC cell becomes not suitable THEN: UE performs a local release of the MA PDU session over 3GPP access and non-3GPP access |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
9 | Y | 38.523-1 | 11.9.3 | Inter-system mobility with established MA PDU session in 5GS/ATSSS/Single-registration mode without N26/establishing a PDN connection as the user plane resource of an MA PDU session is supported/Handover from NR/5GC to E-UTRAN/EPC | ****TP1: [TS 24.193: 4.6]**** WITH: UE is registered over 3GPP and non-3GPP access connected to 5GC and UE indicates its support of establishing a PDN connection as the user plane resource of an MA PDU session during the MA PDU session establishment procedure WHEN: UE detects a suitable EPC E-UTRA cell after the serving NGC cell becomes not suitable THEN: UE performs a Inter-system change from N1 mode to S1 mode by initiating and successfully completing an ATTACH or a TAU procedure, mapped EPC context used and performs a local release of the MA PDU session over 3GPP access and MA PDU session over non-3GPP access was kept |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
10 | Y | 38.523-1 | 11.9.4 | Inter-system mobility with established MA PDU session in 5GS/ATSSS/Single-registration mode without N26/establishing a PDN connection as the user plane resource of an MA PDU session is not supported/Handover from NR/5GC to E-UTRAN/EPC/ | ****TP1: [TS 24.193: 4.6]**** WITH: UE is registered over 3GPP and non-3GPP access connected to 5GC and UE did not indicate its support of establishing a PDN connection as the user plane resource of an MA PDU session during the MA PDU session establishment procedure WHEN: UE detects a suitable EPC E-UTRA cell after the serving NGC cell becomes not suitable THEN: UE performs a local release of the MA PDU session over 3GPP access and non-3GPP access |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
11 |  | 38.523-2 | 4.1 | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD |  |  | 0.2 | 0% | 0% |  | 0% | 0%
12 |  | 38.523-2 | 4.2 | <Title> | Add Applicability Condition for Rel-17 ATSSS devices |  | TBD |  |  | 0.2 | 0% | 0% |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.