## Cover sheet
3GPP TSG-RAN5 Meeting #101 | [8 empty] | R5-236613
Chicago, United States, 13th Nov 2023 - 17th Nov 2023
Agenda Item: | 7.5.2
Source: | NIST
Title: | WP Protocol enhancements for Mission Critical Services for Rel-16 (MCPTT, MCVideo, MCData)
Work item code: | MCProtoc16_enh2MCPTT_eMCData2-ConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0-9
1. Introduction
The goal of this work item is to update the existing 36.579 family of Mission Critical Services test specifications to Rel-16. This effort includes the creation of two new specifications: TS 36.579-8 and TS 36.579-9. (UID = 970077)
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 42% (+10%) | 27 (+8) | 84 (-1)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE (Mission Critical Services) |  | 41.8% (+9.9%) | 27 (+8) | 84 (-1)
Mission Critical Services |  | 41.8% (+9.9%) | 27 (+8) | 84 (-1)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | Mission Critical Services
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
Mission Critical Services
MC Common test environment | 36.579-1 | 86.7% (+6.7%) | 4 | 6 (-1) | 86.7% (+6.7%) | 4 | 6 (-1)
MCPTT UE test cases | 36.579-2 | 100% (+83.3%) | 5 (+4) | 5 | 100% (+83.3%) | 5 (+4) | 5
MCPTT Server Application test cases | 36.579-3 | 0% | 0 | 12 | 0% | 0 | 12
Applicability and ICS MC test cases | 36.579-4 | 11% (+2%) |  |  | 11% (+2%)
MC Test suite (TTCN) | 36.579-5 | 2.5% |  |  | 2.5%
MCVideo UE test cases | 36.579-6 | 33.3% (+22.2%) | 3 (+2) | 9 | 33.3% (+22.2%) | 3 (+2) | 9
MCData UE test cases | 36.579-7 | 50% (+6.7%) | 15 (+2) | 30 | 50% (+6.7%) | 15 (+2) | 30
MCVideo Server Application test cases | 36.579-8 | 0% | 0 | 15 | 0% | 0 | 15
MCData Server Application test cases | 36.579-9 | 0% | 0 | 7 | 0% | 0 | 7
5 References
[1] RP-222549 | New WID on Conformance Test Aspects - Protocol enhancements for Mission Critical Services for Rel-16 (MCPTT, MCVideo, MCData)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Conformance Test Aspects - Protocol enhancements for Mission Critical Services for Rel-16 (MCPTT, MCVideo, MCData) | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | MCProtoc16_enh2MCPTT_eMCData2-ConTest
WP Scope: |  | Rel-16 Mission Critical Services Conformance test aspects with the 36.579 family of specifications
WP Resp: |  | Jason Kahn |  |  | jason.kahn@nist.gov | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | Jason Kahn |  |  | jason.kahn@nist.gov
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | Mission Critical Services
41.8% (+9.9%)
146
95.7
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
Mission Critical Services
TS 36.579-1: MC Common test environment
|  | 36.579-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 36.579-1 | 5.3.3 | MCX pre-established session establishment | Add new parameters for Rel-16 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-233490, R5-234572 |  | 1 | 100% | 100% |  | 100%
2 | Y | 36.579-1 | 5.3.36 | UE initiated MCX functional alias status determination and subscription | New generic procedure | NIST | RAN5#104 (Aug-24) | R5-233293 |  | 1 | 100% | 100% |  | 100%
3 | Y | 36.579-1 | 5.3.37 | UE initiated MCX functional alias status change | New generic procedure | NIST | RAN5#104 (Aug-24) | R5-233293 |  | 1 | 100% | 100% |  | 100%
4 |  | 36.579-1 | 5.5.3.16 | MCS-Regroup Default | see 24.379 clause 16 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-237437 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
5 | Y | 36.579-1 | 5.3C.12 | CO MCData call establishment using a pre-established session | New generic procedure | NIST | RAN5#104 (Aug-24) | R5-235403 |  | 1 | 100% | 100% |  | 100%
6 | Y | 36.579-1 | 5.3C.13 | MCData CO call release keeping the pre-established session | New generic procedure | NIST | RAN5#104 (Aug-24) | R5-235404 |  | 1 | 100% | 100% |  | 100%
7 | Y | 36.579-1 | 5.3C.14 | TBD - MCData Message Store Authentication and Authorization |  | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
8 | Y | 36.579-1 | 5.3C.15 | TBD - MCData - Message Store General |  | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
9 |  | 36.579-1 | 5.5.3.1 | SDP Message | Add new parameters for Rel-16 | NIST | RAN5#104 (Aug-24) | R5-233294, R5-233492 |  | 1 | 100% | 100% |  | 100%
10 |  | 36.579-1 | 5.5.3.2 | MCS Info Lists | Add new parameters for Rel-16 | NIST | RAN5#104 (Aug-24) | R5-233491 |  | 1 | 100% | 100% |  | 100%
11 |  | 36.579-1 | 5.5.3.3 | Resource-lists | Add new parameters for Rel-16 | NIST | RAN5#104 (Aug-24) | R5-234585 |  | 1 | 100% | 100% |  | 100%
12 |  | 36.579-1 | 5.5.3.5 | PIDF | Add new parameters for Rel-16 | NIST | RAN5#104 (Aug-24) | R5-233489 |  | 1 | 100% | 100% |  | 100%
13 |  | 36.579-1 | 5.5.8.3 | MCPTT User Profile | Add new parameters for Rel-16 | NIST | RAN5#104 (Aug-24) | R5-231917, R5-236601 | New for RAN5#98 | 1 | 100% | 100% |  | 100%
14 |  | 36.579-1 | 5.5.8.11 | MCData User Profile | Add new parameters for Rel-16 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-233488 |  | 1 | 100% | 100% |  | 100%
15 |  | 36.579-1 | 5.5.8.12 | MCData Service Configuration | Add new parameters for Rel-16 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-233488 |  | 1 | 100% | 100% |  | 100%
TS 36.579-2: MCPTT UE test cases
|  | 36.579-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
16 | Y | 36.579-2 | 5.9 | Configuration / Functional Alias / Location based functional alias status change | 24.379 9A.2.1.4 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-231918, R5-233829 |  | 1 | 100% | 100% |  | 100%
17 | Y | 36.579-2 | 5.1 | Configuration / Rules based affiliation status change | 24.379 9.2.1.7 | NIST | RAN5#104 (Aug-24) | R5-236603 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
18 |  | 36.579-2 | 6.5 | Group regroup using a preconfigured group | New sub-clause header | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-237438 |  | 0 | 100% (+100%) | 100% (+100%) |  | 100%
19 | Y | 36.579-2 | 6.5.1 | On-network / Group regroup using a preconfigured group / Requesting a group regroup using a preconfigured group / Removing a regroup using preconfigured group / Client Originated (CO) | 24.379 16.2.1.1, 16.2.1.2, Annex F.7 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-237438 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
20 | Y | 36.579-2 | 6.5.2 | On-network / Group regroup using a preconfigured group / Receiving a notification of creation of a regroup using preconfigured group / Receiving notification of removal of a regroup using preconfigured group / Client Terminated (CT) | 24.379 16.2.1.3, 16.2.1.4, Annex F.7 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-237439 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
21 |  | 36.579-2 | 6.5.3 | On-network / User regroup using a preconfigured group / Requesting a user regroup using a preconfigured group / Removing a regroup using preconfigured group / Client Originated (CO) | 24.379 16.3.1.1, 16.3.1.2, Annex F.7 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-237440 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
22 | Y | 36.579-2 | 6.5.4 | On-network / User regroup using a preconfigured group / Creating a user regroup using preconfigured group / Removing a user regroup using preconfigured group / Client Terminated (CT) | 24.379 16.3.1.3, 16.3.1.4, Annex F.7 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-237441 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.579-3: MCPTT Server Application test cases
|  | 36.579-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
23 |  | 36.579-3 | 0 | Foreword | Edits for the new specs | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
24 |  | 36.579-3 | 1 | Scope | Edits for the new specs | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
25 |  | 36.579-3 | 2 | References | Edits for the new specs | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
26 |  | 36.579-3 | 3 | Definitions, symbols and abbreviations | Add new definitions | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
27 |  | 36.579-3 | 4 | General | Edits for the new specs | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
28 | Y | 36.579-3 | 6.2 | MCPTT Server - MCPTT Client / Chat Group Calls | To create a Chat Group Call | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
29 | Y | 36.579-3 | 6.3 | MCPTT Server - MCPTT Client / Conference Event Package | To create a Conference Event Package | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
30 | Y | 36.579-3 | 6.4 | MCPTT Server - MCPTT Client / Remote Change of Selected Group | To create a Remote Change of Selected Group | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
31 | Y | 36.579-3 | 6.5 | MCPTT Server - MCPTT Client / Private Calls | To create a Private Call | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
32 | Y | 36.579-3 | 6.6 | MCPTT Server - MCPTT Client / Location | To create Location services | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
33 | Y | 36.579-3 | 6.7 | MCPTT Server - MCPTT Client / MBMS | To create an MBMS call | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
34 | Y | 36.579-3 | 7.3 | MCPTT Server - MCPTT Server operation / Pre-arranged Group Call / untrusted mode / Controlling server | To create a group call in untrusted mode with the a controlling server | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
35 | Y | 36.579-3 | 7.4 | MCPTT Server - MCPTT Server operation / Pre-arranged Group Call / untrusted mode / Participating server | To create a group call in untrusted mode with the a participating server | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
36 | Y | 36.579-3 | 7.5 | MCPTT Server - MCPTT Server operation / Chat Group Calls / trusted mode / Controlling server | To create a chat call in trusted mode with the a controlling server | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
37 | Y | 36.579-3 | 7.6 | MCPTT Server - MCPTT Server operation / Chat Group Calls / trusted mode / Participating server | To create a chat call in trusted mode with the a participating server | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
38 | Y | 36.579-3 | 7.7 | MCPTT Server - MCPTT Server operation / Chat Group Calls / untrusted mode / Controlling server | To create a chat call in untrusted mode with the a controlling server | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
39 | Y | 36.579-3 | 7.8 | MCPTT Server - MCPTT Server operation / Chat Group Calls / untrusted mode / Participating server | To create a chat call in untrusted mode with the a participating server | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
TS 36.579-4: Applicability and ICS MC test cases
|  | 36.579-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
40 |  | 36.579-4 | 0 | Foreword | Edits for the new specs | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
41 |  | 36.579-4 | 1 | Scope | Edits for the new specs | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
42 |  | 36.579-4 | 2 | References | Edits for the new specs | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
43 |  | 36.579-4 | 3 | Definitions, symbols and abbreviations | Add new definitions | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
44 |  | 36.579-4 | 4 | Recommended Test Case Applicability | Add test case applicability statements for the new test cases introduced in 37.579-x. | NIST | RAN5#104 (Aug-24) | R5-231919, R5-234573, R5-237442 |  | 0.1 | 55% (+10%) | 55% (+10%) |  | 55%
45 |  | 36.579-4 | A.1 | Guidance for completing the ICS proforma | Add new ICS proforma | TBD | RAN5#104 (Aug-24) |  |  | 0.1 | 0% | 0% |  | 0%
46 |  | 36.579-4 | A.2 | Identification of the MCPTT Client/Server Equipment | Edits for the new specs | TBD | RAN5#104 (Aug-24) |  |  | 0.1 | 0% | 0% |  | 0%
47 |  | 36.579-4 | A.3 | Identification of the protocol | Edits for the new specs | TBD | RAN5#104 (Aug-24) |  |  | 0.1 | 0% | 0% |  | 0%
48 |  | 36.579-4 | A.4 | ICS proforma tables | Edits for the new specs | TBD | RAN5#104 (Aug-24) |  |  | 0.1 | 0% | 0% |  | 0%
TS 36.579-5: MC Test suite (TTCN)
|  | 36.579-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
49 |  | 36.579-5 | 0 | Foreword | Edits for the new specs | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
50 |  | 36.579-5 | 1 | Scope | Edits for the new specs | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
51 |  | 36.579-5 | 2 | References | Edits for the new specs | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
52 |  | 36.579-5 | 3 | Definitions, symbols and abbreviations | Add new definitions | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
53 |  | 36.579-5 | 4 | Test system architecture | TBD | TBD | RAN5#104 (Aug-24) |  |  | 0.1 | 0% | 0% |  | 0%
54 |  | 36.579-5 | 5 | Test models | TBD | TBD | RAN5#104 (Aug-24) |  |  | 0.1 | 0% | 0% |  | 0%
55 |  | 36.579-5 | 6 | System interface | TBD | TBD | RAN5#104 (Aug-24) |  |  | 0.1 | 0% | 0% |  | 0%
56 |  | 36.579-5 | 7 | Test methods and design considerations | TBD | TBD | RAN5#104 (Aug-24) |  |  | 0.1 | 0% | 0% |  | 0%
57 |  | 36.579-5 | 8 | Other SS requirements with TTCN-3 impact | TBD | TBD | RAN5#104 (Aug-24) |  |  | 0.1 | 0% | 0% |  | 0%
58 |  | 36.579-5 | 9 | IXIT Proforma | TBD | TBD | RAN5#104 (Aug-24) |  |  | 0.1 | 30% | 30% |  | 30%
59 |  | 36.579-5 | 10 | Postambles | TBD | TBD | RAN5#104 (Aug-24) |  |  | 0.1 | 0% | 0% |  | 0%
60 |  | 36.579-5 | A | Test Suites | TBD | TBD | RAN5#104 (Aug-24) |  |  | 0.1 | 0% | 0% |  | 0%
61 |  | 36.579-5 | B | Style Guide | TBD | TBD | RAN5#104 (Aug-24) |  |  | 0.1 | 0% | 0% |  | 0%
62 |  | 36.579-5 | C | Common TTCN-3 Definitions | TBD | TBD | RAN5#104 (Aug-24) |  |  | 0.1 | 0% | 0% |  | 0%
63 |  | 36.579-5 | D | SIP Type Definitions and XSD References | TBD | TBD | RAN5#104 (Aug-24) |  |  | 0.1 | 0% | 0% |  | 0%
64 |  | 36.579-5 | E | TTCN-3 Definitions for the MCX IPCAN test model | TBD | TBD | RAN5#104 (Aug-24) |  |  | 0.1 | 0% | 0% |  | 0%
TS 36.579-6: MC Video UE test cases
|  | 36.579-6 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
65 | Y | 36.579-6 | 6.1.1.14 | On-network / On-demand Pre-arranged Group Call / Re-join procedure / Client Originated (CO) | 24.281 9.2.1.2.4.1 | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
66 | Y | 36.579-6 | 6.4.2 | On-network / Video pull call / One-to-one video pull call / Client Terminated (CT) | 24.281 12.2.2.2 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-231920, R5-233830 |  | 1 | 100% | 100% |  | 100%
67 | Y | 36.579-6 | 6.4.3 | On-network / Video pull call / One-from-server video pull call / Client Originated (CO) | 24.281 12.2.2.4, 12.2.2.6 | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
68 | Y | 36.579-6 | 6.4.4 | On-network / Video pull call / One-from-server video pull call / Client Terminated (CT) | 24.281 12.2.2.5 | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
69 | Y | 36.579-6 | 6.5.2 | On-network / Video push call / One-to-server video push call / Client Originated (CO) | 24.281 13.2.2.4, 13.2.2.5 | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
70 | Y | 36.579-6 | 6.7.3 | On-network / On-demand ambient viewing call / Locally initiated ambient viewing call / Client Originated (CO) | 24.281 15.2.1.1 (locally initiated) | NIST | RAN5#104 (Aug-24) | R5-237443 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
71 | Y | 36.579-6 | 6.7.4 | On-network / On-demand ambient viewing call / Locally initiated ambient viewing call / Client Terminated (CT) | 24.282 15.2.1.2 (locally initiated) | NIST | RAN5#104 (Aug-24) | R5-237444 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
72 |  | 36.579-6 | 6.9 | Location | New sub-clause header | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
73 | Y | 36.579-6 | 6.9.1 | On-network / Location/ Location Information Request | 24.281 18.3.2, 18.3.3 | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
74 | Y | 36.579-6 | 6.9.2 | On-network / Location / Report triggering | 24.281 18.3.2, 18.3.4 | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
TS 36.579-7: MCData UE test cases
|  | 36.579-7 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
75 | Y | 36.579-7 | 5.5 | Configuration / Pre-established Session Establishment / Pre-established Session Release | 18.3.2.1 MCData client procedures 18.3.3.1.1 MCData client initiated release 18.3.3.2.1 MCData client initiated release | TBD | RAN5#104 (Aug-24) | R5-232594 |  | 1 | 100% | 100% |  | 100%
76 | Y | 36.579-7 | 5.6 | Configuration / Download CSK | 24.282 7.2.5 (also see 36.579-2 5.6) | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-232595, R5-233831 |  | 1 | 100% | 100% |  | 100%
77 | Y | 36.579-7 | 5.7 | Configuration / Functional Alias / Functional alias status determination / Activate functional alias / Deactivate functional alias | 22.2.1.2 22.2.1.3 | NIST, MCC TF160 | RAN5#104 (Aug-24) | R5-233493, R5-233832 |  | 1 | 100% | 100% |  | 100%
78 | Y | 36.579-7 | 5.8 | Configuration / Rules based affiliation status change | 8.2.6 | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
79 | Y | 36.579-7 | 5.9 | Configuration / Functional Alias / Location based functional alias status change | 24.282 22.2.1.4 | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
80 | Y | 36.579-7 | 6.1.13 | On-network / Short Data Service (SDS) / Standalone SDS Using Media Plane / One-to-one Standalone SDS / Pre-established session / Client Originated (CO) | 9.2.5.2.1.1, 9.2.5.4.1.1 | NIST | RAN5#104 (Aug-24) | R5-235405 |  | 1 | 100% | 100% |  | 100%
81 | Y | 36.579-7 | 6.1.14 | On-network / Short Data Service (SDS) / Standalone SDS Using Media Plane / One-to-one Standalone SDS / Pre-established session / Client Terminated (CT) | 9.2.5.2.1.2, 9.2.5.4.1.2 | NIST | RAN5#104 (Aug-24) | R5-235406 |  | 1 | 100% | 100% |  | 100%
82 | Y | 36.579-7 | 6.1.15 | On-network / Short Data Service (SDS) / SDS Session / One-to-one SDS Session / Pre-established session / Client Originated (CO) | 9.2.5.2.1.1, 9.2.5.4.1.1 | NIST | RAN5#104 (Aug-24) | R5-235407 |  | 1 | 100% | 100% |  | 100%
83 | Y | 36.579-7 | 6.1.16 | On-network / Short Data Service (SDS) / SDS Session / One-to-one SDS Session / Pre-established session / Client Terminated (CT) | 9.2.5.2.1.2, 9.2.5.4.1.2 | NIST | RAN5#104 (Aug-24) | R5-235408 |  | 1 | 100% | 100% |  | 100%
84 | Y | 36.579-7 | 6.1.17 | On-network / Short Data Service (SDS) / SDS Session / One-to-one SDS Session / Pre-established session / Client Terminated (CT) | 9.2.5.2.1.2, 9.2.5.4.1.2 | NIST | RAN5#104 (Aug-24) | R5-235409 |  | 1 | 100% | 100% |  | 100%
85 | Y | 36.579-7 | 6.1.18 | On-network / Short Data Service (SDS) / SDS Session / One-to-one SDS Session / Pre-established session / Client Terminated (CT) | 9.2.5.2.1.2, 9.2.5.4.1.2 | NIST | RAN5#104 (Aug-24) | R5-235410 |  | 1 | 100% | 100% |  | 100%
86 | Y | 36.579-7 | 6.1.19 | On-network / Short Data Service (SDS) / SDS Session / Group SDS Session / Pre-established session / Client Originated (CO) | 9.2.5.3.1.1, 9.2.5.4.1.1 | NIST | RAN5#104 (Aug-24) | R5-235411 |  | 1 | 100% | 100% |  | 100%
87 | Y | 36.579-7 | 6.1.20 | On-network / Short Data Service (SDS) / SDS Session / Group SDS Session / Pre-established session / Client Terminated (CT) | 9.2.5.3.1.2, 9.2.5.4.1.2 | NIST | RAN5#104 (Aug-24) | R5-235412 |  | 1 | 100% | 100% |  | 100%
88 | Y | 36.579-7 | 6.1.21 | On-network / Short Data Service (SDS) / Standalone SDS using signalling control plane / One-to-one Standalone SDS / Active functional alias / Client Originated (CO) | 9.2.2.2.1 6.2.2.1 6.2.4.1 12.2.1.2 | NIST | RAN5#104 (Aug-24) | R5-234583 |  | 1 | 100% | 100% |  | 100%
89 | Y | 36.579-7 | 6.1.22 | On-network / Short Data Service (SDS) / Standalone SDS Using Media Plane / One-to-one Standalone SDS / Active functional alias / Client Originated (CO) | TS 24.282, clauses 9.2.3.2.3, 9.2.3.2.1, 13.2.2.2.2.1, 12.2.1.2, TS 24.582 clauses 6.1.1.2.1, 6.1.1.2.2, 6.1.1.2.3, 6.1.1.2.4 | NIST | RAN5#104 (Aug-24) | R5-235413 |  | 1 | 100% | 100% |  | 100%
90 | Y | 36.579-7 | 6.2.14 | On-network / File Distribution (FD) / FD Using HTTP / One-to-one Standalone FD / Non-Mandatory Download / Active functional alias / Client Originated (CO) | TS 24.282, clauses 10.2.1.3.2, 10.2.2.1, 10.2.4.2.1, 12.2.1.2 | NIST | RAN5#104 (Aug-24) | R5-237445 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
91 | Y | 36.579-7 | 6.2.15 | On-network / File Distribution (FD) / FD Using Media Plane / One-to-one Standalone FD / Active Functional Alias / Client Originated (CO) | TS 24.282, clauses 10.2.5.2.3, 6.2.2.3, 12.2.1.2, TS 24.582 clause 7.1.2.1 | NIST | RAN5#104 (Aug-24) | R5-236611 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
92 |  | 36.579-7 | 6.4 | Emergency Alert | New sub-clause header | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
93 | Y | 36.579-7 | 6.4.1 | On-network / Emergency Alert / Cancel Emergency Alert / Client Originated (CO) | 16.2.1.1 Emergency alert origination; 16.2.1.2 Emergency alert cancellation | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
94 | Y | 36.579-7 | 6.4.2 | On-network / Emergency Alert / Client Terminated (CT) | 16.2.1.3 MCData client receives an MCData emergency alert or communication notification | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
95 |  | 36.579-7 | 6.5 | Location | New sub-clause header | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
96 | Y | 36.579-7 | 6.5.1 | On-network / Location / Event Triggered Location Information report | 17.3.2 Location reporting configuration 17.3.4.1 Report triggering 17.3.4.2 Sending location information report | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
97 | Y | 36.579-7 | 6.5.2 | On-network / Location/ On-demand Location Information Request | 17.3.2 Location reporting configuration 17.3.3 Location information request 17.3.4.2 Sending location information report | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
98 |  | 36.579-7 | 6.6 | MBMS transmission usage | New sub-clause header | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
99 | Y | 36.579-7 | 6.6.1 | On-network / MBMS / MBMS Bearer Announcement / MBMS Bearer Listening Status / Transition to MBMS from Unicast / Transition to Unicast from MBMS | 24.282 = 19.3.3.2 Sending the MBMS bearer listening or suspension status report 24.582 = 6.5.2.1 Handling the MSRP connection 6.5.2.2 Receiving Map Group To Bearer and Unmap Group To Bearer 6.5.2.3 Receiving media packets | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
100 |  | 36.579-7 | 6.7 | IP Connectivity | New sub-clause header | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
101 | Y | 36.579-7 | 6.7.1 | On-network / IP Connectivity / Client Originated (CO) | 20.2.1 | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
102 | Y | 36.579-7 | 6.7.2 | On-network / IP Connectivity / Client Terminated (CT) | 20.2.2 | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
103 |  | 36.579-7 | 6.8 | MCData Message Store | New sub-clause header | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
104 | Y | 36.579-7 | 6.8.1 | On-network / MCData Message Store / Objects / Object upload / Object search / Update Object / Object retrieval / Delete stored object | 21.2.15 Object(s) upload procedure 21.2.2 Object search procedure 21.2.3 Update object(s) procedure 21.2.1 Object retrieval procedure 21.2.4 Delete stored object(s) procedure | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
105 | Y | 36.579-7 | 6.8.2 | On-network / MCData Message Store / Folders / Create a folder / Object and folder copy / List subfolders of a given folder / Folder search / Moving object(s) and folder(s) / Deleting a folder | 21.2.8 Create a folder procedure 21.2.6 Object and folder copy procedure 21.2.18 List subfolders of a given folder 21.2.11 Folder search procedure 21.2.10 Moving object(s) and folder(s) procedure 21.2.7 Deleting a folder procedure | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
106 | Y | 36.579-7 | 6.8.3 | On-network / MCData Message Store / Subscription / Create a subscription to notifications / Update a subscription to notifications / Delete a subscription to notifications | 21.2.12A Create a subscription to notifications 21.2.14A Update a subscription to notifications 21.2.13A Delete a subscription to notifications | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
107 | Y | 36.579-7 | 6.8.4 | On-network / MCData Message Store / Synchronization / Synchronization notifications / Search-based synchronization | 21.2.16 Synchronization notifications 21.2.17 Search-based synchronization | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
108 |  | 36.579-7 | 7.3 | Emergency Alert | New sub-clause header | TBD | RAN5#104 (Aug-24) |  |  | 0 | 0% | 0% |  | 0%
109 | Y | 36.579-7 | 7.3.1 | Off-network / Emergency Alert / Emergency Alert Retransmission / Cancel Emergency Alert / Client Originated (CO) | 16.3.3.1 Originating user sending emergency alert 16.3.3.2 Emergency alert retransmission 16.3.3.5 Originating user cancels emergency alert | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
110 | Y | 36.579-7 | 7.3.2 | Off-network / Emergency Alert / Emergency Alert Retransmission / Cancel Emergency Alert / Client Terminated (CT) | 16.3.3.3 Terminating user receiving emergency alert 16.3.3.4 Terminating user receiving retransmitted emergency alert 16.3.3.6 Terminating user receives GROUP EMERGENCY ALERT CANCEL message | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
TS 36.579-8: MCVideo Server Application test cases
|  | 36.579-8 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
111 |  | 36.579-8 | 1 | Scope | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-231912 |  | 0 | 25% | 25% |  | 25%
112 |  | 36.579-8 | 2 | References | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-231912 |  | 0 | 25% | 25% |  | 25%
113 |  | 36.579-8 | 3 | Definitions, symbols and abbreviations | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-231912 |  | 0 | 25% | 25% |  | 25%
114 |  | 36.579-8 | 4 | General | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-231912 |  | 0 | 25% | 25% |  | 25%
115 |  | 36.579-8 | 5 | MCVideo Client Configuration | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-231912 |  | 0 | 100% | 100% |  | 100%
116 | Y | 36.579-8 | 5.1 | MCVideo Server - MCVideo Client / Configuration / Authentication / User Authorisation / UE Configuration / User Profile | Initial authentication and authorization of an MCVideo client | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
117 |  | 36.579-8 | 6 | MCVideo Server - MCVideo Client operation | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-231912 |  | 0 | 100% | 100% |  | 100%
118 | Y | 36.579-8 | 6.1 | MCVideo Server - MCVideo Client / Pre-arranged Group Call | To create a Pre-arranged Group Call | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
119 | Y | 36.579-8 | 6.2 | MCVideo Server - MCVideo Client / Chat Group Calls | To create a Chat Group Calls | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
120 | Y | 36.579-8 | 6.3 | MCVideo Server - MCVideo Client / Conference Event Package | To create a Conference Event Package | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
121 | Y | 36.579-8 | 6.4 | MCVideo Server - MCVideo Client / Remote Change of Selected Group | To create a Remote Change of Selected Group | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
122 | Y | 36.579-8 | 6.5 | MCVideo Server - MCVideo Client / Private Calls | To create a Private Calls | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
123 | Y | 36.579-8 | 6.6 | MCVideo Server - MCVideo Client / Location | To create a Location | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
124 | Y | 36.579-8 | 6.7 | MCVideo Server - MCVideo Client / MBMS | To create a MBMS | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
125 | Y | 36.579-8 | 6.8 | MCVideo Server - MCVideo Client / Emergency Alert | To create a Emergency Alert | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
126 | Y | 36.579-8 | 6.9 | MCVideo Server - MCVideo Client / Video Pull | To create a Video Pull | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
127 | Y | 36.579-8 | 6.1 | MCVideo Server - MCVideo Client / Video Push | To create a Video Push | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
128 | Y | 36.579-8 | 6.11 | MCVideo Server - MCVideo Client / Capability information sharing | To create a Capability information sharing | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
129 | Y | 36.579-8 | 6.12 | MCVideo Server - MCVideo Client / Ambient viewing call | To create a Ambient viewing call | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
130 |  | 36.579-8 | 7 | MCVideo Server - MCVideo Server operation | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-231912 |  | 0 | 100% | 100% |  | 100%
131 | Y | 36.579-8 | 7.1 | MCVideo Server - MCVideo Server / Pre-arranged Group Call | To create a Pre-arranged Group Call | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
132 | Y | 36.579-8 | 7.2 | MCVideo Server - MCVideo Server / Chat Group Calls | To create a Chat Group Calls | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
TS 36.579-9: MCData Server Application test cases
|  | 36.579-9 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
133 |  | 36.579-9 | 1 | Scope | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-231913 |  | 0 | 25% | 25% |  | 25%
134 |  | 36.579-9 | 2 | References | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-231913 |  | 0 | 25% | 25% |  | 25%
135 |  | 36.579-9 | 3 | Definitions, symbols and abbreviations | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-231913 |  | 0 | 25% | 25% |  | 25%
136 |  | 36.579-9 | 4 | General | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-231913 |  | 0 | 25% | 25% |  | 25%
137 |  | 36.579-9 | 5 | MCData Client Configuration | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-231913 |  | 0 | 100% | 100% |  | 100%
138 | Y | 36.579-9 | 5.1 | MCData Server - MCData Client / Configuration / Authentication / User Authorisation / UE Configuration / User Profile | Initial authentication and authorization of an MCData client | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
139 |  | 36.579-9 | 6 | MCData Server - MCData Client operation | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-231913 |  | 0 | 100% | 100% |  | 100%
140 | Y | 36.579-9 | 6.1 | MCData Server - MCData Client / Short Data Service | To create a Short Data Service call | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
141 | Y | 36.579-9 | 6.2 | MCData Server - MCData Client / File Distribution | To create a File Distribution call | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
142 | Y | 36.579-9 | 6.3 | MCData Server - MCData Client / Enhanced Status | To create an Enhanced Status call | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
143 |  | 36.579-9 | 7 | MCData Server - MCData Server operation | New sub-clause header | NIST | RAN5#104 (Aug-24) | R5-231913 |  | 0 | 100% | 100% |  | 100%
144 | Y | 36.579-9 | 7.1 | MCVideo Server - MCVideo Server / Pre-arranged Group Call | To create a Short Data Service call | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
145 | Y | 36.579-9 | 7.2 | MCVideo Server - MCVideo Server / Pre-arranged Group Call | To create a File Distribution call | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
146 | Y | 36.579-9 | 7.3 | MCVideo Server - MCVideo Server / Pre-arranged Group Call | To create an Enhanced Status call | TBD | RAN5#104 (Aug-24) |  |  | 1 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.