## WP scope
Work plan for introduction of NR CA PC2 FR1 configurations into 3GPP UE conformance test specifications
| WP template: | WP NR CA PC2 FR1 v1.6.0
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed.
Workplan scope
| Workplan Name |  | WP NR CA PC2 FR1-CMCC-1bSet0 | [6 empty] | <= Default workplan name is the filename. To change replace the formula with preferred text.
| Company (Contact) |  | CMCC (Luyang Zhao) | [6 empty] | <= Enter Responsible Company and Contact for the configurations in the WP
| Target completion |  | RAN5#101 | [6 empty] | <= Enter target completion date here. Format RAN5#<xx>, where <xx> is the RAN5 meeting, e.g. RAN5#94-e>
Comments
| Overall completion |  | 100%
Target configurations
Note: A work plan can include multiple target configurations but it is recommended to create separate work plans for Intra-band continuous, Intra-band Non-Continuous and Inter-band configurations. Copy target configuration(s) for the WP from the "PRD21 NR bands and 5G NR CADC list" as values in the table below by: 1. Select and copy the complete rows of the target configuration(s) in the "PRD21 NR bands and 5G NR CADC list". 2. Select cell A15 in the table below and right-click. 3. Select paste option "Paste as values" (see picture). It may take a few seconds before the pasted information is shown. 4. To include additional configurations, repeat steps 1 to 3, but in step 2 select the cell in column A next below the last configuration in the list.
Marked config | Release introduced in TS 38.101-x | Type of configuration | TS and Source Table | Configuration | Uplink configuration | PC3 Status | PC2 completed? | RAN5 Completion Meeting (PC3) | Completion Reference (PC3) | Interested operator (PC3) | Responsible Company (contact) (PC3) | Assignment [RAN5 meeting] (PC3) | Applicable RAN5 WI code(s) for CRs | Comments | Introduced in PRD version
| Rel-17 | NR CA FR1 IB cont | 38.101-1:Table 5.5A.1-1 | CA_n41C | n41 PC2 | Ongoing |  |  |  | CMCC | CMCC (Luyang Zhao) | RAN5#99 | NR_PC2_CA_R17_2BDL_2BUL-UEConTest |  | v.1.0.0
v.1.0.0

## WP NR CA PC2 FR1
Work plan for introduction of NR CA PC2 FR1 configurations into 3GPP UE conformance test specifications
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed. | [13 empty] | WP template: WP NR CA PC2 FR1 v1.6.0
1. Configurations covered by the work plan
|  | Type of CA configurations |  |  |  | WP item Applicability Label | CA configurations [DL/UL]
|  | New NR CA configuration with UL CA |  |  |  | DL/UL BCS0 | CA_n41C/n41 PC2
|  | New BCS for NR CA configuration with UL CA |  |  |  | DL/UL new BCS
|  | All configurations |  |  |  | All | CA_n41C/n41 PC2
|  | All BCS0 configurations (No BCS included in config.name) |  |  |  | All BCS0 | CA_n41C/n41 PC2
|  | All new BCS configurations with BCS>0 |  |  |  | All new BCS
2. Overall status vs WP steps
[7 empty] | Overall Sub-WI |  | Handling of not applicable WP item rows: - WP item rows not applicable for the target configurations are indicated as being strikethrough text. You can hide those not applicable WP items by filtering on excluding "(Blanks)" in column "Impacted config(s)". - Some WP items may still not be applicable for the target configurations based on the applicability information in the "Task" column. To NOT include those WP items in the overall status calculations You need to clear the "Detailed Completion Status" cells for the WP item row and state "N/A" in the comments field. Note: It is not recomended to completly delete not applicable WP item rows in case additional target configurations added at a later stage may require those WP Item rows.
|  | Overall completeness |  |  |  |  | 100%
|  | Step 1: Work plan pre-requisite |  |  |  |  | 100%
|  | Step 2: Complete Test Point (TP) analysis for impacted NR CA configurations |  |  |  |  | 100%
Step 3.1: CR(s) to common test environment (TS 38.508-1)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-1)
|  | Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-1, clause 6) |  |  |  |  | 100%
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-1, clause 7)
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
3. Details
Do not edit | [7 empty] | WP item columns to be filled in |  |  |  | Do not edit |  |  | WP item columns to be filled in
Step 1: Work plan pre-requisite
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted config(s) [DL/UL] | Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
PC3 completed
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
All BCS0 | 1-1 | Pre-requisite | PRD21 | 5G NR CADC Configurations worksheet | Corresponding configuration completed for PC3 | CA_n41C/n41 PC2 | Set status in column "PC3 completed" to 100% when all impacted item have been confirmed completed in RAN5 PRD21 worksheet "5G NR CADC Configurations worksheet". |  | RAN5#101 | R5-216625, R5-222238 | CA_n41C PC3 configuration is confirmed completed. | 1 | 100% |  | 100%
All new BCS | 1-2 | Pre-requisite | PRD21 | 5G NR CADC Configurations worksheet | Corresponding configuration completed for PC3 |  | Set status in column "PC3 completed" to 100% when all impacted item have been confirmed completed in RAN5 PRD21 worksheet "5G NR CADC Configurations worksheet". |  | RAN5#101 | R5-216625, |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 2: Complete Test Point (TP) analysis for impacted NR CA configurations
WP item applicability | WP item ID | Area | TR | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
TP analysis
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
All | 2-1 | TP Analysis | 38.905 | 4.1.2 | Test point (TP) analysis for A-MPR | CA_n41C/n41 PC2 | For each UL CA configuration perform an A-MPR TP analysis as described in TR 38.905 clause 4.1.2 for intra-band contiguous UL CA and in clause 4.1.3 for inter-band UL CA. The TP analysis is documented by a CR to 38.905 clause 4.1.x including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required A-MPR TP analysis have been included in TR 38.905. |  | RAN5#101 |  | No changes needed | 1 | 100% |  | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3: CRs to impacted TSs areas
Step 3.1: CR(s) to common test environment (TS 38.508-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
Test Freq.
1
| 3.1-1 | [5 empty] | No changes needed |  | RAN5#101 |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-1)
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Discussion paper | Clause 7
[15 empty] | 1 | 1
All | 3.2-1 | 38.521-1 - General | PRD21 | 4.1 | Discussion paper on adding configuration to chapter 5 without changes to RF transmitter and receiver test cases. | CA_n41C/n41 PC2 | If it is thought there are no configuration specific changes needed for Chapter 6/7, a paper shall be submitted to justify why no such changes are needed to Chapter 6/7. If deemed that no discussion paper is needed then set status to 100% and add comment in the comments column why no discussion paper is needed. |  | RAN5#101 |  |  | 1 | 100% |  | 100%
All | 3.2-2 | 38.521-1 - RF Tx | 38.521-1 | 7.3A.0.4 | Inter-band CA | CA_n41C/n41 PC2 | Add PC2 Reference sensitivity exceptions for inter-band configurations within FR1 to the relevant table. |  | RAN5#101 |  | N/A | 1
All | 3.2-3 | 38.521-1 - RF Tx | 38.521-1 | 7.3A.0.5 | Inter-band CA | CA_n41C/n41 PC2 | Add PC2 Reference sensitivity exceptions for inter-band configurations within FR1 to the relevant table. |  | RAN5#101 |  | N/A | 1
All | 3.2-4 | 38.521-1 - RF Tx | 38.521-1 | 7.3A.0.6 | Inter-band CA | CA_n41C/n41 PC2 | Add PC2 Reference sensitivity exceptions for inter-band configurations within FR1 to the relevant table. |  | RAN5#101 |  | N/A | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-1, clause 6)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
All | 3.3-1 | 38.521-1- RF Tx | 38.521-1 | 6.2A.1.0.3 | UE maximum output power for Inter-band CA | CA_n41C/n41 PC2 | For configurations including any PC2 inter-band UL CA CCs add the UE maximum output power for inter-band UL CA to Table 6.2A.1.0.3-1. |  | RAN5#101 |  | N/A | 1
All | 3.3-2 | 38.521-1- RF Tx | 38.521-1 | 6.2A.1.0.4 | UE maximum output power for Intra-band contiguous CA | CA_n41C/n41 PC2 | For configurations including any PC2 Intra-band contiguous UL CA add the UE maximum output power for Intra-band contiguous UL CA to Table 6.2A.1.0.4-1. |  | RAN5#101 |  | No changes needed | 1 | 100% |  | 100%
All | 3.3-3 | 38.521-1- RF Tx | 38.521-1 | 6.2A.1.0.5 | UE maximum output power for Intra-band non-contiguous CA | CA_n41C/n41 PC2 | For configurations including any PC2 Intra-band non-contiguous UL CA add the UE maximum output power for Intra-band non-contiguous UL CA to Table 6.2A.1.0.5-1. |  | RAN5#101 |  | N/A | 1
All | 3.3-4 | 38.521-1- RF Tx | 38.521-1 | 6.2A.1.1 | UE maximum output power for CA (2UL CA) | CA_n41C/n41 PC2 | For PC2 FR1 Inter-band 2UL CA configurations add the test requirements to Table 6.2A.1.1.5-1a. NOTE: For intra-band contiguous and intra-band non-contiguous UL CA, MPR is always larger than 0. |  | RAN5#101 |  | N/A | 1
All | 3.3-5 | 38.521-1- RF Tx | 38.521-1 | 6.2A.3.0.1 | UE additional maximum output power reduction for Intra-band contiguous CA | CA_n41C/n41 PC2 | For intra-band contiguous CA configurations with PC2 specific A-MPR requirements, add the minimum requirements in 6.2A.3.0.1. |  | RAN5#101 |  | No changes needed | 1 | 100% |  | 100%
All | 3.3-6 | 38.521-1- RF Tx | 38.521-1 | 6.2A.3.0.2 | UE additional maximum output power reduction for Intra-band non-contiguous CA | CA_n41C/n41 PC2 | For intra-band non-contiguous CA configurations with PC2 specific A-MPR requirements, add the minimum requirements in 6.2A.3.0.2. |  | RAN5#101 |  | N/A | 1
All | 3.3-7 | 38.521-1- RF Tx | 38.521-1 | 6.2A.3.1 | UE additional maximum output power reduction for CA (2 UL CA) Note! This WP item is dependent [UDL/UL] on A-MPR TP analysis (Step 2, WP item 5) | CA_n41C/n41 PC2 | For configurations with specific PC2 A-MPR requirements add the Initial Conditions and Test requirement. |  | RAN5#101 |  | N/A | 1
All | 3.3-8 | 38.521-1- RF Tx | 38.521-1 | 6.5A.2.3.0.1 | Additional spectrum emission mask for intra-band contiguous CA | CA_n41C/n41 PC2 | For intra-band contiguous CA configurations with PC2 specific A-MPR requirements related to A-SEM, add the minimum requirements in 6.5A.2.3.0.1. |  | RAN5#101 |  | No changes needed | 1 | 100% |  | 100%
All | 3.3-9 | 38.521-1- RF Tx | 38.521-1 | 6.5A.2.3.0.2 | Additional spectrum emission mask for Intra-band non-contiguous CA | CA_n41C/n41 PC2 | For intra-band non-contiguous CA configurations with PC2 specific A-MPR requirements related to A-SEM, add the minimum requirements in 6.5A.2.3.0.2. |  | RAN5#101 |  | N/A | 1
All | 3.3-10 | 38.521-1- RF Tx | 38.521-1 | 6.5A.2.3.1 | Additional spectrum emission mask for CA (2 UL CA) Note! This WP item is dependent [UDL/UL] on A-MPR TP analysis (Step 2, WP item 5) | CA_n41C/n41 PC2 | For configurations with specific PC2 A-MPR requirements related to A-SEM: - For initial condition, align the tes configuration with A-MPR - Add test requirement |  | RAN5#101 |  | N/A | 1
All | 3.3-11 | 38.521-1- RF Tx | 38.521-1 | 6.5A.3.3.0.1 | Additional spurious emissions for intra-band contiguous CA | CA_n41C/n41 PC2 | For intra-band contiguous CA configurations with PC2 specific A-MPR requirements related to A-SE, add the minimum requirements in 6.5A.3.3.0.1. |  | RAN5#101 |  | No changes needed | 1 | 100% |  | 100%
All | 3.3-12 | 38.521-1- RF Tx | 38.521-1 | 6.5A.3.3.0.2 | Additional spurious emissions for intra-band non-contiguous CA | CA_n41C/n41 PC2 | For intra-band non-contiguous CA configurations with PC2 specific A-MPR requirements related to A-SE, add the minimum requirements in 6.5A.3.3.0.2. |  | RAN5#101 |  | N/A | 1
All | 3.3-13 | 38.521-1- RF Tx | 38.521-1 | 6.5A.3.3.1 | Additional spurious emissions for CA (2 UL CA) Note! This WP item is dependent [UDL/UL] on A-MPR TP analysis (Step 2, WP item 5) | CA_n41C/n41 PC2 | For configurations with specific PC2 A-MPR requirements related to A-SE: - For initial condition, align the tes configuration with A-MPR - Add test requirement |  | RAN5#101 |  | N/A | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-1, clause 7)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
All | 3.4-1 | 38.521-1-RF Rx | 38.521-1 | 7.3A.1_1 | Reference sensitivity power level for 2DL CA exceptions | CA_n41C/n41 PC2 | Add test requirements for any PC2 specifice exceptional requirements for inter-band 2DL CA configurations with FR1 |  | RAN5#101 |  | N/A | 1
All | 3.4-2 | 38.521-1-RF Rx | 38.521-1 | 7.3A.2_1 | Reference sensitivity power level for 3DL CA exceptions | CA_n41C/n41 PC2 | Add test requirements for any PC2 specifice exceptional requirements for inter-band 3DL CA configurations with FR1 |  | RAN5#101 |  | N/A | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
| 3.5-1 | [5 empty] | No changes needed |  | RAN5#101 |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
ICS / TC appli.
1
| 3.6-1 | [5 empty] | No changes needed |  | RAN5#101 |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
ICS / TC appli.
1
All | 4-1 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2A.2.1 | NR CA Intra-band contiguous | CA_n41C/n41 PC2 | Add PC2 indication for Intra-band contiguous CA within FR1 to the relevant table in clause A.4.3.2A.2.1 |  | RAN5#101 |  | No changes needed | 1 | 100% |  | 100%
All | 4-2 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2A.3.1 | NR CA Intra-band non-contiguous | CA_n41C/n41 PC2 | Add PC2 indication for NR Intra-band non-contiguous CA within FR1 to the relevant table in clause A.4.3.2A.3.1 |  | RAN5#101 |  | N/A | 1
All | 4-3 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2A.4 | NR Inter-band CA | CA_n41C/n41 PC2 | Add PC2 indication for NR Inter-band CA within FR1 to the relevant table in clause A.4.3.2A.4 |  | RAN5#101 |  | N/A | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Note on N29: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N37: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N45: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on N52: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N62: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N81: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N89: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N96: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N103: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.

## Revision History WP template
Revision history for WP template only Note! Cell A3 shall always include the version of the latest version of the WP as used to set the WP template version in the WP scope worksheet.
Version | Date | Comment
v1.6.0 | RAN5#100 | 1.Add Reference sensitivity power level for 3DL CA exceptions to Step 3.4 WP item 3.4-2
v1.5.0 | RAN5#99 | 1. Editorial corrections to Step 3.4 table header. 2. Editorial corrections to Step 3.2 WP item 3.2-2, 3.2-3 and 3.2-4
v1.4.0 | RAN5#98 | No changes. Same as v1.3.0.
v1.3.0 | RAN5#97 | No changes. Same as v1.2.0.
v1.2.0 | RAN5#96-e | Initial version