## Cover sheet
3GPP TSG-RAN WG5 Meeting #101 | [8 empty] | R5-236780
Chicago, USA, November 13th to 17th, 2023
Agenda Item: | 7.4.2
Source: | Apple
Title: | WP UE Conformance - Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR UEs
Work item code: | NR_MIMO_OTA-UEConTest
Release: | Rel-17
Document for: | Approval
RAN5 WP template v2.0-8
1. Introduction
The objective of this work item is to enable the UE conformance testing corresponding to NR MIMO OTA WI listed under clause 2.2, by analysing the test cases impact, applicability and test environment. The work item’s outcome shall be captured in TS 38.551.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% | 0 | 0
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 100% | 0 | 0
FR1 |  | 100% | 0 | 0
NSA Option 3 (EN-DC) |  | 100% | 0 | 0
FR1 |  | 100% | 0 | 0
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  |  |  | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  |  | Completion | Number of new completed test cases | Number of new test cases
5GS
MIMO OTA requirements for NR UEs
TS 38.551: common clauses 1-6 |  | 100% | 0 | 0 | 100% | 0 | 0 |  |  | 100% | 0 | 0
TS 38.551: Annexes |  | 100%
5 References
[1] RP-221939 | New WID on UE Conformance - Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR UEs
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance - Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR UEs | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_MIMO_OTA-UEConTest
WP Scope: |  | The objective of this work item is to define the UE conformance requirements corresponding to ‘WI NR_MIMO_OTA-UEConTest’, by analysing the test case impact, applicability and test environment, and updating the relevant conformance specifications. This work item will cover Signaling, Demod and RRM conformance test specifications for NR_feMIMO.
WP Resp: |  | Istvan Szini, Siting Zhu, Thorsten Hertel |  |  | Istvan@apple.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
TS Resp: |  | Istvan Szini |  |  | Istvan@apple.com
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR1
[15 empty] | 100% | 100%
[15 empty] | 8 | 8
[15 empty] | 5.2 | 5.2
50%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR UEs
TS 38.551: General Section
1 |  | 38.551 | 1 | Scope |  | Apple | RAN5#100 (Aug-23) | R5-232702 |  | 0.1 | 100% | 100% | 100% |  | 100% | 100%
2 |  | 38.551 | 2 | References |  | Apple | RAN5#100 (Aug-23) | R5-230843 |  | 0.1 | 100% | 100% | 100% |  | 100% | 100%
3 |  | 38.551 | 3 | Definitions |  | Apple | RAN5#100 (Aug-23) | R5-230842 R5-236788 | Includes full test structure | 0.2 | 100% | 100% | 100% |  | 100% | 100%
4 |  | 38.551 | 4 | General |  | Apple | RAN5#101 (Nov-23) | R5-231804 R5-230844 | Includes full test structure | 0.3 | 100% | 100% | 100% |  | 100% | 100%
5 |  | 38.551 | 5 | Frequency Bands |  | Apple | RAN5#100 (Aug-23) | R5-230848 R5-232703 | Core spec. alignment with TS 38.151 | 1 | 100% | 100% | 100% |  | 100% | 100%
6 |  | 38.551 | 6 | FR1 MIMO OTA Performance |  | Apple | RAN5#101 (Nov-23) | R5-230847 R5-232704 | Includes full test structure including Test Requirements | 1 | 100% | 100% | 100% |  | 100% | 100%
TS 38.551: Annexes
7 |  | 38.551 | Annex A | FR1 Test methodology |  | Apple | RAN5#100 (Aug-23) | R5-231803 R5-231803 | Includes full test structure including Test Requirements | 1 | 100% | 100% | 100% |  | 100% | 100%
8 |  | 38.551 | Annex B | MU Budget |  | Apple | RAN5#101 (Nov-23) | R5-231803 R5-232699 R5-237844 R5-237845 | Includes full test structure inclusing final MU analysis | 1 | 100% | 100% | 100% |  | 100% | 100%
9 |  | 38.551 | Annex C | FR1 Channel models and Validation procedure |  | Apple | RAN5#100 (Aug-23) | R5-231803 R5-232701 R5-237846 | Core spec. alignment with TS 38.151 | 1 | 100% | 100% | 100% |  | 100% | 100%
10 |  | 38.551 | Annex D | gNB configurations |  | Apple | RAN5#101 (Nov-23) | R5-231805 R5-231803 | Core spec. alignment with TS 38.151 | 0.7 | 100% | 100% | 100% |  | 100% | 100%
11 |  | 38.551 | Annex E | Environmental requirements |  | Apple | RAN5#100 (Aug-23) | R5-231803 | Core spec. alignment with TS 38.151 | 0.4 | 100% | 100% | 100% |  | 100% | 100%
12 |  | 39.551 | Annex F | Change history |  | Apple | RAN5#101 (Nov-23) | R5-231803 |  | 0.1 | 100% | 100% | 100% |  | 100% | 100%
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.