## Cover sheet
3GPP TSG-RAN WG5 Meeting #101 | [8 empty] | R5-236858
Chicago, USA, 13th – 17th Nov, 2023
Agenda Item: | 7.5.2
Source: | CATT, Huawei
Title: | WP UE Conformance - NR sidelink enhancement
Work item code: | NR_SL_enh-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% (+5%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
PC5 (FR1) |  | 5% (+5%)
FR1 |  | 5% (+5%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | PC5
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF, Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0%
Common ICS | 38.508-2 | 0% |  |  | 0%
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1 | 0% |  |  | 0%
FR1 RF Tx test cases | 38.521-1 Tx | 0% |  |  | 0%
FR1 RF Rx test cases | 38.521-1 Rx | 0% |  |  | 0%
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% |  |  | 0%
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-yyxxxx | <WID document title>
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - NR sidelink enhancement | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_SL_enh-UEConTest
WP Scope: |  | The objective of this work item is to specify solutions to UE conformance testing corresponding to the features described in WID of NR Sidelink enhancement, including protocol, RF and RRM test cases and associated test environment, test applicability, etc.
WP Resp: |  | Xiaozhong CHEN |  |  | chenxiaozhong@catt.cn | [5 empty] | WP item completion |  |  | PC5
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | PC5 |  | FR1
5% (+5%)
87 (+87)
66.3 (+66.3)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-1 | 4.3.1.8 | Test frequencies for NR Sidelink operating bands | [New V2X band n14 and n79] To add Test frequencies for NR V2X test |  | RAN5#99 (May-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.508-1 | 4.10.1 | Pre-configuration for V2X | [PC1 and PC2] To add pre-configuration for PC1 and PC2 V2X testing |  | RAN5#99 (May-23) |  | Contributions could be accepted only when the PC1 and PC2 on relevant band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.508-1 | 6.2.3 | Test frequencies for signalling testing | [New V2X band n14 and n79] To add Test frequencies for NR V2X test |  | RAN5#99 (May-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-2 | A.4.3.10 | PICs for NR SL testing | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | RAN5#99 (May-23) |  |  | 1 | 0% | 0% |  | 0%
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-1 | 5 | Operating bands and Channel arrangement | [New V2X band n14 and n79] define the frequency bands and channel arragement |  | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 | Annex A | measurement channels | [New V2X band n14 and n79] Define mesurement channels |  | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT |  | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  | 0%
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-1 Tx | 6.1E | General | Adding common RB allocations |  | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.1 | UE maximum output power for V2X | Sub-clause heading |  |  |  |  | 0
TBD |  | 38.521-1 Tx | 6.2E.1.0 | Minimum conformance requirements | [New V2X band n14 and n79] [PC1 and PC2] [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,2E.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.1.1 | UE maximum output power for V2X / non-concurrent operation | [New V2X band n14 and n79] [PC1 and PC2] TS 38.101-1 cl 6,2E.1.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.1.1D | UE maximum output power for V2X / non-concurrent operation / SL-MIMO | [New V2X band n14 and n79] [PC1 and PC2] TS 38.101-1 cl 6,2E.1.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.1.2 | UE maximum output power for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,2E.1.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.2 | UE maximum output power reduction for V2X | Sub-clause heading |  |  |  |  | 0
TBD |  | 38.521-1 Tx | 6.2E.2.0 | Minimum conformance requirements | [PC1 and PC2] [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,2E.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.2.1 | UE maximum output power reduction for V2X / non-concurrent operation | [PC1 and PC2] TS 38.101-1 cl 6,2E.2.1, 6.2E.2.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.2.1D | UE maximum output power reduction for V2X / non-concurrent operation / SL-MIMO | [PC1 and PC2] TS 38.101-1 cl 6,2E.2.1, 6.2E.2.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.2.2 | UE maximum output power reduction for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,2E.2.3 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.3 | UE additional maximum output power reduction for V2X | Sub-clause heading |  |  |  |  | 0
TBD |  | 38.521-1 Tx | 6.2E.3.0 | Minimum conformance requirements | [PC1 and PC2] [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,2E.3 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.3.1 | UE additional maximum output power reduction for V2X / non-concurrent operation | [PC1 and PC2] TS 38.101-1 cl 6,2E.3.1, 6.2E.3.2, 6.2E.3.3 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.3.1D | UE additional maximum output power reduction for V2X / non-concurrent operation / SL-MIMO | [PC1 and PC2] TS 38.101-1 cl 6,2E.3.1, 6.2E.3.2, 6.2E.3.3 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.3.2 | UE additional maximum output power reduction for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,2E.3.4 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.4 | Configured transmitted power for V2X | Sub-clause heading |  |  |  |  | 0
TBD |  | 38.521-1 Tx | 6.2E.4.0 | Minimum conformance requirements | [PC1 and PC2] [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,2E.4 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.4.1 | Configured transmitted power for V2X / non-concurrent operation | [PC1 and PC2] TS 38.101-1 cl 6,2E.4.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.4.1D | Configured transmitted power for V2X / non-concurrent operation / SL-MIMO | [PC1 and PC2] TS 38.101-1 cl 6,2E.4.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.2E.4.2 | Configured transmitted power for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,2E.4.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.3E.1.0 | Minimum conformance requirements | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,3E.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.3E.1.2 | Minimum output power for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,3E.1.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.3E.2.0 | Minimum conformance requirements | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,3E.2.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.3E.2.2 | Transmit OFF power for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,3E.2.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.3E.3.0 | Minimum conformance requirements | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6.3E.3 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.3E.3.1.2 | General time mask for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6.3E.3.4 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.3E.3.2.2 | S-SSB time mask for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6.3E.3.4 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.3E.4.0 | Minimum conformance requirements | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,3E.4 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.3E.4.1.2 | Absolute power tolerance for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,3E.4.3 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.4E.1.0 | Minimum conformance requirements | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,4E.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.4E.1.2 | Frequency error for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,4E.1.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.4E.2.1 | Minimum conformance requirements | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,4E.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.4E.2.2.2 | Error Vector Magnitude for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,4E.2.6 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.4E.2.3.2 | Carrier leakage for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,4E.2.6 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.4E.2.4.2 | In-band emissions for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,4E.2.6 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.4E.2.5.2 | EVM equalizer spectrum flatness for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,4E.2.6 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.1.0 | Minimum conformance requirements | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,5E.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.1.2 | Occupied bandwidth for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,5E.1.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.2 | Spectrum emission mask for V2X | Sub-clause heading |  |  |  |  | 0
TBD |  | 38.521-1 Tx | 6.5E.2.2.0 | Minimum conformance requirements | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,5E.2.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.2.1 | Spectrum emission mask for V2X / non-concurrent operation | [PC1 and PC2] TS 38.101-1 cl 6,5E.2.2.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.2.1D | Spectrum emission mask for V2X / non-concurrent operation / SL-MIMO | [PC1 and PC2] TS 38.101-1 cl 6,5E.2.2.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.2.2 | Spectrum emission mask for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,5E.2.2.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.3 | Additional Spectrum emission mask for V2X | Sub-clause heading |  |  |  |  | 0
TBD |  | 38.521-1 Tx | 6.5E.2.3.0 | Minimum conformance requirements | [New V2X band n14 and n79] [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,5E.2.3 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.3.1 | Additional Spectrum emission mask for V2X / non-concurrent operation | [New V2X band n14 and n79] [PC1 and PC2] TS 38.101-1 cl 6,5E.2.3.1, 6,5E.2.3.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.3.1D | Additional Spectrum emission mask for V2X / non-concurrent operation / SL-MIMO | [New V2X band n14 and n79] [PC1 and PC2] TS 38.101-1 cl 6,5E.2.3.1, 6,5E.2.3.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.3.2 | Additional Spectrum emission mask for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,5E.2.3.3 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.4 | Adjacent channel leakage ratio for V2X | Sub-clause heading |  |  |  |  | 0
TBD |  | 38.521-1 Tx | 6.5E.2.4.0 | Minimum conformance requirements | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,5E.2.4 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.4.1 | Adjacent channel leakage ratio for V2X / non-concurrent operation | [PC1 and PC2] TS 38.101-1 cl 6,5E.2.4.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.4.1D | Adjacent channel leakage ratio for V2X / non-concurrent operation / SL-MIMO | [PC1 and PC2] TS 38.101-1 cl 6,5E.2.4.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.2.4.2 | Adjacent channel leakage ratio for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,5E.2.4.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.3.2.0 | Minimum conformance requirements | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,5E.3.2, 6.5E.3.3 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.3.2.2 | Spurious emissions for UE co-existence / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6,5E.3.3 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.4.0 | Minimum conformance requirements | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6.5E.4 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Tx | 6.5E.4.2 | Transmit intermodulation for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 6.5E.4.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TS 38.521-1: FR1 RF test cases - Rx
|  | 38.521-1 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-1 Rx | 7.3E | Reference sensitivity for V2X | Sub-clause heading |  |  |  |  | 0
TBD |  | 38.521-1 Rx | 7.3E.1 | Minimum conformance requirements | [New V2X band n14 and n79] [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 7.3E.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.3E.2 | Reference sensitivity for V2X / non-concurrent operation | [New V2X band n14 and n79] TS 38.101-1 cl 7.3E.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.3E.3 | Reference sensitivity for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 7.3E.3 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.4E | Maximum input level for V2X | Sub-clause heading |  |  |  |  | 0
TBD |  | 38.521-1 Rx | 7.4E.0 | Minimum conformance requirements | [New V2X band n14] [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 7.4E |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.4E.1 | Maximum input level for V2X / non-concurrent operation | [New V2X band n14 and n79] TS 38.101-1 cl 7.4E.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.4E.2 | Maximum input level for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 7.4E.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.5E | Adjacent channel selectivity for V2X | Sub-clause heading |  |  |  |  | 0
TBD |  | 38.521-1 Rx | 7.5E.0 | Minimum conformance requirements | [New V2X band n14] [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 7.5E |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.5E.1 | Adjacent channel selectivity for V2X / non-concurrent operation | [New V2X band n14] TS 38.101-1 cl 7.5E.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.5E.2 | Adjacent channel selectivity for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 7.5E.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.6E.2 | In-band blocking for V2X | Sub-clause heading |  |  |  |  | 0
TBD |  | 38.521-1 Rx | 7.6E.2.0 | Minimum conformance requirements | [New V2X band n14] [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 7.6E.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.6E.2.1 | In-band blocking for V2X / non-concurrent operation | [New V2X band n14] TS 38.101-1 cl 7.6E.2.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.6E.2.2 | In-band blocking for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 7.6E.2.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.6E.3 | Out-of-band blocking for V2X | Sub-clause heading |  |  |  |  | 0
TBD |  | 38.521-1 Rx | 7.6E.3.0 | Minimum conformance requirements | [New V2X band n14] [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 7.6E.3 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.6E.3.1 | Out-of-band blocking for V2X / non-concurrent operation | [New V2X band n14] TS 38.101-1 cl 7.6E.3.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.6E.3.2 | Out-of-band blocking for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 7.6E.3.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.7E | Spurious response for V2X | Sub-clause heading |  |  |  |  | 0
TBD |  | 38.521-1 Rx | 7.7E.0 | Minimum conformance requirements | [New V2X band n14] [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 7.7E |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.7E.1 | Spurious response for V2X / non-concurrent operation | [New V2X band n14] TS 38.101-1 cl 7.7E.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.7E.2 | Spurious response for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 7.7E.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.8E.2 | Wide band Intermodulation for V2X | Sub-clause heading |  |  |  |  | 0
TBD |  | 38.521-1 Rx | 7.8E.2.0 | Minimum conformance requirements | [New V2X band n14] [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 7.8E.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.8E.2.1 | Wide band Intermodulation for V2X / non-concurrent operation | [New V2X band n14] TS 38.101-1 cl 7.8E.2.1 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-1 Rx | 7.8E.2.2 | Wide band Intermodulation for V2X / con-current operation | [Intra-band contigous con-currrent operation (n79B)] TS 38.101-1 cl 7.8E.2.2 |  | RAN5#100 (Aug-23) |  | Contributions could be accepted only when the band is 'Ongoing' in PRD21 | 1 | 0% | 0% |  | 0%
TS 38.521-4: Demod/QSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
TBD |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-1 |  | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.522 | 4.1.4 | Performance conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-4. |  | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced for 38.533. |  | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  | 0%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.533 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.533 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.533 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | To add TT analysis for NR sidelink RRM test cases. |  | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.905 | 4.1 | Test point analysis for FR1 test cases in TS 38.521-1 | To add test point analysis for NR sidelink TCs |  | RAN5#100 (Aug-23) |  |  | 1 | 0% | 0% |  | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
PC5-only operation
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1 | 0% | 0% |  | 0%
Inter-carrier concurrent operation
TBD |  | 38.523-1 | 12.2 | Inter-carrier concurrent operation |  |  | TBD |  |  | 0
|  |  | 12.2.11 | Inter-concurrent operation / DRX operation
TBD | Y | 38.523-1 | 12.2.11.1 | Inter-concurrent operation / DRX operation / Behaviour of UE receving SL-SCH Data | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | 12.2.11.2 | Inter-concurrent operation / DRX operation / Behaviour of UE transmitting SL-SCH Data | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.523-2 | 4.1 | Applicibility for NR sidelink enhancement test cases | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD |  |  | 0.1 | 0% | 0% |  | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.