## Cover sheet
3GPP TSG-RAN WG5 Meeting #101 | [8 empty] | R5-237273
Chicago, USA, Nov 13-17, 2023
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | WP UE Conformance- Introduction of DL 1024 QAM for NR Frequency Range 1 (FR1)
Work item code: | NR_DL1024QAM_FR1-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% | 14 (+9) | 14 (+8)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 100% | 14 (+9) | 14 (+8)
FR1 |  | 100% | 14 (+9) | 14 (+8)
NSA Option 3 (EN-DC) |  | 100% | 14 (+9) | 14 (+8)
FR1 |  | 100% | 14 (+9) | 14 (+8)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  |  |  | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  |  | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% |  |  | 100% |  |  |  |  | 100%
Common ICS | 38.508-2 | 100% |  |  | 100% |  |  |  |  | 100%
UE specific testing functions | 38.509 | 100% (+100%) |  |  | 100% (+100%) |  |  |  |  | 100% (+100%)
RF Transmitter and Receiver performance (conducted requirements) | 38.521-1 | 100% (+11.7%) | 4 (-1) | 4 (-2) | 100% (+13.4%) | 4 (-1) | 4 (-2) |  |  | 100% (+9.3%) | 4 (-1) | 4 (-2)
Demodulation performance requirements (conducted requirements) | 38.521-4 | 100% | 10 (+5) | 10 (+4) | 100% | 10 (+5) | 10 (+4) |  |  | 100% | 10 (+5) | 10 (+4)
5 References
[1] RP-221240 | New WID on UE Conformance - Introduction of DL 1024 QAM for NR FR1
[2] R5-231339 | WP UE Conformance Test Aspects - Introduction of DL 1024QAM for NR frequency range 1 (FR1)
[3] R5-232849 | WP UE Conformance Test Aspects - Introduction of DL 1024QAM for NR frequency range 1 (FR1)
[4] R5-234271 | WP UE Conformance Test Aspects - Introduction of DL 1024QAM for NR frequency range 1 (FR1)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance- Introduction of DL 1024 QAM for NR Frequency Range 1 (FR1) | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_DL1024QAM_FR1-UEConTest
WP Scope: |  | This part of the work plan covers all applicable test cases for DL 1024 QAM for NR Frequency Range 1 (FR1) Work item
WP Resp: |  | Vijay Balasubramanian |  |  | vijayb@qti.qualcomm.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR1
[15 empty] | 100% | 100%
[15 empty] | 28 (+8) | 21 (+6)
[15 empty] | 25.7 (+7) | 19.2 (+5.5)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
15 |  | 38.508-1 | 4, 5 | Introduction of General and RF Demod Test Environment for Rel17 DL 1024QAM | [5 empty] | 1 | 100% | 100% | 100% |  | 100% | 100%
TS 38.508-2: Common ICS
16 |  | 38.508-2 | TBD | Introduction of common implementation conformance statements for Rel-17 DL 1024QAM |  | Qualcomm |  | R5-227709 |  | 1 | 100% |  | 100% |  | 100% | 100%
TS 38.509: UE specific testing functions
|  | 38.509 | TBD | TBD |  |  |  |  | No change needed | 1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.521-1: RF Transmitter and Receiver performance (conducted requirements)
21 |  | 38.521-1 | 7 | General | Exisiting sub-clause header |  |  |  |  | 0.5 | 100% | 100% | 100% |  | 100% | 100%
22 | Y | 38.521-1 | 7.4 | Maximum input level | 38.101-1 requirements in clause 7.4 | Qualcomm |  | R5-235458 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
23 | Y | 38.521-1 | 7.4A.1 | Maximum input level for CA (2DL CA) | 38.101-1 requirements in clause 7.4A | Qualcomm |  | R5-235459 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
24 | Y | 38.521-1 | 7.4A.2 | Maximum input level for CA (3DL CA) | 38.101-1 requirements in clause 7.4A | Qualcomm |  | R5-235459 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
25 | Y | 38.521-1 | 7.4A.3 | Maximum input level for CA (4DL CA) | 38.101-1 requirements in clause 7.4A | Qualcomm |  | R5-235459 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
TS 38.521-4: Demodulation performance (conducted requirements)
1 |  | 38.521-4 | 5.1 | General | Exisiting sub-clause header |  |  |  |  | 0.5 | 100% | 100% | 100% |  | 100% | 100%
2 | Y | 38.521-4 | 5.2.2.1.1_3 | 2Rx FDD FR1 PDSCH mapping Type A performance - 2x2 MIMO with baseline receiver for both SA and NSA (DL 1024QAM) | 38.101-4 requirements in TC 5.2.2.1.1 subtest 1-8 | Qualcomm |  | R5-227811 R5-233751 R5-235874 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
3 | Y | 38.521-4 | 5.2.2.2.1_3 | 2Rx TDD FR1 PDSCH mapping Type A performance - 2x2 MIMO with baseline receiver for both SA and NSA (DL 1024QAM) | 38.101-4 requirements in TC 5.2.2.2.1 subtest 1-12 | Qualcomm |  | R5-227812 R5-233751 R5-235874 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
4 | Y | 38.521-4 | 5.2.3.1.1_5 | 4Rx FDD FR1 PDSCH mapping Type A performance - 2x4 MIMO with baseline receiver for both SA and NSA (DL 1024QAM) | 38.101-4 requirements in TC 5.2.3.1.1 subtest 1-8 |  |  | R5-227811 R5-233751 R5-235874 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
5 | Y | 38.521-4 | 5.2.3.2.1_5 | 4Rx TDD FR1 PDSCH mapping Type A performance - 2x4 MIMO with baseline receiver for both SA and NSA (DL 1024QAM) | 38.101-4 requirements in TC 5.2.3.2.1 subtest 1-12 | Qualcomm |  | R5-227812 R5-233751 R5-235874 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
6 | Y | 38.521-4 | 5.5.1_1 | FR1 Sustained downlink data rate performance for single carrier (DL 1024QAM) | 38.101-4 requirements in TC 5.5.1 |  |  | R5-235873 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
7 | Y | 38.521-4 | 5.5A.1.1_1 | FR1 SDR performance for CA (2DLCA) with DL 1024QAM | 38.101-4 requirements in TC 5.5A.1 |  |  | R5-235873 |  | 1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.521-4: CSI reporting requirements (conducted requirements)
8 |  | 38.521-4 | 6.1 | General | Exisiting sub-clause header |  |  |  |  | 0.2 | 100% | 100% | 100% |  | 100% | 100%
17 | Y | 38.521-4 | 6.2.2.1.1.3 | 2Rx FDD FR1 periodic CQI reporting with Table 4 under AWGN conditions for both SA and NSA |  | Qualcomm |  | R5-234282 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
18 | Y | 38.521-4 | 6.2.2.2.1.4 | 2Rx TDD FR1 periodic CQI reporting with Table 4 under AWGN conditions for both SA and NSA |  | Qualcomm |  | R5-234282 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
19 | Y | 38.521-4 | 6.2.3.1.1.3 | 4Rx FDD FR1 periodic CQI reporting with Table 4 under AWGN conditions for both SA and NSA |  | Qualcomm |  | R5-234282 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
20 | Y | 38.521-4 | 6.2.3.2.1.4 | 4Rx TDD FR1 periodic CQI reporting with Table 4 under AWGN conditions for both SA and NSA |  | Qualcomm |  | R5-234282 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
TS 38.521-1: Annex
26 |  | 38.521-1 | Annex A | Measurements Channels |  | Qualcomm |  | R5-234044 |  | 0.5 | 100% | 100% |  |  | 100%
27 |  | 38.521-1 | Annex F | Measurement uncertainties and test tolerances |  | Qualcomm |  | R5-235458 R5-235459 |  | 1 | 100% | 100% |  |  | 100%
TS 38.521-4: Annex
9 |  | 38.521-4 | Annex A | Measurements Channels |  | Qualcomm |  | R5-233751 R5-234044 |  | 1 | 100% | 100% |  |  | 100%
10 |  | 38.521-4 | Annex B | Propagation conditions |  | Qualcomm |  | R5-233751 R5-235876 |  | 1 | 100% | 100% |  |  | 100%
11 |  | 38.521-4 | Annex C | Downlink physical channels |  | Qualcomm |  |  |  | 1 | 100% | 100% |  |  | 100%
12 |  | 38.521-4 | Annex F | Measurement uncertainties and test tolerances |  | Qualcomm |  | R5-235874 R5-237696 |  | 1 | 100% | 100% |  |  | 100%
13 |  | 38.521-4 | Annex G | Statistical testing |  | Qualcomm |  | R5-235875 R5-237696 |  | 1 | 100% | 100% |  |  | 100%
TS 38.522: Applicability for Demodulation and CSI test cases
14 |  | 38.522 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.521-4 |  | Qualcomm |  | R5-227872 R5-235874 |  | 1 | 100% | 100% | 100% |  | 100% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.