## Slide 1: MCC TF160 Status Report
Olivier Genoud
Task Force 160 Leader, 3GPP MCC

## Slide 2
TTCN workflow Simplified view
Note: Each step above has a feedback loop to any previous step(s) (e.g. prose/TTCN bug report).
Who:
RAN5_SIG
TF160 +
SS Vendors
TF160
SS Vendor(s) +
UE Vendor(s) +
TF160
Where:
RAN5 meeting
TTCN Workshop
ETSI
SS/UE Vendor
lab
scope of this report
Notes: ASP: Abstract Service Primitive
SS: System Simulator
TTCN: Testing and Test Control Notation (version 3)
UE: User Equipment

## Slide 3
Test Models – 5G:
  Rel-15:
    Proposed a prose + TTCN solution for handling UEs which do not trigger autonomously a new PDU on a new RRC connection.
    Proposed test model updates for intra-frequency multi-cells test cases, to prevent/mitigate the inter-cell PDCCH clash for SIB1 & Other SI.
    NR CA: endorsed clarification for UL Grant on SCell for PUCCH SR received on PSCell.
    Endorsed enhancement of NR processing delay procedure for RRC resume.
  Rel-17:
    RedCap:
      Endorsed test model updates to support SIB1 of size higher than 1032 bits.
      Endorsed test model & ASP updates to support NCD-SSB.
    MUSIM: endorsed update to MMI command, to add USIM ID when removing USIM.
  Prose CRs to TS 38.523-3, 38.508-1, 38.508-2, 36.523-3 submitted at RAN5#101 for the above.
Test models & system interface design Progress at TTCN Workshop #63 (24th Oct’23)
Notes: ASP: Abstract Service Primitive

## Slide 4
Test Models – NB-IoT:
  Rel-17 NTN:
    Endorsed test model updates for NTN timing & scheduling aspects.
    Proposed NTN NGSO test model & associated ASP updates.
  Prose CR to TS 36.523-3 submitted at RAN5#101 for the above.
Test Models – MCX:
  Clarified codec requirements on TTCN type definitions for MCPTT Floor Control and MCVideo Transmission Control messages.
  Prose CR to TS 36.579-5 submitted at RAN5#101 for the above.
Test Models – Upper Tester:
  Clarified handling of UT commands before timers.
RAN5 TTCN Workshop #63 material:
  https://portal.3gpp.org/Home.aspx#/meeting?MtgId=60563
Test models & system interface design Progress at TTCN Workshop #63 (24th Oct’23)
Notes: ASP: Abstract Service Primitive

## Slide 5: TTCN development Progress for period: Sep to Nov’23
Completed:
  5G Rel-15:
    UAC access id 0 - AC7
  5G Rel-16:
    NR 2-step RACH
  5G Rel-17:
    NR UL data compression
  POS:
    Rel-16 NR positioning
    Rel-17 NR positioning enhancements
Progressed 5G:
  5G Rel-16:
    V2X
    MR-DC & NR CA enhancements
    Redirection with MPS Indication
  5G Rel-17:
    RedCap
    NR RAN slicing enhancements
    SON/MDT enhancements
    NR UE power saving enhancements
Started:
  5G Rel-17:
    Non-public networks (NPN) enhancements
    NR Multi-SIM
    EN-DC user-plane integrity protection
Progressed 4G:
  NB-IoT:
    Rel-17 Non-terrestrial networks (NTN) GSO
  Mission Critical:
    Rel-16 MCData over LTE
Notes: Completed: The TTCN of all test cases is ready for verification.
Progressed: TTCN development ongoing, not yet completed.
Started: TTCN development has started since last report.
Suspended: TTCN development on hold due to external blocker.

## Slide 6: TTCN verification Progress for period: 16th Aug --> 7th Nov’23
Completed:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
IMS eCall over NR/5GC (34.229) | Rel-16 | 537 | 5 / 5 | +3 | 
Inter-RAT SON/MDT | Rel-16 | none | 4 / 4 | +1 | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 7: TTCN verification Progress for period: 16th Aug --> 7th Nov’23
Progressed – 5G (EN-DC, NR/5GC):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
EN-DC access stratum | Rel-15 | 503 | 95 / 102 | = | +1 under verification
NR/5GC access stratum | Rel-15 | 503 | 151 / 160 | = | Prio1: 92/95 ; Prio2: 59/65
NR/5GC NR-DC | Rel-15 | 503 | 11 / 13 | = | Prio1: 9/11 ; Prio2: 2/2
NR/5GC NAS | Rel-15 | 504 | 75 / 76 | = | Prio1: 35/35 ; Prio2: 40/41
NR/5GC NR CA | Rel-15 | 510 | 30 / 32 | = | Prio1: 14/15 ; Prio2: 16/17
EN-DC NR CA | Rel-15 | 512 | 14 / 17 | +1 | Prio1: 13/13 ; Prio2: 1/4
5G private network - SNPN | Rel-16 | 518 | 7 / 9 | = | Prio1: 3/3 ; Prio2: 3/4
NR mobility enhancements | Rel-16 | 522 | 10 / 13 | = | Prio1: 5/7 ; Prio2: 5/6
NR UE power saving | Rel-16 | 533 | 3 / 9 | +1 | 
NR RRC DL segmentation | Rel-16 | 538 | 1 / 2 | = | 
MR-DC & NR CA enhancements | Rel-16 | none | 3 / 28 | = | +3 under verification
NR reduced capability (RedCap) | Rel-17 | 530 | 4 / 8 | = | Prio1: 4/4 ; Prio2: 0/2 +1 under verification
5G network slicing enhancements – Phase 2 | Rel-17 | none | 4 / 13 | +2 | +4 under verification
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 8: TTCN verification Progress for period: 16th Aug --> 7th Nov’23
Progressed – IMS, Positioning, MCX:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
LTE positioning | Rel-9+ | 166, RTF-115 | 17 / 27 | = | 
MCPTT over LTE | Rel-14 | 288, RFT-153 | 38 / 51 | +1 | Prio1: 29/38 ; Prio2: 9/13
IMS eCall over LTE (34.229) | Rel-14 | 298 | 5 / 12 | = | 
MCData over LTE | Rel-14 | 329, RFT-153 | 4 / 28 | = | Prio1: 4/22 ; Prio2: 0/6
MCPTT enhancements over LTE | Rel-15 | 330, RFT-153 | 5 / 22 | +3 | Prio1: 3/14 ; Prio2: 2/8
IMS over NR/5GC | Rel-15 | 505 | 92 / 94 | = | Prio1: 19/19 ; Prio2: 73/75
5G Positioning | Rel-15 | 506 | 9 / 10 | = | Left: TC 9.3.3.1B
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 9: TTCN verification Progress for period: 16th Aug --> 7th Nov’23
Progressed – 4G (LTE, eMTC, NB-IoT):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
CA intra-band contiguous | Rel-11 | 162 | 20 / 21 | = | Left: TC 7.1.2.11.1(multiple TA)
SCE-PHY | Rel-12 | 245 | 6 / 9 | = | 
eDRX | Rel-13 | 253 | 4 / 5 | = | Left: TC 9.2.4.1.3(emergency call)
eMTC (CAT-M1) | Rel-13 | 254-A | 14 / 15 | = | Left: TC 7.1.4.3a(Lch prioritization)
eMTC (CIoT) | Rel-13 | 254-C | 2 / 5 | = | 
NB-IoT (CAT-NB1) | Rel-13 | 257 | 72 / 73 | = | Left: TCs 22.1.1.M2
LAA | Rel-13 | 272 | 1 / 2 | = | Left: TC 8.3.1.32(RSSI measurement)
eNB-IoT | Rel-14 | 295 | 11 / 14 | = | Left: SC-PTM (in iWD-003), IRAT with E-UTRA
IMS eCall over LTE (36.523) | Rel-14 | 298 | 3 / 9 | = | 
Notes: Progress: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 10: TTCN verification Progress for period: 16th Aug --> 7th Nov’23
Started:
Starting:
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
MPS Priority Indication | Rel-16 | none | 1 / 4 | +1 | 
NB-IoT NTN | Rel-17 | 333_NB | 2 / 7 | +2 | Prio1: 2/6 ; Prio2: 0/1 +4 under verification
5G CP SOR enhancements in connected mode | Rel-17 | 534 | 3 / 6 | +3 | +1 under verification
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
UAC access id 0 - AC7 | Rel-15 | none | 0 / 1 |  | +1 under verification
IMS eCall over NR/5GC (38.523) | Rel-16 | 537 | 0 / 15 |  | +2 under verification
Notes: Started: lists the features for which at least one (first) test case has been submitted and agreed since the last report.
Starting: lists the feature for which no test case has yet been verified, but at least one submission has been made, which is under review (consultation period still running).

## Slide 11
2022 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2023 WkLoad | TTCN Status (as of Nov’23) / Comments
5GS: NE-DC (option 4) | Rel-15 | N,L | Q4’23 | 34 | Q1’22-Q4’23 | 1 | 76% (@iwd-23wk24)
5G V2X with NR sidelink | Rel-16 | N,L | Q2’24 | 72 | Q4’20-Q2’24 | 2 | 47% (@iwd-23wk37)
MR-DC & NR CA enhancements | Rel-16 | N,L | Q2’23 | 28 | Q1’22-Q3’23 | 1 | 85% (@iwd-23wk37)
NR in unlicensed spectrum (NR-U) | Rel-16 | N | Q2’24 | 14 | Q1’22-Q2’24 | 2 | 2% ; Test Model work
IMS eCall over NR | Rel-16 | N | Q1’23 | 20 | Q3’21-Q1’23 | 0.5 | 100% (@iwd-23wk12)
NR positioning | Rel-16 | N | Q3’23 | 29 | Q2’21-Q3’23 | 0.2 | 100% (@iwd-23wk37)
NR MIMO enhancements | Rel-16 | N | Q4’22 | 1 | Q4’22-Q1’24 | 0.3 | 2% ; Test Model work
NR 2-step RACH | Rel-16 | N | Q4’22 | 10 | Q3’22-Q3’23 | 1 | 100% (@iwd-23wk37)
NW slicing enhancements - Phase2 | Rel-17 | N | Q2’23 | 13 | Q4’22-Q2’23 | 0.5 | 100% (@iwd-23wk24)
NR & MR-DC SON/MDT enhancements | Rel-17 | N,L | Q3’23 | >11 | Q4’22-Q4’23 | 2 | 70% (@iwd-23wk37)
Reduced capability NR UE (RedCap) | Rel-17 | N | Q1’24 | >12 | Q4’22-Q1’24 | 1.5 | 92% (@iwd-23wk37)
NR multi/broadcast services (MBS) | Rel-17 | N | Q4’23 | 45 | Q4’22-Q1’24 | 4 | Not started
LTE/NR multi-USIM UE (MUSIM) | Rel-17 | N,L | Q3’23 | 14 | Q4’22-Q1’24 | 1.5 | 28% (@iwd-23wk37)
NR UE power saving enhancements | Rel-17 | N | Q3’23 | 5 | Q4’22-Q4’23 | 1.5 | 80% (@iwd-23wk37)
NR RAN slicing enhancements | Rel-17 | N | Q3’23 | 8 | Q4’22-Q4’23 | 1.5 | 87% (@iwd-23wk37)
NR sidelink enhancements | Rel-17 | N | Q1’24 | 2 | Q4’22-Q3’24 | 0.5 | Not started ; no prose
NR sidelink relay | Rel-17 | N | Q2’24 | 19 | Q4’22-Q4’24 | 2 | Not started ; no prose
TEIx_Test (new TC coverage) | Rel-15+ | All | n/a | 10 | Q1’23-Q4’23 | 1 | 2023 total after RAN5#101: 8 new tests
TTCN maintenance & deliveries |  |  |  |  | Q1–Q4 | 45 | 
Release & configuration management |  |  |  |  | Q1–Q4 | 6 | 
Total: |  |  |  | >347 |  | 75 | person-months
TTCN workplan 2023
Status of 2022 tasks carried over and maintenance
Notes: Note: TTCN of some features initially started in 2022 will only be completed in 2023 due to availability of prose late in CY2022, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 12
2023 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2023 WkLoad | TTCN Status (as of Nov’23) / Comments
MCX Client enhancements | R15to16 | L | Q3’24 | 80 | Q1’23-Q4’24 | 4 | 62% (@iwd-23wk37)
Inter-system mobility between untrusted non-3GPP and 3GPP | Rel-15 | L,N,W | Q2’23 | 7 | Q1’23-Q4’23 | 3 | Not started
5G access traffic steering, switch and splitting | Rel-16 | N,W | Q2’23 | 7 | Q1’23-Q1’24 | 1.5 | Not started
NB-IoT/eMTC for non-terrestrial networks (NTN) | Rel-17 | L | Q1’24 | >15 | Q1’23-Q1’24 | 3 | 45% (@iwd-23wk37)
5G control plane steering of roaming for UE in connected mode enhancements (CP SOR) | Rel-17 | N | Q1’23 | 6 | Q1’23-Q2’23 | 1 | 100% (@iwd-23wk24)
NR UL data compression (UDC) | Rel-17 | N | Q2’23 | 9 | Q1’23-Q3’23 | 2 | 100% (@iwd-23wk37)
NR IIoT and URLLC enhancements | Rel-17 | N | Q4’23 | 4 | Q1’23-Q1’24 | 1.5 | Not started
EN-DC user plane integrity protection (UPIP) | Rel-17 | L,N | Q1’24 | 9 | Q1’23-Q1’24 | 1.5 | 33% (@iwd-23wk37)
NR coverage enhancements | Rel-17 | N | Q1’24 | 9 | Q1’23-Q1’24 | 1.5 | Not started
NR small data Tx in INACTIVE state | Rel-17 | N | Q2’24 | 8 | Q1’23-Q2’24 | 1.5 | Not started
NR positioning enhancements | Rel-17 | N | Q3’23 | 3 | Q1’23-Q3’23 | 1 | 100% (@iwd-23wk37)
NR for non-terrestrial networks (NTN) | Rel-17 | N | Q2’24 | >22 | Q1’23-Q2’24 | 3 | Not started
5G non-public network (NPN) enhancements | Rel-17 | N | Q2’24 | 16 | Q1’23-Q2’24 | 2 | 44% (@iwd-23wk37)
NR QoE management and optimizations | Rel-17 | N | Q3’24 | 4 | Q1’23-Q3’24 | 1 | Not started ; no prose
NR MIMO further enhancements | Rel-17 | N | Q2’24 | 3 | Q1’23-Q2’24 | 1 | Not started ; no prose
New/extended bands & band combinations | R16to18 | L,N | Q2’25 | n/a | Q1’21-Q2’25 | 0.5 | 20% (@iwd-23wk37)
Total: |  |  |  | >202 |  | 29 | person-months
TTCN workplan 2023
Status of new 2023 tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 13
2023 workload is estimated at 104 person-months (pm), see previous slides.
PCG#49/OP#48 approved the 3GPP funding of 58 pm for 2023 TTCN tasks.
CTIA/PTCRB and GCF have agreed to continue TF160 financial support in 2023.
Current commitments for 2023 are as follows:
3GPP companies / 3GPP MRPs committed to provide 20 pm as voluntary contributions for 2023 TTCN development.
Total resources of 104 pm  no estimated funding gap.
TTCN funding 2023
Status
Funding |  | 
Entity | Person-months | Comments
3GPP | 58 | PCG#49/OP#48 approved (decision OP48/05)
CTIA/PTCRB | 12 | NE-DC, NR IIoT/URLLC, MCX, RedCap
GCF | 12 | NR V2X, NR 2-step RACH, NR Rel-17 enh., RedCap, MCX
Qualcomm | 2 | NR-U, SDT, NTN-IoT
Total: | 84 | 
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 
Adare | 3 | 
Anritsu | 1 | 
Keysight | 1 | 
Rohde&Schwarz | 1 | NTN-IoT
Total: | 20 | 

## Slide 14: Preparing for 2024 TTCN Work Overview
Course of action to secure funding for TF160 work in 2024:
  Prior to RAN5#100 meeting (August), a request to identify the potential TTCN development tasks in 2024 has been made to 3GPP members.
  At RAN5#100, a provisional ‘TTCN Tasks List’ has been endorsed by RAN5.
  The TTCN Tasks List has been presented at RAN#101 (Sep) and endorsed by TSG RAN.
  The RAN Chair has presented the List to 3GPP PCG/OP (Oct) in order to support TF160 request for the TTCN funding in 2024. 3GPP PCG/OP has approved the 2024 TTCN funding request from TSG RAN of 58 person-months.
  The finalized TTCN Tasks List has been reviewed and endorsed at RAN5#101 (Nov) for TSG RAN approval at RAN#102 (Dec).
 The finalized TTCN Tasks List is to be approved by TSG RAN at RAN#102.
Based on inputs to RAN5#101, the updated list of TTCN tasks is presented in the next slides.

## Slide 15
2023 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2024 WkLoad | 3GPP related Work Item
MCX Client enhancements | Rel-16 | L | Q3’24 | 80 | Q1’23-Q4’24 | 2.5 | MCProtoc16_enh2MCPTT_eMCData2-ConTest
5G V2X with NR sidelink | Rel-16 | N,L | Q2’24 | 72 | Q4’20-Q2’24 | 2 | 5G_V2X_NRSL_eV2XARC-UEConTest
NR in unlicensed spectrum (NR-U) | Rel-16 | N | Q2’24 | 14 | Q1’22-Q2’24 | 1 | NR_unlic-UEConTest
LTE multi-USIM UE (MUSIM) | Rel-17 | L | Q3’23 | 14 | Q4’22-Q1’24 | 1 | LTE_NR_MUSIM_plus_CT1-UEConTest
NR multi/broadcast services (MBS) | Rel-17 | N | Q4’23 | 45 | Q4’22-Q1’24 | 2.5 | NR_MBS_5MBS_5MBUSA-UEConTest
NR IIoT and URLLC enhancements | Rel-17 | N | Q4’23 | 4 | Q1’23-Q1’24 | 0.5 | NR_IIOT_URLLC_enh-UEConTest
EN-DC user plane integrity protection | Rel-17 | L,N | Q4’23 | 9 | Q1’23-Q1’24 | 0.5 | UPIP_SEC_LTE-RAN-UEConTest
NR sidelink enhancements | Rel-17 | N | Q1’24 | 2 | Q4’22-Q3’24 | 0.5 | NR_SL_enh-UEConTest
NR sidelink relay | Rel-17 | N | Q2’24 | 19 | Q4’22-Q4’24 | 1.5 | NR_SL_Relay-UEConTest
NR coverage enhancements | Rel-17 | N | Q1’24 | 9 | Q1’23-Q1’24 | 0.5 | NR_cov_enh-UEConTest
NR small data Tx in INACTIVE state | Rel-17 | N | Q2’24 | 8 | Q1’23-Q2’24 | 0.5 | NR_SmallData_INACTIVE-UEConTest
NR for non-terrestrial networks (NTN) | Rel-17 | N | Q2’24 | >22 | Q1’23-Q2’24 | 1 | NR_NTN_solutions_plus_CT-UEConTest
5G non-public network enhancements | Rel-17 | N | Q2’24 | 16 | Q1’23-Q2’24 | 1 | NG_RAN_PRN_enh_plus_CT-UEConTest
NR QoE management and optimizations | Rel-17 | N | Q3’24 | 4 | Q1’23-Q3’24 | 0.5 | NR_QoE-UEConTest
NR MIMO (further) enhancements | R16to17 | N | Q2’24 | 4 | Q1’23-Q2’24 | 1 | NR_eMIMO-UEConTest, NR_feMIMO-UEConTest
New/extended bands & band combinations | R16to18 | L,N | Q2’25 | n/a | Q1’21-Q2’25 | 0.5 | NR_lic_bands_BW_R18-UEConTest NR_CADC_NR_LTE_DC_R1x-UEConTest, LTE_CA_R17-UEConTest
TEIx_Test (new TC coverage) | Rel-15+ | All | n/a | 10 | Q1’24-Q4’24 | 2 | TEIx_Test
TTCN maintenance & deliveries |  |  |  |  | Q1–Q4 | 45 | 
Release & configuration management |  |  |  |  | Q1–Q4 | 6 | 
Total: |  |  |  | >323 |  | 70 | person-months
Preparing for 2024 TTCN Work – Tasks List
2023 tasks completion and maintenance
Notes: Note: TTCN of some features initially started in 2023 will only be completed in 2024 due to availability of prose late in CY2023, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 16
2024 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2024 WkLoad | 3GPP related Work Item
MR-DC further enhancement | Rel-17 | N | Q1’24 | 10 | Q1’24-Q2’24 | 2 | LTE_NR_DC_enh2-UEConTest
UAS connectivity, identification and tracking | Rel-17 | N,L | Q4’24 | 12 | Q1’24-Q4’24 | 1.5 | ID_UAS-UEConTest
IMS voice & NW usability no E-UTRA in 5GS | Rel-17 | N,L | Q1’24 | 2 | Q1’24-Q2’24 | 0.5 | ING_5GS-UEConTest
IMS data channel | Rel-17 | N,L | Q3’24 | 10 | Q1’24-Q4’24 | 2 | IMSProtoc17_dataCH-UEContest
5G ATSSS – Phases 1 & 2 | R16to17 | N,W | Q3’24 | 17 | Q2’24-Q4’24 | 2.5 | ATSSS-UEConTest, ATSSS_Ph2-UEConTest
Signal level enhanced network selection | Rel-18 | L | Q2’24 | 4 | Q3’24-2025 | 1 | SENSE-UEContest
IoT NTN with enhancements | R17to18 | L | Q2’25 | 12 | Q3’24-2025 | 2.5 | LTE_NBIOT_eMTC_NTN_plus_EPS-UEConTest, IoT_NTN_enh-UEConTest (new for info)
NR mobility further enhancements | Rel-18 | N | Q2’25 | 10 | Q3’24-2025 | 2 | NR_Mob_enh2-UEConTest (new for info)
Enhanced RedCap NR UE | R17to18 | N | Q4’25 | 10 | Q3’24-2025 | 2.5 | NR_redcap_plus_ARCH-UEConTest, NR_redcap_enh_plus_CT1-UEConTest (new for info)
5G non-public networks (NPN) – Phase 2 | Rel-18 | N | Q2’25 | 10 | Q3’24-2025 | 2 | eNPN_Ph2-NGRAN_plus_CT1-UEConTest (new for info)
NR multi-carrier enhancements | Rel-18 | N | 2024 | 5 | Q3’24-2025 | 1 | NR_MC_enh
NR coverage further enhancements | Rel-18 | N | 2024 | 10 | Q3’24-2025 | 1.5 | NR_cov_enh2
NR network energy savings | Rel-18 | N | 2024 | 5 | Q3’24-2025 | 1 | Netw_Energy_NR
XR enhancements for NR | Rel-18 | N | 2024 | 10 | Q3’24-2025 | 1.5 | NR_XR_Enh
NR NTN enhancements | Rel-18 | N | 2024 | FFS | Q3’24-2025 | 2 | NR_NTN_enh, 5GSAT_Ph2
Enhanced LTE support for UAV | Rel-18 | L | 2024 | FFS | Q3’24-2025 | 1 | LTE_UAV_enh, UAS_Ph2
NR support for UAV | Rel-18 | N | 2024 | FFS | Q3’24-2025 | 1 | NR_UAV, UAS_Ph2
Dual Tx/Rx MUSIM for NR | Rel-18 | N | 2024 | FFS | Q3’24-2025 | 1 | NR_DualTxRx_MUSIM
Expanded and improved NR positioning | Rel-18 | N | 2024 | FFS | Q3’24-2025 | 0.5 | NR_pos_enh2
NR MBS enhancements | Rel-18 | N | 2024 | FFS | Q3’24-2025 | 1 | NR_MBS_enh
NR sidelink relay enhancements | Rel-18 | N | 2024 | FFS | Q3’24-2025 | 1 | NR_SL_relay_enh
Total: |  |  |  | >127 |  | 31 | person-months
Preparing for 2024 TTCN Work – Tasks List
New 2024 tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 17
2024 workload is estimated at 101 person-months (pm), see previous slides.
PCG#51/OP#50 approved the 3GPP funding of 58 pm for 2024 TTCN tasks.
CTIA/PTCRB and GCF have agreed to continue TF160 financial support in 2024.
Current commitments for 2024 are as follows:
3GPP companies / 3GPP MRPs committed to provide 19 pm as voluntary contributions for 2024 TTCN development.
Total resources of 97 pm  estimated funding gap of 4 pm.
Preparing for 2024 TTCN Work
Funding
Funding |  | 
Entity | Person-months | Comments
3GPP | 58 | PCG#51/OP#50 approved (decision OP50/XY)
GCF | 12 | 
CTIA/PTCRB | 6 | 
Qualcomm | 2 | NR NTN enh., UAV enh.
Total: | 78 | 
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 
Adare | 3 | 
Keysight | 1 | 
Rohde&Schwarz | 1 | 
Total: | 19 | 

## Slide 18: Annexes

## Slide 19: TTCN deliveries and baseline 2023 schedule
One TTCN-2 full delivery (FDD & LCR TDD) and four TTCN-3 full deliveries.
  RAN5 decided to stop releasing LCR TDD TTCN2 deliveries, as not needed anymore by the industry.
Type definitions baseline upgrade in 2023:
  Rel-17 Phase2: partial upgrade to Rel-17 Jun'23 baseline for NR+5GC+E-UTRA+LPP due to new/updated ASN.1+tabular IEs required by Rel-17 NR/5GC, NB-IoT & POS test cases.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
 wk05 |  |  | 03-Feb |  | GCF CAG#73 (7-9 Feb)
 wk07 |  |  | 17-Feb |  | PTCRB PVG#100 (21-23 Feb)
 wk12 | 24-Mar | 20-Mar | 24-Mar | TTCN-3 | 
 wk16 |  |  | 21-Apr |  | GCF CAG#74 (25-28 Apr)
 wk19 |  |  | 12-May |  | PTCRB PVG#101 (16-18 May)
 wk24 | 16-Jun | 12-Jun | 16-Jun | TTCN-3 | 
 wk29 |  |  | 21-Jul |  | GCF CAG#75 (25-27 Jul)
 wk32 |  |  | 11-Aug |  | PTCRB PVG#102 (15-17 Aug)
 wk37 | 15-Sep | 11-Sep | 15-Sep | TTCN-3 Rel-17 phase2 baseline upgrade | Partial upgrade to Rel-17 Jun'23 baseline for NR+5GC+E-UTRA+LPP
 wk41 |  |  | 13-Oct |  | GCF CAG#76 (17-19 Oct)
 wk44 |  |  | 03-Nov |  | PTCRB PVG#103 (7-9 Nov)
wk48 | 30-Nov | 27-Nov |  | TTCN2 (FDD) | 
wk48 | 01-Dec | 27-Nov |  | TTCN2 (LCR TDD) | 
wk49 | 08-Dec | 04-Dec | 08-Dec | TTCN-3 | 

## Slide 20: TTCN deliveries and baseline 2024 schedule
One TTCN-2 full delivery (FDD) and five TTCN-3 full deliveries.
Type definitions baseline upgrade to 3GPP Release 18 required in 2024:
  Rel-18 Stage3 freeze planned by 3GPP in March 2024.
  Rel-18 ASN.1 freeze planned by 3GPP in June 2024.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk03 |  |  | 19-Jan |  | GCF CAG#77 (24-25 Jan)
wk09 |  |  | 01-Mar |  | PTCRB PVG#104 (5-7 Mar)
wk12 | 22-Mar | 18-Mar | 22-Mar | TTCN-3 | 
wk16 |  |  | 19-Apr |  | GCF CAG#78 (23-24 Apr)
wk19 |  |  | 10-May |  | PTCRB PVG#105 (14-16 May)
wk24 | 14-Jun | 10-Jun | 14-Jun | TTCN-3 | 
wk29 |  |  | 19-Jul |  | GCF CAG#79 (23-24 Jul)
wk32 | 09-Aug | 31-Jul |  | TTCN-3 Rel-18 Baseline upgrade | Move to Rel-18 Jun'24 baseline (working assumption)
wk32 |  |  | 09-Aug |  | PTCRB PVG#106 (13-15 Aug)
wk37 | 13-Sep | 09-Sep | 13-Sep | TTCN-3 | 
wk41 |  |  | 11-Oct |  | GCF CAG#80 (15-16 Oct)
wk43 | 25-Oct | 16-Oct |  | TTCN-3 Rel-18 Baseline upgrade | Move to Rel-18 Sep'24 baseline (fallback plan)
wk44 |  |  | 01-Nov |  | PTCRB PVG#107 (5-7 Nov)
wk49 | 06-Dec | 02-Dec |  | TTCN2 (FDD) | 
wk50 | 13-Dec | 09-Dec | 13-Dec | TTCN-3 |