## R5#102
3GPP TSG RAN WG5 (RAN5) Meeting #102 | [9 empty] | R5-240015
Athens, Greece, 26 February - 1 March 2024
WI Progress and Target Completion Date Review
Source: RAN5 Chair
To: RAN5
Purpose: For Endorsement
UIC | WI Name | Rel | Tdoc# | Pre TCD | pre % | post % | post TCD | change (mths) | Rapporteur | other comments
830083 | UE Conformance Test Aspects - Rel-16 NR CA and DC; and NR and LTE DC Configurations | Rel-16 | R5-240087 | 2024-06-01 | 50% | 52% | 2024-06-01 |  | CMCC
880069 | UE Conformance Test Aspects - 5G V2X with NR sidelink | Rel-16 | R5-240768 | 2024-06-01 | 63% | 65% | 2024-06-01 |  | Huawei
900056 | UE Conformance - Rel-17 NR CA and DC; and NR and LTE DC Configurations | Rel-17 | R5-240300 | 2024-12-01 | 11% | 11% | 2024-12-01 |  | Huawei
911003 | UE Conformance Test Aspects - NR-based access to unlicensed spectrum | Rel-16 | R5-241133 | 2024-06-01 | 65% | 70% | 2024-06-01 |  | Qualcomm
930051 | UE Conformance - Power Class 2 for EN-DC with x LTE bands + y NR band(s) in DL and with 1 LTE band +1 TDD NR band in UL (either x= 2, 3, y=1 or x=1, 2, y=2) | Rel-17 | R5-240785 | 2024-06-01 | 6% | 6% | 2024-06-01 |  | Ericsson
950062 | UE Conformance - Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258 | Rel-17 | R5-240302 | 2024-12-01 | 33% | 33% | 2024-12-01 |  | Huawei
950063 | UE Conformance - NR coverage enhancements | Rel-17 | R5-240246 | 2024-03-01 | 98% | 100% | 2024-03-01 |  | China Telecom
950066 | UE Conformance - Support of reduced capability NR devices | Rel-17 | R5-240392 | 2024-03-01 | 92% | 100% | 2024-03-01 |  | China Unicom
960072 | UE Conformance - NR small data transmissions in INACTIVE state | Rel-17 | R5-240666 | 2024-06-01 | 90% | 95% | 2024-06-01 |  | Qualcomm
960074 | UE Conformance - Solutions for NR to support non-terrestrial networks (NTN) | Rel-17 | R5-241135 | 2024-06-01 | 65% | 70% | 2024-06-01 |  | Qualcomm
960075 | UE Conformance - Further enhancement on NR demodulation performance | Rel-17 | R5-240247 | 2024-03-01 | 65% | 82% | 2024-06-01 | +3 | China Telecom
960076 | UE Conformance - Enhancement of Private Network Support for NG-RAN including CT aspects | Rel-17 | R5-240362 | 2024-06-01 | 54% | 63% | 2024-06-01 |  | China Telecom
960079 | UE Conformance - Further enhancements on MIMO for NR | Rel-17 | R5-240502 | 2024-06-01 | 67% | 67% | 2024-06-01 |  | Samsung
960080 | UE Conformance - NR support for high speed train scenario in frequency range 2 | Rel-17 | R5-240504 | 2024-06-01 | 42% | 44% | 2024-06-01 |  | Samsung
960083 | UE Conformance - NR Sidelink Relay | Rel-17 | R5-240488 | 2024-06-01 | 20% | 25% | 2024-09-01 | +3 | CATT
960084 | UE Conformance - NR Sidelink enhancement | Rel-17 | R5-240486 | 2024-03-01 | 5% | 5% | 2024-09-01 | +6 | CATT
960086 | UE Conformance - UE power saving enhancements for NR | Rel-17 | R5-241450 | 2024-03-01 | 97% | 100% | 2024-03-01 |  | MediaTek
960087 | UE Conformance - NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects | Rel-17 | R5-240197 | 2024-03-01 | 99% | 100% | 2024-03-01 |  | MediaTek
960089 | UE Conformance Test Aspects - NR RRM enhancement | Rel-16 | R5-241340 | 2024-06-01 | 50% | 65% | 2024-06-01 |  | Apple
960090 | UE Conformance - RF requirements enhancement for NR frequency range 1 (FR1) | Rel-17 | R5-241032 | 2024-06-01 | 50% | 100% | 2024-03-01 | -3 | Huawei
970070 | UE Conformance - Further enhancements of NR RF requirements for frequency range 2 (FR2) | Rel-17 | R5-240451 | 2024-03-01 | 81% | 100% | 2024-03-01 |  | Nokia
970072 | UE Conformance - NR QoE management and optimizations for diverse services | Rel-17 | R5-240033 | 2024-09-01 | 20% | 20% | 2024-09-01 |  | Ericsson
970074 | UE Conformance - User Plane Integrity Protection support for EPC connected architectures (incl. CT/SA aspects) | Rel-17 | R5-240608 | 2024-03-01 | 75% | 100% | 2024-03-01 |  | Vodafone
970075 | UE Conformance - NR Positioning Enhancements | Rel-17 | R5-240135 | 2024-06-01 | 27% | 38% | 2024-06-01 |  | CATT
970077 | Conformance Test Aspects - Protocol enhancements for Mission Critical Services for Rel-16 (MCPTT, MCVideo, MCData) | Rel-16 | R5-240912 | 2024-09-01 | 42% | 67% | 2024-09-01 |  | NIST
981033 | UE Conformance - Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink | Rel-17 | R5-240249 | 2024-03-01 | 76% | 100% | 2024-03-01 |  | China Telecom
981034 | UE Conformance - NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks | Rel-18 | R5-240068 | 2024-03-01 | 75% | 100% | 2024-03-01 |  | CMCC
981035 | UE Conformance - NR and MR-DC measurement gap enhancements | Rel-17 | R5-240195 | 2024-03-01 | 90% | 95% | 2024-06-01 | +3 | MediaTek
991033 | UE Conformance - Further Multi-RAT Dual-Connectivity enhancement | Rel-17 | R5-240341 | 2024-03-01 | 94% | 94% | 2024-06-01 | +3 | Huawei
991034 | UE Conformance - Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking | Rel-17 | R5-240665 | 2024-12-01 | 65% | 95% | 2024-12-01 |  | Qualcomm
1000050 | UE Conformance - Additional NR bands for UL-MIMO in Rel-18 | Rel-18 | R5-240395 | 2024-06-01 | 49% | 49% | 2024-12-01 | +6 | China Unicom
1000051 | UE Conformance - High power UE (power class 2) for NR FR1 FDD single band | Rel-18 | R5-240397 | 2024-06-01 | 5% | 12% | 2024-12-01 | +6 | China Unicom
1000052 | UE Conformance - IMS voice service support and network usability guarantee for UE’s E-UTRA capability disabled scenario in 5GS | Rel-17 | R5-240037 | 2024-03-01 | 57% | 90% | 2024-06-01 | +3 | China Telecom
1000053 | UE Conformance - High power UE (power class 1.5) for NR FR1 TDD single band | Rel-18 | R5-240077 | 2025-06-01 | 35% | 66% | 2025-06-01 |  | CMCC
1000054 | UE Conformance - Rel-18 High Power UE for NR CA and DC; and NR and LTE DC Configurations | Rel-18 | R5-240364 | 2025-06-01 | 15% | 40% | 2025-06-01 |  | China Telecom
1000055 | UE Conformance - IMS Data Channel | Rel-17 | R5-240874 | 2024-09-01 | 6% | 8% | 2024-09-01 |  | Huawei
1000056 | UE Conformance - UE Conformance - Rel-17 Power Class 2 UE for NR inter-band CA/DC with or without SUL configurations with x (6>=x>2) bands DL and y (y=1, 2) bands UL | Rel-17 | R5-240298 | 2025-06-01 | 9% | 9% | 2025-06-01 |  | Huawei
1000057 | UE Conformance - Rel-18 NR CA and DC; and NR and LTE DC Configurations | Rel-18 | R5-240296 | 2025-06-01 | 5% | 5% | 2025-06-01 |  | Huawei
1000058 | UE Conformance - New Rel-18 NR licensed bands and extension of existing NR bands | Rel-18 | R5-240293 | 2025-06-01 | 5% | 5% | 2025-06-01 |  | Huawei
1000059 | UE Conformance - High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands in Rel-18 | Rel-18 | R5-240453 | 2024-06-01 | 18% | 18% | 2024-06-01 |  | Nokia
1010050 | UE Conformance - Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 2 | Rel-17 | R5-240038 | 2024-09-01 | 5% | 36% | 2024-09-01 |  | China Telecom
1010051 | UE Conformance - Rel-17 LTE CA Configurations | Rel-17 | R5-240366 | 2024-12-01 | 5% | 30% | 2024-12-01 |  | China Telecom
1010052 | UE Conformance - Signal level Enhanced Network Selection | Rel-18 | R5-240411 | 2024-06-01 | 5% | 100% | 2024-03-01 |  | Huawei
1020087 | UE Conformance - Air-to-ground network for NR | Rel-18 | R5-240043 | 2025-06-01 |  | 50% | 2025-06-01 |  | CMCC
1020088 | UE Conformance - 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC | Rel-17 | R5-240343 | 2025-06-01 |  | 7% | 2025-06-01 |  | Huawei