## Cover sheet
3GPP TSG-RAN WG5 Meeting #102 | [7 empty] | R5-240078
Athens, Greece, February 26 – March 1 , 2024
Agenda Item: | 7.5.2
Source: | CMCC
Title: | WP UE Conformance Test Aspects for High power UE (power class 1.5) for NR FR1 TDD single band
Work item code: | HPUE_NR_FR1_TDD_R18-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 66% (+32%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 66.5% (+31.9%)
FR1 |  | 66.5% (+31.9%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2 | 100% (+35%) |  |  | 100% (+35%)
NR RF/RRM
FR1 RF Tx test cases | 38.521-1 | 75% (+26.3%) |  |  | 75% (+26.3%)
RRM test cases | 38.533
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5 References
[1] RP-231152 | New WID on UE Conformance - HPUE PC1.5 for NR FR1 TDD single band - CMCC, HUAWEI, HiSilicon (Supporting companies:CATT, CAICT, ZTE, MTK, Ericsson, TIM)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects for High power UE (power class 1.5) for NR FR1 TDD single band | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | HPUE_NR_FR1_TDD_R18-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for NR PC1.5 n34 n39 and n40 support comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Dan Song, CMCC |  |  | songdan@chinamobile.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
66.5% (+31.9%)
8
1.7 (-0.6)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-2 | A.4.3.1 |  | Introduction of common implementation conformance statements for PC1.5 n34 n39 n40 UE into Table A.4.3.1-4e | CMCC | RAN5#102 (Feb-24) | R5-234741 R5-242023 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.3 | 100% (+35%) | 100% (+35%) |  | 100%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.521-1 | 6.2G.1 | UE maximum output power for Tx Diversity | Update Table 6.2G.1.3-1 in "6.2G.1.3 Minimum conformance requirements",Table 6.2G.1.5-2 in "6.2G.1.5 Test requirement" for PC1.5 n34 n39 n40 | CMCC | RAN5#102 (Feb-24) | R5-234742, R5-234746(To add PC2 n40 MOP in Clause 6.2.1) R5-240080 R5-240081(To add PC2 n40 MOP in Clause 6.2G.1) | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.2 | 100% (+35%) | 100% (+35%) |  | 100%
3 |  | 38.521-1 | 6.2G.2 | UE maximum output power reduction for Tx Diversity | update the test requirements for PC1.5 n34 n39 n40 | CMCC | RAN5#102 (Feb-24) | R5-234743 R5-240082 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.2 | 100% (+35%) | 100% (+35%) |  | 100%
4 |  | 38.521-1 | 6.2G.3 | UE additional maximum output power reduction for Tx Diversity | update TC 6.2G.3 for PC1.5 n39 as per R4-2321703 | CMCC | RAN5#103 (May-24) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> A-MPR for PC1.5 n39 is still missing. | 0.2 | 0% | 0% |  | 0%
5 |  | 38.521-1 | 6.2G.4 | Configured transmitted power for Tx Diversity | Update the configured tx power requirements | CMCC | RAN5#102 (Feb-24) | R5-234744 R5-240083 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.2 | 100% (+35%) | 100% (+35%) |  | 100%
6 |  | 38.521-1 Annex I | I.1 | Indication of modified MPR behavior | Add rows in Table I.1-1 of Annex I ModifiedMPR-Behavior for PC1.5 n34 n39 n40, aligned with core specifications TS 38.101-1. | CMCC | RAN5#102 (Feb-24) | R5-236677 R5-240084 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.2 | 100% (+35%) | 100% (+35%) |  | 100%
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
|  | 38.522 | <Clause> | <Title> | Add new ICS statements.
7 |  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria | CMCC | RAN5#103 (May-24) |  |  | 0.2 | 0% | 0% |  | 0%
8 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Update test applicability for 38.521-1 PC1.5 n34 n39 n40 test cases. | CMCC | RAN5#103 (May-24) |  |  | 0.2 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.