## R17 NR bands and CBW extensions
WP Title: | UE Conformance - New Rel-18 NR licensed bands and extension of existing NR bands | [9 empty] | Overall config. Completion | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-x: Common clauses (chapter 5) | 38.521-x: Tx test cases | 38.521-x: Rx test cases | 38.523-3: Protocol | 38.533: RRM & 38.571-1: LCS | 38.903: MU and TT | 38.905: Test point analysis | End of work plan columns. Note! Do not remove this column. | [6 empty] | Columns AF to AI is only used for WP rapporteur guide and notes and will be removed when the work plan is published
WP rapporteur's guide: All WP rows that represent WP work tasks must have a WP item ID number assigned. Other WP rows such as header rows used to group WP Items should NOT have any WP item ID numbers assigned (leave empty). How to assign unique WP item ID numbers (column A): In the WP item ID column double-click in the cell for the WP item row to assign the next free WP item ID number. Note! If You add numbers manually make sure each WP item row have an unique WP item ID number.
WI code: | NR_lic_bands_BW_R18-UEConTest
WP Scope: | This work plan covers the tasks needed to include new Rel-18 NR bands and new channel bandwidths added to existing Rel-15, Rel-16 and Rel-18 bands. NOTE! The company listed in column H is responsible to secure that required information for the NR bands or extended channel bandbidth is complete in the TSs and TRs as listed in columns P to Y.
WP Resp: | Yuxin Hao (Huawei) and Lei Gao (China Telecom) | [5 empty] | haoyuxin@huawei.com;gaol8@chinatelecom.cn
TS Resp: | - | [5 empty] | - | [20 empty] | WP rapporteur internal notes |  | Company <-> Contact email address(es)
WP Item ID | Source TS | Type | RAN4 WI code | RAN4 WID | RAN4 completion | Sub-WI Scope | Company | Target | Comments | Weight | [11 empty] | WP | 5% | (Work plan contribution to WI completion) |  |  |  | <Internal note column#1> | <Internal note column#2> | Company | E-mail address(es)
[22 empty] | Grp | completion | #configs | #assigned | #completed | #ongoing |  |  | Ligado Networks | Ojas.Choksi@ligado.com
[6 empty] | (New band/Ref. Config/New CBW) | [15 empty] | Overall | 5% | 8 | -5 | 0 | 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [11 empty] | 1 | 1 | 1 | 3 | 3 | 0.1 | 1 | 5 | 5
| 38.101-1 | New Rel-18 NR FR1 bands | [19 empty] | 1 | 0% | 2 | 0 | 0 | 0
1 | 38.101-1 | New Rel-18 NR FR1 bands | NR_TDD_n54 |  | 100% | n54 |  |  |  | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2 | 38.101-1 | New Rel-18 NR FR1 bands | NR_600MHz_APT |  | 100% | n105 |  |  |  | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3 | 38.101-1 | New Rel-18 NR FR1 bands | NR_900MHz_US |  | 100% | n106 |  |  | N106 can't declare completed until the general test environment and band-agnostic test cases in NR_FR1_less_than5MHz_BW-UEConTest are complete | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4 | 38.101-1 | New Rel-18 NR FR1 bands | NR_FDD_ULn28_DLn75_n76 |  | 100% | n109 |  |  |  | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5 | 38.101-1 | New Rel-18 NR FR1 bands | NR_bands_n31_n72 |  | 100% | n31 |  |  |  | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6 | 38.101-1 | New Rel-18 NR FR1 bands | NR_bands_n31_n72 |  | 100% | n72 |  |  |  | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
| 38.101-5 | New Rel-18 NR NTN bands | [19 empty] | 1 | #DIV/0! | 0 | -2 | 0 | 0
7 | 38.101-5 | New Rel-18 NR NTN bands | NR_NTN_LSband |  | 100% | n254 | Apple |  |  | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 38.101-1 | New Rel-18 NR FR1 SUL or SDL bands and reference CA configurations included in the associated RAN4 WID (if any) | [19 empty] | 3 | #VALUE! | 0 | -1 | 0 | 0
Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
| 38.101-2 | New Rel-18 NR FR2 bands | [19 empty] | 4 | #VALUE! | 0 | -1 | 0 | 0
Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
| 38.101-1 | Rel-18 Channel bandwidth addition to existing Rel-15, Rel-16 and Rel-18 FR1 bands | [19 empty] | 5 | 0% | 6 | -1 | 0 | 0
| 38.101-1 | Rel-18 Channel bandwidth addition to existing Rel-15, Rel-16 and Rel-18 FR1 bands | NR_bands_R18_BWs |  | 100% | n8 adding CBWs 25MHz (All SCS) |  |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  |  |  | 0%
| 38.101-1 | Rel-18 Channel bandwidth addition to existing Rel-15, Rel-16 and Rel-18 FR1 bands | NR_bands_R18_BWs |  | 100% | n8 adding 30MHz (15 -30 kHz SCS) |  |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  |  |  | 0%
| 38.101-1 | Rel-18 Channel bandwidth addition to existing Rel-15, Rel-16 and Rel-18 FR1 bands | NR_bands_R18_BWs |  | 100% | n39 adding 35 MHz (15-60 kHz SCS) |  |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  |  |  | 0%
| 38.101-1 | Rel-18 Channel bandwidth addition to existing Rel-15, Rel-16 and Rel-18 FR1 bands | NR_bands_R18_BWs |  | 100% | n98 adding 35 MHz for (15-60 kHz SCS) |  |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  |  |  | 0%
| 38.101-1 | Rel-18 Channel bandwidth addition to existing Rel-15, Rel-16 and Rel-18 FR1 bands | NR_bands_R18_BWs |  | 100% | n71 adding 25 and 30 MHz for uplink (15 kHz SCS for 25 MHz) |  |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  |  |  | 0%
| 38.101-1 | Rel-18 Channel bandwidth addition to existing Rel-15, Rel-16 and Rel-18 FR1 bands | NR_bands_R18_BWs |  | 100% | n71 adding 35 MHz (15-30 kHz SCS) |  |  |  | 1 | 0% | 0% |  | 0% | 0% | 0% |  |  |  | 0%
Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on O1: Todo for 38.508-1: - Add test frequencies to clause 4.3.1 for the new band. - Add test frequencies to clause 6.2.3.1 for protocol testing based on the default CBW chosen for protocol testing of teh band. - Add RF low, Mid and High test channel bandwidth in clause 4.3.1
Note on P1: To do 38.508-2: - Add the new band to the relevant table in clause A.4.3.1
Note on Q1: To do 38.521-x chapter 5: - Add operating band to clause 5.2. - Add the channel bandwidth for the band to clause 5.3.5. - Add the applicable NR-ARFCN for teh band to Table 5.4.2.3-1. - Add the applicable SS raster for teh band to Table 5.4.3.3-1. - Add the default UE TX-RX frequency separation for teh band to Table 5.4.4-1.
Note on T1: Todo for 38.523-3: If the band's overall bandwidth is less than 4*default CBW for protocol testing then thenexecution guidelineneed to be added to 38.523-3 clause 11. Remark: Some protocol test cases use up to 4 inter-frequency cells. If not then there is no impact on 38.523-3 and the completion can be set to 100%.
Note on U1: 38.533: Add band to NR band groups in clause 3A.4 in TS 38.533. This clause is referenced from TSuse is referenced from TS 37.571-1 clause 4.12.3 for defintion of NR band groups.
Note on AG6: The company and email addresses are used by the WP support tool when creating WP status update request emails. The companies in the company column should be the assigned companies in column F of the WP.
Note on A7: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on K7: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 fpr a WP item means that it will not be included at all in the calculation.
Note on AH7: Use email address format as used in the address fields of emails. If needed multipe email addresses may be included separated by semicolon (;).