## 2DL-1UL configs
Work plan for introduction of E-UTRA CA configurations into 3GPP UE conformance test specifications | [13 empty] | Source: PRD20 v.1.5.0
Note! A copy of the completed work plan shall be attached to the CR to TS 36.521-2 adding the E-UTRA CA configuration(s) to clause A.4.6 (see Step 4 below).
1. Scope
|  | Workplan Name |  |  | Rel-17: CA_30A-48A 2DL/1UL without UL CA
|  | Company |  |  | Bureau Veritas ADT/Sporton International | [5 empty] | <= Enter Your Company name here.
|  | Contact |  |  | amy.tao@bureauveritas.com / IvanCheng@sporton.com.tw | [5 empty] | <= Enter the name and email address to the contact person responsible for the WP here.
|  | Target completion |  |  | RAN5#102 | [5 empty] | <= Enter target completion date here. Format RAN5#xx (mm-yy), where xx is the RAN5 meeting number and 'mm' and 'yy' is the number of the month and year, e.g. RAN5#94 (02-22)>
Comments
|  | Type of CA configurations |  |  | CA configurations [DL/UL]
|  | CA configuration(s) with DL only |  |  | CA_30A-48A
|  | CA configuration(s) with SDL band |  |  | -
|  | CA configurations with UL |  |  | -
|  | DL CA type(s) |  |  | CA_XA-YA
|  | UL CA type(s) |  |  | -
2. Overall status
Overall Sub-WI
|  | Overall completeness |  |  |  |  | 100%
|  | Step 1: Work plan pre-requisite |  |  |  |  | 100%
|  | Step 2: Complete Test Point (TP) analysis for impacted E-UTRA CA configurations |  |  |  |  | 100%
|  | Step 3.1: CR(s) to common test environment (TS 36.508) |  |  |  |  | 100%
|  | Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 36.521-1) |  |  |  |  | 100%
Step 3.3: CR(s) for RF transmitter test cases (TS 36.521-1, clause 6)
|  | Step 3.4: CR(s) for RF receiver test cases (TS 36.521-1, clause 7) |  |  |  |  | 100%
|  | Step 3.5: CR(s) for RF Performance test cases (TS 36.521-1, clause 8 and 9) |  |  |  |  | 100%
|  | Step 3.6: CR to add ICS for protocol testing (TS 36.523-2) |  |  |  |  | 100%
|  | Step 4: Declare completion of E-UTRA CA configurations by CR to TS 38.521-1 (after completion of step 1 to 3) |  |  |  |  | 100%
3. Details
The strikethrough WP items are not applicable to the type of CA configuration(s) in this Work Plan and can be ignored. You can hide not applicable WP items by filtering on excluding "-" in column H "Impacted CA config(s)". | [7 empty] | WP item columns to be filled in |  |  |  | Do not edit |  | WP item columns to be filled in
Step 1: Work plan pre-requisite
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Bands completed | TCs available
[14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
All | 1 | Pre-requisite | 36.521-1, 36.521-2 | Annex A | Impacted E-UTRA bands completed | CA_30A-48A | Set status in column "Bands completed" to 100% when all impacted E-UTRA bands have been confirmed completed in RAN5 TSs and TRs. | BV ADT/Sporton | RAN5#102 |  |  | 1 | 100% | 100%
All | 2 | Pre-requisite | 36.521-1, 36.521-2 | Annex A | Impacted Transmitter (clause 6), Receiver (clause 7), RF perfromance (Clause 8 and 9) | CA_30A-48A | Set status in column "TCs available" to 100% when all applicable test cases in 36.521-1 for the E-UTRA CA configuration types are available. If the tets cases are not available contact the responsible for the test case as indicated in the relevant WI WP and consider to support to get the test case(s) completed. | BV ADT/Sporton | RAN5#102 |  |  | 1 | 100% |  | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 2: Complete Test Point (TP) analysis for impacted E-UTRA CA configurations
WP item applicability | WP item ID | Area | TR | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
TP analysis
[14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
UL CA | 3 | TP Analysis | 36.905 | 4.1.x | Test point (TP) analysis for A-MPR | - | For each UL CA configuration perform an A-MPR TP analysis as described in TR 36.905 clause 4.1.2 for intra-band contiguous UL CA and in clause 4.1.3 for inter-band UL CA. The TP analysis is documented by a CR to 36.905 clause 4.1.x including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required A-MPR TP analysis have been included in TR 36.905. |  | RAN5#102 |  |  | 1 |  | 0%
All | 4 | TP Analysis | 36.905 | 4.2.x | Test point (TP) analysis for reference sensitivity | CA_30A-48A | For each CA configurations with exceptions perform referense sensitivity TP analysis as described in TR 36.905 clause 4.2.x. Document the TP analysis by a CR to TR 36.905 clause 4.2.x including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required TP analysis have been included in TR 36.905. | Sporton International/BV ADT | RAN5#102 |  | No exception defined in 36.101, no changes need. Default test configuration could be used. | 1 | 100% | 100%
UL CA | 5 | TP Analysis | 36.905 | 4.3 | Test point (TP) analysis for Tx spurious emissions test cases for UL CA | - | For each UL CA configuration perform spurious emission TP analysis as described in TR 36.905 clause 4.3. Document the TP analysis by a CR to TR 36.905 clause 4.3 including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required TP analysis have been included in TR 36.905. |  | RAN5#102 |  |  | 1 |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3: CRs to impacted TSs areas
Step 3.1: CR(s) to common test environment (TS 36.508)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
Test Freq.
1
All | 6 | 36.508 - (4) Common | 36.508 | 4.3.1 | Test frequencies | CA_30A-48A | For new CA configurations: - Check if the involved bands have single carrier test frequencies specified in 4.3.1.x - Add test frequencies for the new CA configuration in sub-clause 4.3.1.x . - Check if reference system configurations in sub-clause 4.4 need to be updated. For new BCS of existing CA configurations: - Check if test frequencies need to be updated for the new BCS. | BV ADT/Sporton | RAN5#102 |  | No changes need | 1 | 100% | 100%
All | 7 | 36.508 - (6) Common SIG | 36.508 | 6.2.3.2 | Test frequencies for CA signalling test | CA_30A-48A | This WP item is only applicable if the If number of bands is less or equal to 2 bands. For new CA configurations: Add test frequencies for the new CA configuration for CA signalling tests in sub-clause 6.2.3.2. For new BCS of existing CA If additional BCS is added to existing CA configuration in clause 6.2.3.2. then check if alternative test frequencies are needed for the additional BCS. | BV ADT/Sporton/CATT | RAN5#102 | R5-240939 |  | 1 | 100% | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 36.521-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
Clause 5
1
All | 8 | 36.521-1 - General | 36.521-1 | 5.2A and 5.4.2A | Operating bands for CA in clause 5.2.A and channel bandwidths and bandwidth combination sets to clause 5.4.2A | CA_30A-48A | Add CA operating band in clause 5.2A and CA Channel bandwidth ín clause 5.4.2A for the new CA configuration. | BV ADT/Sporton | RAN5#102 | R5-241853 |  | 1 | 100% | 100%
UL CA | 9 | 36.521-1 - General | 36.521-1 | 6.2.5 | Delta TIB | - | For the CA configurations with UL CA: - Check if delta TIB of the CA configurations need to be added to clause 6.2.5 |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
All | 31 | 36.521-1 - General | 36.521-1 | 7.3.3 | Delta RIB | CA_30A-48A | For the CA configurations with or without UL CA: - Check if delta RIB of the new CA configuration need to be added to clause 7.3.3. | BV ADT/Sporton | RAN5#102 | R5-241874 |  | 1 | 100% | 100% |  | 100% |  | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.3: CR(s) for RF transmitter test cases (TS 36.521-1, clause 6)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Min. Req. | Test proc. | Test Pts | Mess. Cont. | TT / TR 36.905 |  | Other Areas
[14 empty] | 1 | 5 | 5 | 2 | 2 |  | 2
UL CA | 9 | 36.521-1 - (6.2) RF Tx | 36.521-1 | 6.2.2A.x | UE Maximum Output Power for CA ... <nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 10 | 36.521-1 - (6.2) RF Tx | 36.521-1 | 6.2.3A.x | Maximum Power Reduction (MPR) for CA ....<nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 11 | 36.521-1 - (6.2) RF Tx | 36.521-1 | 6.2.4A.x | Additional Maximum Power Reduction (A-MPR) for CA....<nUL>; n=2,3 etc Note! This WP item is dependent on A-MPR TP analysis (Step 2, WP item 3) | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed to Test Configuration Table as per A-MPR test point analysis in Step 2 (WP item 3).. - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 26 | 36.521-1 - (6.6) RF Tx | 36.521-1 | 6.6.2.2A.x, 6.2.5 | Additional Spectrum Emission Mask for CA ..<nUL>; n=2,3 etc Note! This WP item is dependent [UDL/UL] on A-MPR TP analysis (Step 2, WP item 3) | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table) to be aligned with A-MPR TP analysis done in Step 2 (WP item 3) - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 30 | 36.521-1 - (6.6) RF Tx | 36.521-1 | 6.6.3.3A.x | Additional spurious emissions for CA..<nUL>; n=2,3 etc Note! This WP item is dependent [UDL/UL] on A-MPR TP analysis (Step 2, WP item 3) | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table) to be aligned with A-MPR TP analysis done in Step 2 (WP item 3) - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 12 | 36.521-1 - (6.2) RF Tx | 36.521-1 | 6.2.5 | Configured UE transmitted Output Power | - | - Add delta TIB for the new CA configuration in sub-clause 6.2.5. |  | RAN5#102 |  |  | 1 |  | 0%
UL CA | 13 | 36.521-1 - (6.2) RF Tx | 36.521-1 | 6.2.5A.x | Configured UE transmitted Output Power for CA ....<nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 14 | 36.521-1 - (6.3) RF Tx | 36.521-1 | 6.3.2A.x | Minimum Output Power for CA ....<nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 15 | 36.521-1 - (6.3) RF Tx | 36.521-1 | 6.3.3A.x | UE Transmit OFF power for CA ....<nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 16 | 36.521-1 - (6.3) RF Tx | 36.521-1 | 6.3.4A.1.1 | General ON/OFF time mask for CA ....<nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 17 | 36.521-1 - (6.3) RF Tx | 36.521-1 | 6.3.5A.1.x | Power Control Absolute power tolerance for CA ....<nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 18 | 36.521-1 - (6.3) RF Tx | 36.521-1 | 6.3.5A.2.x | Power Control Relative power tolerance for CA ....<nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 19 | 36.521-1 - (6.3) RF Tx | 36.521-1 | 6.3.5A.3.x | Aggregate power control tolerance for CA....<nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 20 | 36.521-1 - (6.5) RF Tx | 36.521-1 | 6.5.1A.x | Frequency error for CA....<nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 21 | 36.521-1 - (6.5) RF Tx | 36.521-1 | 6.5.2A.1.x | Error Vector Magnitude (EVM) for CA...<nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 22 | 36.521-1 - (6.5) RF Tx | 36.521-1 | 6.5.2A.2.x | Carrier leakage for CA ..<nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 23 | 36.521-1 - (6.5) RF Tx | 36.521-1 | 6.5.2A.3.x | In-band emissions for non allocated RB for CA ..<nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 24 | 36.521-1 - (6.6) RF Tx | 36.521-1 | 6.6.1A.x | Occupied bandwidth for CA ..<nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 25 | 36.521-1 - (6.6) RF Tx | 36.521-1 | 6.6.2.1A.x | Spectrum emission mask for CA ..<nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated (including delta TIB of the new CA configuration in sub-clause 6.2.5). - For 2UL CA add test points if needed based on the A-MPR test point analysis (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 27 | 36.521-1 - (6.6) RF Tx | 36.521-1 | 6.6.2.3A.x | Adjacent Channel Leakage power Ratio for CA..<nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed based on A-MPR test point anaysis (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 28 | 36.521-1 - (6.6) RF Tx | 36.521-1 | 6.6.3.1A.x | Transmitter Spurious emissions for CA..<nUL>; n=2,3 etc Note! This WP item is dependent [UDL/UL] on Spurious emission TP analysis (Step 2, WP item 5) | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed based on A-MPR tets point analysis inTR 36.905 (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 29 | 36.521-1 - (6.6) RF Tx | 36.521-1 | 6.6.3.2A.x | Spurious emission band UE co-existence for CA ..<nUL>; n=2,3 etc Note! This WP item is dependent [UDL/UL] on A-MPR TP analysis (Step 2, WP item 3) | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirement. - Add test point analysis to TR 36.905. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
UL CA | 31 | 36.521-1 - (6.7) RF Tx | 36.521-1 | 6.7A.x | Transmit intermodulation for CA..<nUL>; n=2,3 etc | - | For the CA configurations with UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirement. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.4: CR(s) for RF receiver test cases (TS 36.521-1, clause 7)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Min. Req. | Test proc. | Test Pts | Mess. Cont. | TT / TR 36.905 |  | Other Areas
[14 empty] | 1 | 5 | 5 | 2 | 2 |  | 2
All | 31 | 36.521-1 - (7.3) RF Rx | 36.521-1 | 7.3A.x | Reference sensitivity level for CA..<nDL>; n=2,3 etc Note! This WP item is dependent [UDL/UL] on Reference TP analysis (Step 2, WP item 4) | CA_30A-48A | For the CA configurations with or without UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated in sub-clause 7.3A.0. - Add test points to Test Configuration Table as per reference sensitivity TP analysis in Step 2 (WP item 4). - Add test requirements. | BV ADT/Sporton | RAN5#102 | R5-241874 | Updated 7.3A.3 requirement, and test configuration could used default as no exception defined in 36.101 | 1 | 100% | 100% |  | 100% |  | 100%
All | 32 | 36.521-1 - (7.4) RF Rx | 36.521-1 | 7.4A.x | Maximum input level for CA..<nDL>; n=2,3 etc | CA_30A-48A | For the CA configurations with or without UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. | BV ADT/Sporton | RAN5#102 |  | test refer to 7.3A.3, no update to the test case | 1 | 100% | 100% |  | 100% |  | 100%
All | 33 | 36.521-1 - (7.5) RF Rx | 36.521-1 | 7.5A.x | Adjacent Channel Selectivity (ACS) for CA..<nDL>; n=2,3 etc | CA_30A-48A | For the CA configurations with or without UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. | BV ADT/Sporton | RAN5#102 |  | test refer to 7.3A.3, no update to the test case | 1 | 100% | 100% |  | 100% |  | 100%
All | 34 | 36.521-1 - (7.6) RF Rx | 36.521-1 | 7.6.1A.x | In-band blocking for CA..<nDL>; n=2,3 etc | CA_30A-48A | For the CA configurations with or without UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. | BV ADT/Sporton | RAN5#102 |  | test refer to 7.3A.3, no update to the test case | 1 | 100% | 100% |  | 100% |  | 100%
All | 35 | 36.521-1 - (7.6) RF Rx | 36.521-1 | 7.6.2A.x | Out-of-band blocking for CA..<nDL>; n=2,3 | CA_30A-48A | For the CA configurations with or without UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. | BV ADT/Sporton | RAN5#102 |  | test refer to 7.3A.3, no update to the test case | 1 | 100% | 100% |  | 100% |  | 100%
DL CA | 36 | 36.521-1 - (7.6) RF Rx | 36.521-1 | 7.6.3A.x | Narrow band blocking for CA ..<nDL>; n=2,3 | CA_30A-48A | For the CA configurations without UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. | BV ADT/Sporton | RAN5#102 |  | test refer to 7.3A.3, no update to the test case | 1 | 100% | 100% |  | 100% |  | 100%
DL CA | 37 | 36.521-1 - (7.7) RF Rx | 36.521-1 | 7.7A.x | Spurious response for CA ..<nDL>; n=2,3 | CA_30A-48A | For the CA configurations without UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. | BV ADT/Sporton | RAN5#102 |  | test refer to 7.3A.3, no update to the test case | 1 | 100% | 100% |  | 100% |  | 100%
DL CA | 38 | 36.521-1 - (7.8) RF Rx | 36.521-1 | 7.8.1A.x | Wideband intermodulation for CA ..<nDL>; n=2,3 | CA_30A-48A | For the CA configurations without UL CA and relevant TC variant(s): - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. | BV ADT/Sporton | RAN5#102 |  | test refer to 7.3A.3, no update to the test case | 1 | 100% | 100% |  | 100% |  | 100%
SDL | 39 | 36.521-1 - (7.9) RF Rx | 36.521-1 | 7.9A | Spurious emissions for CA (only applicable for CA configs with SDL) | - | For the CA configurations with a SDL band: - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. |  | RAN5#102 |  |  | 1 |  | 0% |  | 0% |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.5: CR(s) for RF Performance test cases (TS 36.521-1, clause 8 and 9)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
[14 empty] | Min. Req. | Test proc. | Test Pts | Mess. Cont. | TT / TR 36.905 |  | Other Areas
[14 empty] | 1 | 5 | 5 | 2 | 2 |  | 2
DL CA type | 40 | 36.521-1 - (8.1) General | 36.521-1 | 8.1.2 | Applicability of requirements | CA_XA-YA | Add new BW combinations in section 8.1.2 if needed If this is the first CA configuration of this CA configuration type, add it in section 8.1.2 | BV ADT/Sporton | RAN5#102 |  | No changes need | 1 | 100% | [6 empty] | 100%
DL CA type | 41 | 36.521-1 - (8.2) Demod | 36.521-1 | 8.2.1.x (FDD) 8.2.2.x (TDD) 8.2.3.x (TDD FDD) 8.7.1.x (FDD) 8.7.2.x (TDD) 8.7.5.x (TDD FDD) | Misc. CA test cases | CA_XA-YA | For relevant CA test cases: - Add new BW combinations if needed | BV ADT/Sporton | RAN5#102 |  | No changes need | 1 | 100% | 100% |  | 100% | 100% | 100%
DL CA type | 42 | 36.521-1 - (9.1) General | 36.521-1 | 9.1 | Applicability of requirements | CA_XA-YA | Add new BW combinations in section 9.1.1 if needed. If this is the first CA configuration of the CA configuration type, add it in section 9.1.1 | BV ADT/Sporton | RAN5#102 |  | No changes need | 1 | 100% | [6 empty] | 100%
DL CA type | 43 | 36.521-1 - (9.6) CSI reporting | 36.521-1 | 9.6.1.1_A.x (FDD) 9.6.1.2_A.x (TDD) 9.6.1.3_A.x (TDD-FDD CA for FDD PCell) 9.6.1.4_A.x (TDD-FDD CA for TDD PCell) | Misc. CA test cases | CA_XA-YA | For relevant CA test cases: - Add new BW combinations if needed | BV ADT/Sporton | RAN5#102 |  | No changes need | 1 | 100% | 100% |  | 100% | 100% | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.6: CR to add ICS for protocol testing (TS 36.523-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
ICS / TC appli.
1
All | 44 | 36.523-2 - ICS | 36.523-2 | Annex A.4.3.3 | Implementation Conformance Statements for Protocol test cases | CA_30A-48A | Add CA Physical Layer Baseline Implementation Capabilities for the new CA configurations in Annex A.4.3.3. | BV ADT/Sporton/CATT | RAN5#102 | R5-240939 |  | 1 | 100% | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 4: Declare completion of E-UTRA CA configurations by CR to TS 38.521-1 (after completion of step 1 to 3)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness | Detailed Completion Status per area
ICS / TC appli.
1
All | 45 | 36.521-2 - ICS | 36.521-2 | Annex A.4.6 | Declaration of E-UTRA CA configurations completion | CA_30A-48A - | The completion of E-UTRA CA configurations covered by this work plan is done by a CR to TS 36.521-2 adding the CA Physical Layer Baseline Implementation Capabilities for the CA configurations in Annex A.4.6. Any exceptions for not completed parts need to be stated in the CR cover sheet and as a note for the entry of the CA configuration in the CA Physical Layer Baseline Implementation Capabilities table. This work plan shall be attached to the CR in the TDOC zip-file. | BV ADT/Sporton | RAN5#102 | R5-240937 |  | 1 | 100% | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Note on G12: DL CA configurations shall for bandwidth combination set (BCS) >0 is listed with suffix "BCSx" where x is the BCS number. E.g. CA configuration CA_3A-7C-28A is listed as "CA_3A-7C-28A" for BCS0 and as "CA_3A-7C-28A BCS1" for BCS1.
Note on G14: CA configurations with UL CA shall be listed as DL CA band combination + BCS /UL CA band combination. E.g . For DL CA_3A-7C-28A BCS1 with UL CA_3A-7A are to be listed as "CA_3A-7C-28A BCS1/UL CA_3A-7A.
Note on G15: CA configuration types are listed as CA_X<BWC>-Y<BWC>...-TzBWC>, where X, Y, Z, R, S and T are E-UTRA bands.
Note on N36: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N44: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N54: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on N62: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N71: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N100: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N115: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N125: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N132: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.