## Cover sheet
3GPP TSG-RAN WG5 Meeting #102 | [8 empty] | R5-241031
Athens, Greece, February 26 - March 1, 2024
Agenda Item: | 7.5.2
Source: | Huawei, China Telecom, CMCC, China Unicom
Title: | WP for UE Conformance - RF requirements enhancement for NR frequency range 1 (FR1)
Work item code: | NR_RF_FR1_enh-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of the UE Conformance Test Aspects for RF requirements enhancement for NR frequency range 1 (FR1) work item is to define the UE conformance requirements corresponding to WID on RF requirements for NR frequency range 1 (FR1) with Unique identifier 890062, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for the FR1 enhancement the RAN4 work item in Rel-16. At the RAN#96-e meeting the Rel-17 RAN5 work item for RF requirements enhancement for NR frequency range 1 (NR_RF_FR1_enh-UEConTest) was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item. Quite a few FR1 NR CA configurations for intra-band contiguous CA are impacted by the new requirements included in the scope of both "NR_RF_FR1_enh" WI. Only CA_n41C is selected as the example "UL intra-band contiguous CA configuration" to complete the test cases in "NR_RF_FR1_enh" WI. For remaining CA configurations, the relevant work will be traced by RAN5 PRD21. The intra-band non-contigous PC2 requirements are also part of this WI. However the requirements are not reflected in the WP since there is no ongoing intra-band non-contigous PC2 configuration that could be taken as example combination
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+51%) | 42 (+28) | 42 (+4)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 100% (+50.5%) | 42 (+28) | 42 (+4)
FR1 |  | 100% (+50.5%) | 42 (+28) | 42 (+4)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+85%) |  |  | 100% (+85%)
Common ICS | 38.508-2 | 100% (+70%) |  |  | 100% (+70%)
NR RF/RRM
FR1 RF common parts | 38.521-1 | 100% (+61.9%) |  |  | 100% (+61.9%)
FR1 RF Tx test cases | 38.521-1 Tx | 100% (+54.4%) | 36 (+26) | 36 (+4) | 100% (+54.4%) | 36 (+26) | 36 (+4)
RRM test cases | 38.533 | 100% (+42.5%) | 6 (+2) | 6 | 100% (+42.5%) | 6 (+2) | 6
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% (+60%) |  |  | 100% (+60%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 100% (+50%) |  |  | 100% (+50%)
Test Point analysis receiver and transmitter test cases | 38.905 | 100% (+50%) |  |  | 100% (+50%)
5 References
[1] RP-221848 | New WID on UE Conformance - RF requirements enhancement for NR frequency range 1 (FR1)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP for UE Conformance - RF requirements enhancement for NR frequency range 1 (FR1) | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_RF_FR1_enh-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item RF requirements enhancement for NR frequency range 1 (FR1) comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Chunying Gu, Huawei |  |  | guchunying@huawei.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
100% (+50.5%)
88 (+4)
82 (+13)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS - RAN and CN
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-1 | 4.6.3 | Radio resource control information elements | Updating message contents |  | RAN5#101 (Nov-23) |  |  | 0.3 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.508-1 | A.3 | Set up diagrams | Introducing new connection diagrams |  | RAN5#101 (Nov-23) | R5-236900 |  | 0.3 | 100% (+70%) | 100% (+70%) |  | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-2 | A.x | Annex A (normative):ICS proforma for NR/5GS Generation User Equipment | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | Huawei | RAN5#101 (Nov-23) | R5-224833 R5-235845 R5-235613 R5-236901 R5-241029 |  | 1 | 100% (+70%) | 100% (+70%) |  | 100%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 | 4.3. | Specification suffix information | Adding suffix H Removing limitation for SUL+MIMO for Rel-17 |  | RAN5#101 (Nov-23) |  | TS 38.101-1, 4.3 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 | F.1.2 | Measurement of transmitter | [Intra-band UL contiguous and non-contiguous CA] Intra-band contiguous: Adding MU for intra-band UL CA Intra-band non-contiguous: Adding MU for intra-band UL CA |  | RAN5#101 (Nov-23) | R5-231639 R5-234848 R5-236910 |  | 1 | 100% (+60%) | 100% (+60%) |  | 100%
|  | 38.521-1 | F.3.2 | Measurement of transmitter | [Intra-band UL contiguous and non-contiguous CA] Intra-band contiguous: Adding TT for intra-band UL CA Intra-band non-contiguous: Adding TT for intra-band UL CA |  | RAN5#101 (Nov-23) | R5-231639 R5-234848 R5-236910 |  | 1 | 100% (+60%) | 100% (+60%) |  | 100%
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.521-1 Tx | 6.1A | General | [Intra-band UL contiguous CA PC2] Adding instruction of RB allocations for intra-band UL CA PC2 |  | RAN5#101 (Nov-23) | R5-227936 | TS 38.101-1 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
6.2A Transmitter power for CA
|  | 38.521-1 Tx | 6.2A.1.0 | Minimum conformance requirements | [Intra-band UL contiguous CA PC2] Adding minimum requirements for PC2 | Huawei | RAN5#101 (Nov-23) | R5-224834 | TS 38.101-1 6.2A.1 No changes to test detail is needed. | 0.1 | 100% | 100% |  | 100%
|  | 38.521-1 Tx | 6.2A.1.1 | UE maximum output power for CA (2 UL CA) | [Intra-band UL contiguous CA PC2] No test point satisfying MPR=0. No changes are needed. | Huawei | RAN5#101 (Nov-23) |  | TS 38.101-1 6.2A.1.1 TS 38.522: TR 38.905: Note: CA_n41C is selected as example CA configuration to complete the test case | 0 | 100% | 100% |  | 100%
|  | 38.521-1 Tx | 6.2A.2.0 | Minimum conformance requirements | [Intra-band UL contiguous CA PC2] [Intra-band UL non-contiguous CA PC2] Adding minimum requirements for PC2 | Huawei | RAN5#101 (Nov-23) | R5-224835 | TS 38.101-1 6.2A.2 | 0.1 | 100% | 100% |  | 100%
|  | 38.521-1 Tx | 6.2A.2.1 | Maximum Power Reduction (MPR) for CA (2 UL CA) | [Intra-band UL contiguous CA PC2] Adding test configuration and test requirements for PC2 | Huawei | RAN5#101 (Nov-23) | R5-224835 | TS 38.101-1 6.2A.2.1 TS 38.522:R5-224839 TR 38.905:R5-225779 Note: CA_n41C is selected as example CA configuration to complete the test case No CA configuration specified for non-contiguous PC2. No test detail would be specified. PC2 test requirements with TxD iare missing | 1 | 100% | 100% |  | 100%
|  | 38.521-1 Tx | 6.2A.3.0 | Minimum conformance requirements | [Intra-band UL contiguous CA PC2] Adding minimum requirements for PC2 | Huawei | RAN5#101 (Nov-23) | R5-231641 | TS 38.101-1 6.2A.4 | 0.1 | 100% | 100% |  | 100%
|  | 38.521-1 Tx | 6.2A.3.1 | UE additional maximum output power reduction for CA (2UL CA) | [Intra-band UL contiguous CA PC2] Adding test configuration and test requirements for PC2 | Huawei | RAN5#101 (Nov-23) | R5-231641 R5-233036 | TS 38.101-1 6.2A.4.1 TS 38.522: R5-230829r1 TR 38.905: R5-231620 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  | 100%
|  | 38.521-1 Tx | 6.2A.4.0 | Minimum conformance requirements | [Intra-band UL contiguous CA PC2] Adding minimum requirements for PC2 | Huawei | RAN5#101 (Nov-23) | R5-224837 | TS 38.101-1 6.2A.4 | 0.1 | 100% | 100% |  | 100% | 100
|  | 38.521-1 Tx | 6.2A.4.1 | Configured transmitted power for CA (2 UL CA) | [Intra-band UL contiguous CA PC2] Adding test configuration and test requirements for PC2 | Huawei | RAN5#101 (Nov-23) | R5-224837 | TS 38.101-1 6.2A.4.1 TS 38.522: TR 38.905: Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  | 100%
6.2H Transmitter power for CA with UL MIMO
|  | 38.521-1 Tx | 6.2H.1 | Transmitter power for intra-band UL contiguous CA with UL MIMO | Sub-title |  | RAN5#101 (Nov-23) |  | TS 38.101-1 6.2H.1 | 0.1 | 100% | 100% |  | 100%
| Y | 38.521-1 Tx | 6.2H.1.1 | UE maximum output power for intra-band UL contiguous CA with UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO No test points as MPR is always larger than 0dB |  | RAN5#101 (Nov-23) | R5-236902 | TS 38.101-1 6.2H.1.1 TS 38.522: R5-236912 TR 38.905: R5-237935 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  | 100%
| Y | 38.521-1 Tx | 6.2H.1.2 | UE maximum output power reduction for intra-band UL contiguous CA with UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-237624 | TS 38.101-1 6.2H.1.2 TS 38.522: R5-236912 TR 38.905: R5-237935 Note: CA_n41C is selected as example CA configuration to complete the test case Editor’s Note: - Test tolerance for BW>100M is FFS. | 1 | 100% | 100% |  | 100%
| Y | 38.521-1 Tx | 6.2H.1.3 | UE additional maximum output power reduction for intra-band UL contiguous CA with UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R4-241970 | TS 38.101-1 6.2H.1.3 TS 38.522: R5-241988 TR 38.905: R5-241008 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.2H.1.4 | Configured transmitted power for intra-band UL contiguous CA with UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-237625 | TS 38.101-1 6.2H.1.4 TS 38.522: R5-236912 TR 38.905: R5-237935 Note: CA_n41C is selected as example CA configuration to complete the test case Editor’s Note: - Test tolerance for BW>100M is FFS. | 1 | 100% | 100% |  | 100%
6.3A Output power dynamics for CA
| Y | 38.521-1 Tx | 6.3A.3.0.3.3 | Time mask for switching between two uplink carriers with two transmit antenna connectors | [UL Tx switching] Minimum requirements for 2Tx-2Tx switching |  | RAN5#101 (Nov-23) | R5-234848 | TS 38.101-1 6.3A.3.3.3 TS 38.522 TR 38.905 | 1 | 100% | 100% |  | 100%
| Y | 38.521-1 Tx | 6.3A.3.0.3.4 | Time mask for switching between one uplink band with one transmit antenna connector and one uplink band with two transmit antenna connectors | [UL Tx switching] Minimum requirements for 1CC+2CC CA with 1Tx-2Tx switching |  | RAN5#101 (Nov-23) | R5-241983 | TS 38.101-1 6.3A.3.3.4 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.3A.3.0.3.5 | Time mask for switching between two uplink bands with two transmit antenna connectors | [UL Tx switching] Minimum requirements for 1CC+2CC CA with 2Tx-2Tx switching |  | RAN5#101 (Nov-23) | R5-241983 | TS 38.101-1 6.3A.3.3.5 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.3A.3.3 | Time mask for switching between two uplink carriers with two transmit antenna connectors | [UL Tx switching] The test case for 2Tx-2Tx switching |  | RAN5#101 (Nov-23) | R5-234848 | TS 38.101-1 6.3A.3.3.3 TS 38.522: R5-235802 TR 38.905: R5-234849 | 1 | 100% | 100% |  | 100%
| Y | 38.521-1 Tx | 6.3A.3.4 | Time mask for switching between one uplink band with one transmit antenna connector and one uplink band with two transmit antenna connectors (3UL CA) | [UL Tx switching] Minimum requirements for 1CC+2CC CA with 1Tx-2Tx switching |  | RAN5#101 (Nov-23) | R5-241983 | TS 38.101-1 6.3A.3.3.5 TS 38.522: R5-241988 TR 38.905: R5-241008 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.3A.3.5 | Time mask for switching between two uplink bands with two transmit antenna connectors (3UL CA) | [UL Tx switching] Minimum requirements for 1CC+2CC CA with 2Tx-2Tx switching |  | RAN5#101 (Nov-23) | R5-241984 | TS 38.101-1 6.3A.3.3.5 TS 38.522: R5-241988 TR 38.905: R5-241008 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
6.3C Output power dynamics for SUL
| Y | 38.521-1 Tx | 6.3C.3.0.2 | Time mask for switching between two uplink carriers with two transmit antenna connectors | [UL Tx switching] Minimum requirements for 2Tx-2Tx switching between UL carrier and SUL carrier |  | RAN5#101 (Nov-23) | R5-241985 | TS 38.101-1 6.3C.3.2 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.3C.3.0.3 | Time mask for switching between one uplink band with one transmit antenna connector and one uplink band with two transmit antenna connectors | [UL Tx switching] Minimum requirements for 2 UL carriers +1 SUL carrier with 1Tx-2Tx switching |  | RAN5#101 (Nov-23) | R5-241985 | TS 38.101-1 6.3C.3.3 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.3C.3.0.4 | Time mask for switching between two uplink bands with two transmit antenna connectors | [UL Tx switching] Minimum requirements for 2 UL carriers +1 SUL carrier with 2Tx-2Tx switching |  | RAN5#101 (Nov-23) | R5-241985 | TS 38.101-1 6.3C.3.4 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.3C.3.3 | General transmit ON/OFF time mask for switching between two uplink carriers with two transmit antenna connectors | [UL Tx switching] The test case for 2Tx-2Tx switching |  | RAN5#101 (Nov-23) | R5-241985 | TS 38.101-1 6.3C.3.2 TS 38.522 TR 38.905 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.3C.3.4 | General transmit ON/OFF time mask for switching between one uplink band with one transmit antenna connector and one uplink band with two transmit antenna connectors | [UL Tx switching] The test case for 1CC-2CC SUL configuration with 1Tx-2Tx switching |  | RAN5#101 (Nov-23) | R5-241986 | TS 38.101-1 6.3C.3.2 TS 38.522: R5-241988 TR 38.905: R5-241008 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.3C.3.5 | General transmit ON/OFF time mask for switching between two uplink bands with two transmit antenna connectors | [UL Tx switching] The test case for 1CC-2CC SUL configuration with 1Tx-2Tx switching |  | RAN5#101 (Nov-23) | R5-241987 | TS 38.101-1 6.3C.3.2 TS 38.522: R5-241988 TR 38.905: R5-241008 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
6.3H Output power dynamics for with UL MIMO
|  | 38.521-1 Tx | 6.3H.1 | Output power dynamics for intra-band UL contiguous CA with UL MIMO | Sub-title |  | RAN5#101 (Nov-23) | R5-237626 | TS 38.101-1 6.3H.1 | 0.1 | 100% | 100% |  | 100%
| Y | 38.521-1 Tx | 6.3H.1.1 | Minimum output power for intra-band UL contiguous CA with UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-237626 | TS 38.101-1 6.3H.1.1 TS 38.522 R5-236912 TR 38.905 R5-237935 Note: CA_n41C is selected as example CA configuration to complete the test case Editor’s Note: - Test tolerance for BW>100M is FFS. | 1 | 100% | 100% |  | 100%
| Y | 38.521-1 Tx | 6.3H.1.2 | Transmit OFF power for intra-band UL contiguous CA with UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-237627 | TS 38.101-1 6.3H.1.2 TS 38.522 R5-236912 TR 38.905 R5-237935 Note: CA_n41C is selected as example CA configuration to complete the test case Editor’s Note: - Test tolerance for BW>100M is FFS. | 1 | 100% | 100% |  | 100%
| Y | 38.521-1 Tx | 6.3H.1.3 | Transmit ON/OFF time mask for intra-band UL contiguous CA with UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-237628 | TS 38.101-1 6.3H.1.3 TS 38.522 R5-236912 TR 38.905 R5-237935 Note: CA_n41C is selected as example CA configuration to complete the test case Editor’s Note: - Test tolerance for BW>100M is FFS. | 1 | 100% | 100% |  | 100%
|  | 38.521-1 Tx | 6.3H.1.4 | Power control for intra-band UL contiguous CA with UL MIMO | Sub-title |  | RAN5#101 (Nov-23) | R5-241010 | TS 38.101-1 6.3H.1.4 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 Tx | 6.3H.1.4.0 | Minimum conformance requirements | [Intra-band UL contiguous CA+UL-MIMO] Add the minimum requirements |  | RAN5#101 (Nov-23) | R5-241010 | TS 38.101-1 6.3H.1.4 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.3H.1.4.1 | Absolute power tolerance for intra-band UL contiguous CA with UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241010 | TS 38.101-1 6.3H.1.4 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.3H.1.4.2 | Relative power tolerance for intra-band UL contiguous CA with UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241010 | TS 38.101-1 6.3H.1.4 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.3H.1.4.3 | Aggregate power tolerance for intra-band UL contiguous CA with UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241010 | TS 38.101-1 6.3H.1.4 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% (+100%) | 100% (+100%) |  | 100%
6.4D Transmit signal quality for UL MIMO
|  | 38.521-1 Tx | 6.4D.4 | Requirements for coherent UL MIMO | [UL Tx switching] Updating minimum conformance requirements Test method pending on RAN4/RAN5 further discussion |  | RAN5#101 (Nov-23) | R5-241023 | TS 38.101-1 6.3H.1 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
6.4H Transmit signal quality for CA with UL MIMO
|  | 38.521-1 Tx | 6.4H.1 | Transmit signal quality for intra-band UL contiguous CA for UL MIMO | Sub-title |  | RAN5#101 (Nov-23) | R5-241971 | TS 38.101-1 6.4H.1 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.4H.1.1 | Frequency error for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241971 | TS 38.101-1 6.4H.1.1 TS 38.522: R5-241988 TR 38.905: R5-241008 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 Tx | 6.4H.1.2 | Transmit modulation quality for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241972 | TS 38.101-1 6.4H.1.2 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 Tx | 6.4H.1.2.0 | Minimum conformance requirements | [Intra-band UL contiguous CA+UL-MIMO] Add the minimum requirements |  | RAN5#101 (Nov-23) | R5-241972 | TS 38.101-1 6.4H.1.2 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.4H.1.2.1 | Error Vector Magnitude for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241972 | TS 38.101-1 6.4H.1.2.1 TS 38.522: R5-241988 TR 38.905: R5-241008 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.4H.1.2.2 | Carrier leakage for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241973 | TS 38.101-1 6.4H.1.2. TS 38.522: R5-241988 TR 38.905: R5-241008 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.4H.1.2.3 | In-band emissions for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241974 | TS 38.101-1 6.4H.1.2.3 TS 38.522: R5-241988 TR 38.905: R5-241008 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.4H.1.3 | Time alignment error for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241975 | TS 38.101-1 6.4H.1.3 TS 38.522: R5-241988 TR 38.905: R5-241008 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.4H.1.4 | Coherent UL MIMO requirement for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241976 | TS 38.101-1 6.4H.1.4 TS 38.522: R5-241988 TR 38.905: R5-241008 Note: CA_n41C is selected as example CA configuration to complete the test case Editor’s note: This clause is incomplete. The following aspects are either missing or not yet determined: - Test config table is still FFS. - Scheduling pattern within 20ms measurement window is FFS - The test procedure is FFS. - MU and TT value are still FFS | 1 | 100% (+100%) | 100% (+100%) |  | 100%
6.5A Output RF spectrum emissions for CA
65 |  | 38.521-1 Tx | 6.5A.2.2.0 | Minimum conformance requirements | [Intra-band UL contiguous CA PC2] Adding minimum requirements for PC2 |  | RAN5#101 (Nov-23) | R5-224838 | TS 38.101-1, 6.5A.2.2 | 0.1 | 100% | 100% |  | 100%
66 |  | 38.521-1 Tx | 6.5A.2.2.1 | Spectrum emission mask for CA (2UL CA) | [Intra-band UL contiguous CA PC2] Adding test configuration and test requirements for PC2. Test points should be aligned with MPR |  | RAN5#101 (Nov-23) | R5-224838 R5-230974 | TS 38.101-1, 6.5A.2.2.1 TS 38.522: TR 38.905: Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  | 100%
65 |  | 38.521-1 Tx | 6.5A.2.3.0 | Minimum conformance requirements | [Intra-band UL contiguous CA PC2] Adding minimum requirements for PC2 |  | RAN5#101 (Nov-23) | R5-231642 | TS 38.101-1, 6.5A.2.3 | 0.1 | 100% | 100% |  | 100%
66 |  | 38.521-1 Tx | 6.5A.2.3.1 | Additional spectrum emission mask for CA (2UL CA) | [Intra-band UL contiguous CA PC2] No new test point for PC2. Test procedure needs to consider dualPA-Architecture |  | RAN5#101 (Nov-23) | R5-231642 | TS 38.101-1, 6.5A.2.3 TS 38.522: R5-230829r1 TR 38.905: R5-231620 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  | 100%
72 |  | 38.521-1 Tx | 6.5A.2.4.1.0 | Minimum conformance requirements | [Intra-band UL contiguous CA PC2] Adding minimum requirements for PC2 |  | RAN5#101 (Nov-23) | R5-231644 | TS 38.101-1, 6.5A.2.4.1 | 0.1 | 100% | 100% |  | 100%
73 |  | 38.521-1 Tx | 6.5A.2.4.1.1 | NR ACLR for CA (2UL CA) | [Intra-band UL contiguous CA PC2] New test requirements for PC2 Test procedure needs to consider dualPA-Architecture |  | RAN5#101 (Nov-23) | R5-231644 | TS 38.101-1, 6.5A.2.4.1 TS 38.522: R5-230829r1 TR 38.905: R5-231621 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  | 100%
75 |  | 38.521-1 Tx | 6.5A.3.1.0 | Minimum conformance requirements | [Intra-band UL contiguous CA PC2] Adding minimum requirements for PC2 |  | RAN5#101 (Nov-23) | R5-231645 | TS 38.101-1, 6.5A.3.1 | 0.1 | 100% | 100% |  | 100%
76 |  | 38.521-1 Tx | 6.5A.3.1.1 | General spurious emissions for CA (2UL CA) | [Intra-band UL contiguous CA PC2] No new test point for PC2. Test procedure needs to consider dualPA-Architecture |  | RAN5#101 (Nov-23) | R5-231645 R5-232348 | TS 38.101-1, 6.5A.3.1 TS 38.522: R5-230829r1 TR 38.905: R5-231622 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  | 100%
78 |  | 38.521-1 Tx | 6.5A.3.2.0 | Minimum conformance requirements | [Intra-band UL contiguous CA PC2] Adding minimum requirements for PC2 |  | RAN5#101 (Nov-23) | R5-231646 | TS 38.101-1, 6.5A.3.2 | 0.1 | 100% | 100% |  | 100%
79 |  | 38.521-1 Tx | 6.5A.3.2.1 | Spurious emissions for UE co-existence for CA (2UL CA) | [Intra-band UL contiguous CA PC2] No new test point for PC2. Test procedure needs to consider dualPA-Architecture |  | RAN5#101 (Nov-23) | R5-231646 R5-233037 | TS 38.101-1, 6.5A.3.2 TS 38.522: R5-230829r1 TR 38.905: R5-231624 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  | 100%
78 |  | 38.521-1 Tx | 6.5A.3.3.0 | Minimum conformance requirements | [Intra-band UL contiguous CA PC2] Adding minimum requirements for PC2 |  | RAN5#101 (Nov-23) | R5-231643 | TS 38.101-1, 6.5A.3.3 | 0.1 | 100% | 100% |  | 100%
79 |  | 38.521-1 Tx | 6.5A.3.3.1 | Additional spurious emissions for CA (2UL CA) | [Intra-band UL contiguous CA PC2] No new test point for PC2. Test procedure needs to consider dualPA-Architecture |  | RAN5#101 (Nov-23) | R5-231643 | TS 38.101-1, 6.5A.3.3 TS 38.522: R5-230829r1 TR 38.905: R5-231620 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  | 100%
6.5H Output RF spectrum emissions for CA with UL MIMO
|  | 38.521-1 Tx | 6.5H.1 | Output RF spectrum emissions for intra-band UL contiguous CA for UL MIMO | Sub-title |  | RAN5#101 (Nov-23) | R5-241977 | TS 38.101-1 6.5H.1 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.5H.1.1 | Occupied bandwidth for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241977 | TS 38.101-1 6.5H.1.1 TS 38.522: R5-241988 TR 38.905: R5-241008 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 Tx | 6.5H.1.2 | Out of band emission for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241978 | TS 38.101-1 6.5H.1.2 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 Tx | 6.5H.1.2.0 | Minimum conformance requirements | [Intra-band UL contiguous CA+UL-MIMO] Add the minimum requirements |  | RAN5#101 (Nov-23) | R5-241978 | TS 38.101-1 6.5H.1.2 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.5H.1.2.1 | Spectrum emission mask for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-236908 | TS 38.101-1 6.5H.1.2 TS 38.522 R5-236912 TR 38.905 R5-237935 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% | 100% |  | 100%
| Y | 38.521-1 Tx | 6.5H.1.2.2 | Additional spectrum emission mask for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241978 | TS 38.101-1 6.5H.1.2 TS 38.522: R5-241988 TR 38.905: R5-241008 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.5H.1.2.3 | NR ACLR for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-237629 | TS 38.101-1 6.5H.1.2 TS 38.522 R5-236912 TR 38.905 R5-237935 Note: CA_n41C is selected as example CA configuration to complete the test case Editor’s Note: - Test tolerance for BW>100M is FFS. | 1 | 100% | 100% |  | 100%
|  | 38.521-1 Tx | 6.5H.1.3 | Spurious emission for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241979 | TS 38.101-1 6.5H.1.3 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 Tx | 6.5H.1.3.0 | Minimum conformance requirements | [Intra-band UL contiguous CA+UL-MIMO] Add the minimum requirements |  | RAN5#101 (Nov-23) | R5-241979 | TS 38.101-1 6.5H.1.3 | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.5H.1.3.1 | General spurious emissions for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241979 | TS 38.101-1 6.5H.1.3 TS 38.522: R5-241988 TR 38.905: R5-241008 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.5H.1.3.2 | Spurious emissions for UE co-existence for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241980 | TS 38.101-1 6.5H.1.3 TS 38.522: R5-241988 TR 38.905: R5-241008 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.5H.1.3.3 | Additional spurious emissions for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241981 | TS 38.101-1 6.5H.1.3 TS 38.522: R5-241988 TR 38.905: R5-241008 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.521-1 Tx | 6.5H.1.4 | Transmit intermodulation for intra-band UL contiguous CA for UL MIMO | [Intra-band UL contiguous CA+UL-MIMO] Specify the new test case for UL CA+MIMO |  | RAN5#101 (Nov-23) | R5-241982 | TS 38.101-1 6.5H.1.4 TS 38.522: R5-241988 TR 38.905: R5-241008 Note: CA_n41C is selected as example CA configuration to complete the test case | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
|  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Adding applicability for test cases in 38.521-1 |  | RAN5#101 (Nov-23) | R5-224839 R5-230829r R5-235802 R5-236912 R5-241988 |  | 1 | 100% (+60%) | 100% (+60%) |  | 100%
|  | 38.522 | 4.2 | RRM conformance test cases | Adding applicability for test cases in 38.533 |  | RAN5#101 (Nov-23) | R5-235801 R5-240368 |  | 1 | 100% (+60%) | 100% (+60%) |  | 100%
TS 38.533: RRM test cases
| Y | 38.533 | 6.5.7A.1 | NR SA FR1 DL interruptions at switching between two uplink carriers in FDD-TDD CA | Adding new RRM test case | China Telecom | RAN5#101 (Nov-23) | R5-240369 | TS 38.133 A.6.5.7A.1 38.903 CR: R5-240373 38.522 CR: R5-230368 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.533 | 6.5.7A.2 | NR SA FR1 DL interruptions at switching between two uplink carriers in TDD-TDD CA | Adding new RRM test case | Nokia | RAN5#101 (Nov-23) | R5-234351r1 | TS 38.133 A.6.5.7A.2 38.903 CR: R5-234349 38.522 CR: R5-235801 | 1 | 100% | 100% |  | 100%
| Y | 38.533 | 6.5.7B.1 | NR SA FR1 DL interruptions at switching between two uplink bands in FDD-TDD CA | Adding new RRM test case | China Telecom | RAN5#101 (Nov-23) | R5-241896 | TS 38.133 A.6.5.7B.1 38.903 CR: R5-240374 38.522 CR: R5-230368 | 1 | 100% (+100%) | 100% (+100%) |  | 100%
| Y | 38.533 | 6.5.7B.2 | NR SA FR1 DL interruptions at switching between two uplink bands in TDD-TDD CA | Adding new RRM test case | Nokia | RAN5#101 (Nov-23) | R5-234352r1 | TS 38.133 A.6.5.7B.2 38.903 CR: R5-234350 38.522 CR: R5-235801 | 1 | 100% | 100% |  | 100%
| Y | 38.533 | 6.5.7C.1 | NR SA FR1 DL interruptions at switching between two uplink bands with two transmit antenna connectors in FDD-TDD CA | Adding new RRM test case | Nokia | RAN5#101 (Nov-23) | R5-235706 R5-236216 | TS 38.133 A.6.5.7C.1 38.903: R5-236214 38.522: | 1 | 100% | 100% |  | 100%
| Y | 38.533 | 6.5.7C.2 | NR SA FR1 DL interruptions at switching between two uplink bands with two transmit antenna connectors in TDD-TDD CA | Adding new RRM test case | Nokia | RAN5#101 (Nov-23) | R5-234354r1 R5-236217 | TS 38.133 A.6.5.7C.2 38.903: R5-236215 38.522: | 1 | 100% | 100% |  | 100%
|  | 38.533 | Annex E | Cell configuration mapping |  |  | RAN5#101 (Nov-23) | R5-234351r1 R5-234352r1 R5-235706 R5-234354r1 R5-241832 |  | 1 | 100% (+90%) | 100% (+90%) |  | 100%
|  | 38.533 | Annex F | Measurement uncertainties and test tolerances |  |  | RAN5#101 (Nov-23) | R5-234776 R5-240372 |  | 1 | 100% (+50%) | 100% (+50%) |  | 100%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | Adding TT analysis for RRM test cases |  | RAN5#93 (Nov-21) | R5-234349 R5-234350 R5-236214 R5-236215 R5-240373 R5-240374 |  | 10 | 100% (+50%) | 100% (+50%) |  | 100%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 | 4.1 | Test point analysis for FR1 test cases in TS 38.521-1 | Adding TP analysis for test cases in 38.521-1 |  | RAN5#98 (Feb-23) | R5-225779 R5-231620 R5-231621 R5-231622 R5-231624 R5-237935 R5-236911r2 R5-241008 |  | 10 | 100% (+50%) | 100% (+50%) |  | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.