## Cover sheet
3GPP TSG-RAN WG5 meeting #102 | [6 empty] | R5-241439
Athens, Greece, Feb 26th to Mar 1st, 2024
Agenda Item:
Source: | Apple
Title: | Internal WP UE Conformance Test Aspects for NR RF FR2 Enhanced Test Methods
Work item code: | Not Applicable
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to incorporate the outcomes of the FR2 Enhanced Test Methods into RAN5 specifications.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 85% | - | - | Pending Rel17 Testability Topics which can be covered as part of Release 17 maintainance as part of the TEI_Test and corresponding WIDs 1) High DL/Low UL Impacted Tests : Awaiting completion of n262 testability MU to identify for which tests the issues can be removed 2) UL Demod Enhancements topics related to the NOTE 1 in the Work Plan (See details on pending actions)
Completion Compensation |  | -
| Note 1: | No new tests are added as part of this WP. The count refers to any additional tests on which impact due to the FR2 Enhanced Test Methods was identified
5 References
[1] RP-210363 | 5GS UE Conformance Test Aspects
[2] RP-212304 | Study on FR2 RF Enhanced Test Methods
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects for NR RF FR2 Enhanced Test Methods | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | Not Applicable
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for FR2 RF Enhanced Test Methods comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Ashwin Mohan, Apple |  |  | ashwin_mohan@apple.com | [7 empty] | WP item completion |  |  | SA Option 2 (SA NR) | NSA Option 3
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | Release Applicability for Test Method/Enhancement in Column F | Associated WIC to bring in Contribution (Contributors to check and re-confirm) | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR2 | FR2
[16 empty] | 87% (+6%) | 85% (+3%)
|  |  |  | Release Applicability for Test Method/Enhancement in Column F1) 6.2.1 Min Peak EIRP and Spherical Cov with autonomously chosen UL beam and without UL beam sweeping. Use 6.6.4.3.3 CSI-RS -based Enh BCorr side conditions | [11 empty] | 147 (+147) | 147 (+147)
[16 empty] | 20.5 (+20.5) | 20.5 (+20.5)
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  |  | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | TBD
1 |  | 38.508-1 | 4.3 | Reference test conditions | Add necessary test conditions for Rel-16 NR RF FR2 aspects |  | RAN5#101 (Nov-23) |  | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.1 | 100% | 100% |  | 100% | 100%
2 |  | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | New message and IE definition for new Rel-16 NR RF FR2 features |  | RAN5#99 (May-23) | Rel15 | TEI15_test, 5GS_NR_LTE-UEConTest | R5-224118r1 |  | 0.1 | 100% | 100% |  | 100% | 100%
3 |  | 38.508-1 | 5 | Test environments for RF test | New testing methodologies needs to be added also to section 5.1.1.3 and associated sub-clauses *NOTE 2* |  | RAN5#101 (Nov-23) |  | TEI15_test, 5GS_NR_LTE-UEConTest |  | NF based test methods are currently deprioritized and can be revisited in Release 18 | 0.1 | 100% | 100% |  | 100% | 100%
|  | 38.508-1 | Annex B |  | Will require updates if new test methodologies are finally accepted after analysis and discussion | Keysight | RAN5#99 (May-23) |  | TEI15_Test |  |  |  | 100% | 100% |  | 100% | 100%
TS 38.508-2: Common ICS
4 |  | 38.508-2 | A,4 | ICS proforma tables | Add ICS as needed for the updates that need new vendor declarations for conformance testing |  | RAN5#101 (Nov-23) |  |  |  |  | 0.1 | 100% | 100% |  | 100% | 100%
NR RF/RRM
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  | RAN5#101 (Nov-23) |  |  |  |  | TBD
|  | 38.521-2 | 2 | References | Update references to Rel.16 and Rel.17 SID/WID |  | RAN5#101 (Nov-23) |  |  |  |  | 0.5 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreviations respectively |  | RAN5#99 (May-23) | Rel15 | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 | 4 | General | Incorporate applicability statement from TR 38.884 for the enhanced FR2 RF test methods |  | RAN5#99 (May-23) | Rel15 | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 | 5 | Operating bands and Channel arrangement | Frequency Separation Classes, Intra-band and Inter-band CA configuration updates |  | RAN5#99 (May-23) | Rel15 | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 | Annex A | Measurement channels | Pending review of new test methodologies and any changes to the test parameters brought in by the same. *NOTE* |  | RAN5#101 (Nov-23) | FFS | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 | Annex B | Propagation conditions | Pending review of new test methodologies and any changes to the test parameters brought in by the same. *NOTE* |  | RAN5#101 (Nov-23) | FFS | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 | Annex C | Downlink physical channels | Pending review of new test methodologies and any changes to the test parameters brought in by the same. *NOTE* |  | RAN5#101 (Nov-23) | FFS | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 | Annex D | Interfering signals | Define any updates to characteristics of the interfering signal updates in Rel-16 NR RF FR2 tests |  | RAN5#101 (Nov-23) |  | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 | Annex E | Global In-Channel TX-Test | Pending review of new test methodologies and any changes to the test parameters brought in by the same. *NOTE* |  | RAN5#101 (Nov-23) | FFS | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT for new test methodologies *NOTE 2* | Keysight | RAN5#101 (Nov-23) | FFS | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 | Annex G | Uplink Physical Channels | TBD |  | RAN5#101 (Nov-23) |  | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 | Annex H | Statistical Testing | TBD |  | RAN5#101 (Nov-23) |  | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0.5 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 | Annex J |  | Will require updates if new test methodologies are finally accepted after analysis and discussion | Keysight | RAN5#101 (Nov-23) |  | TEI15_test, 5GS_NR_LTE-UEConTest |  |  | 0 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 | Annex K | EIRP, TRP, EIS Measurement Procedures | Add RSRP-B based Peak Beam Search Fast Spherical Coverage Single Link Polarization Measurement | Apple | RAN5#101 (Nov-23) | Rel-15 | NR_RF_FR2_req_enh2-UEConTest/TEI15_test | R5-224119r1 (TPMI MU) | MU impact assessment requires TE vendor expertise | 0.5 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 | Annex M | Measurement Grids | Non-Uniform TRP measurement Grids |  | RAN5#101 (Nov-23) | Rel-15 | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | MU impact assessment requires TE vendor expertise | 0.5 | 70%% | 70%% |  | 70%% | 70%%
TS 38.521-2: FR2 RF test cases - Tx
|  | 38.521-2 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [7 empty] | TBD
|  | 38.521-2 Tx | 6.2.1.1 | UE maximum output power - EIRP and TRP | Check for references to test time reduction TPMI Method Introduction (For UEs supporting TxD) Evaluate Single Link Polarization based Peak EIRP and Tx Beam Peak Search (UE declaration) | Apple | RAN5#101 (Nov-23) |  | NR_RF_TxD-UEConTest |  |  | 1
|  | 38.521-2 Tx | 6.2.1.2 | UE maximum output power - Spherical coverage | Check for references to test time reduction (fast spherical cov), TPMI Method Introduction (For UEs supporting TxD) | Apple | RAN5#101 (Nov-23) | Rel-15 | NR_RF_TxD-UEConTest | R5-224121r1 (Fast Sph Cov-Tx) |  | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Tx | 6.2.2 | UE maximum output power reduction | Check for references to test time reduction TPMI Method Introduction (For UEs supporting TxD) | Keysight | RAN5#101 (Nov-23) |  | NR_RF_TxD-UEConTest |  |  | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Tx | 6.2.3 | UE maximum output power with additional requirements | Check for references to test time reduction TPMI Method Introduction (For UEs supporting TxD) | Keysight | RAN5#101 (Nov-23) |  | NR_RF_TxD-UEConTest |  |  | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Tx | 6.2.4 | Configured transmitted power | Check for references to test time reduction TPMI Method Introduction (For UEs supporting TxD) | Keysight | RAN5#101 (Nov-23) |  | NR_RF_TxD-UEConTest |  |  | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Tx | 6.2D.1.1 | UE maximum output power - EIRP and TRP (UL-MIMO) | TPMI Method Introduction | Apple | RAN5#101 (Nov-23) |  | NR_RF_TxD-UEConTest |  |  | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Tx | 6.2D.1.2 | UE maximum output power - Spherical coverage (UL-MIMO) | TPMI Method Introduction | Apple | RAN5#101 (Nov-23) |  | NR_RF_TxD-UEConTest |  |  | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Tx | 6.2D.2 | UE maximum output power reduction (ULMIMO) | TPMI Method Introduction | Keysight | RAN5#101 (Nov-23) |  | NR_RF_TxD-UEConTest |  |  | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Tx | 6.2D.3 | UE maximum output power with additional requirements (UL-MIMO) | TPMI Method Introduction | Keysight | RAN5#101 (Nov-23) |  | NR_RF_TxD-UEConTest |  |  | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Tx | 6.2D.4 | Configured transmitted power (UL-MIMO) | TPMI Method Introduction | Keysight | RAN5#101 (Nov-23) |  | NR_RF_TxD-UEConTest |  |  | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Tx | 6.3.1 | Minimum output power | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test | R5-227823 | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Tx | 6.3.2 | Transmit OFF power | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Tx | 6.3.3 | Transmit ON/OFF time mask | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Tx | 6.5.1 | Occupied bandwidth | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test | R5-227823 | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 0 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Tx | 6.5.2.3 | Adjacent channel leakage ratio | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Tx | 6.5.3.2 | Additional spurious emissions | High DL Power/ Low UL Power *NOTE 2* | Qualcomm | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test | R5-227823 | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 0 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Tx | 6.4.1 | Frequency Error | UL Demod Measurement Enhancements |  | RAN5#101 (Nov-23) |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  |  | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Tx | 6.4.2 | Transmit Modulation Quality | UL Demod Measurement Enhancements |  | RAN5#101 (Nov-23) |  | NR_RF_FR2_req_enh2-UEConTest |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.4.2.1 | Error Vector Magnitude | UL Demod Measurement Enhancements, Details related to AP#96e.29 and AP#96e.30 (see Note Below) will also be covered in this Work Plan |  | RAN5#101 (Nov-23) |  | NR_RF_FR2_req_enh2-UEConTest |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.4.2.2 | Carrier Leakage | UL Demod Measurement Enhancements |  | RAN5#101 (Nov-23) |  | NR_RF_FR2_req_enh2-UEConTest |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.4.2.3 | In-band Emissions | UL Demod Measurement Enhancements |  | RAN5#101 (Nov-23) |  | NR_RF_FR2_req_enh2-UEConTest |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.4.2.4 | EVM equalizer spectrum flatness | UL Demod Measurement Enhancements, Details related to AP#96e.29 and AP#96e.30 (see Note Below) will also be covered in this Work Plan |  | RAN5#101 (Nov-23) |  | NR_RF_FR2_req_enh2-UEConTest |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-2 Tx | 6.4.2.5 | EVM spectral flatness for pi/2 BPSK modulation | UL Demod Measurement Enhancements, Details related to AP#96e.29 and AP#96e.30 (see Note Below) will also be covered in this Work Plan |  | RAN5#101 (Nov-23) |  |  |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
Equivalent CA tests to be analyzed for applicability here
TBD |  | 38.521-2 Annex |  |  | Incorporation of 6x2 Measurement Grids in TS 38.521-2 |  | RAN5#101 (Nov-23) |  | NR_RF_FR2_req_enh2-UEConTest |  |  | 1 | 100% | 100% |  | 100% | 100%
TS 38.521-2: FR2 RF test cases - Rx
|  | 38.521-2 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [7 empty] | TBD
|  | 38.521-2 Rx | 7.3 | Receiver Sensitivity | Rx Fast Spherical Coverage | Keysight | RAN5#101 (Nov-23) | Rel15 | NR_RF_FR2_req_enh2-UEConTest/TEI15_test | R5-224121r1 (Fast Sph Cov-Tx) | Newly added due to Fast Spherical Coverage update impact | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Rx | 7.4 | Maximum input power | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Rx | 7.5 | Adjacent channel selectivity (case 1) | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test | R5-227823 | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 0 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Rx | 7.5 | Adjacent channel selectivity (case 2) | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Rx | 7.6.2 | In-band blocking | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test | R5-227823 | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 0 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Rx | 7.9 | Receiver spurious emissions | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-2 Rx |  | Receiver Inter-band CA tests (expand List of tests) | Inter-band CA Test Enhancements | Apple | RAN5#101 (Nov-23) |  | FFS |  | Has to be evaluated for IBM and CBM combos in Rel17
Equivalent CA tests to be analyzed for applicability here
TS 38.521-3: EN-DC FR2 RF test cases - necessary updates
|  | 38.521-3 | 6.2B.1.4 | UE Maximum Output Power for Inter-Band EN-DC including FR2 | Check for references to test time reduction TPMI Method Introduction (For UEs supporting TxD) | Apple | RAN5#101 (Nov-23) |  | NR_RF_TxD-UEConTest |  | Evaluation completed. TPMI does not have imapct on existing tests as UL-MIMO tests cover this aspect (endorsed by RAN5) | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-3 | 6.2B.1.4.1 | UE Maximum Output Power for Inter-Band EN-DC including FR2 - EIRP and TRP | Check for references to test time reduction TPMI Method Introduction (For UEs supporting TxD) | Apple | RAN5#101 (Nov-23) |  | NR_RF_TxD-UEConTest |  | Evaluation completed. TPMI does not have imapct on existing tests as UL-MIMO tests cover this aspect (endorsed by RAN5) | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-3 | 6.2B.1.4.2 | UE Maximum Output Power for Inter-Band EN-DC including FR2 (1 NR CC) - Spherical Coverage | Check for references to test time reduction TPMI Method Introduction (For UEs supporting TxD) | Apple | RAN5#101 (Nov-23) |  | NR_RF_TxD-UEConTest |  | Evaluation completed. TPMI does not have imapct on existing tests as UL-MIMO tests cover this aspect (endorsed by RAN5) | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-3 | 6.2B.2.4 | UE Maximum Output power reduction for inter-band EN-DC including FR2 (1 NR CC) | Check for references to test time reduction TPMI Method Introduction (For UEs supporting TxD) | Apple | RAN5#101 (Nov-23) |  | NR_RF_TxD-UEConTest |  | Evaluation completed. TPMI does not have imapct on existing tests as UL-MIMO tests cover this aspect (endorsed by RAN5) | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-3 | 6.2B.1.4D | UE Maximum Output Power for Inter-Band EN-DC including FR2 for UL MIMO | TPMI Method Introduction | Keysight | RAN5#101 (Nov-23) |  | NR_RF_TxD-UEConTest |  | Evaluation completed. TPMI does not have imapct on existing tests as UL-MIMO tests cover this aspect (endorsed by RAN5) | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-3 | 6.2B.4.1.4 | Configured Output power level for inter-band EN-DC including FR2 (1 NR CC) | Check for references to test time reduction TPMI Method Introduction (For UEs supporting TxD) | Keysight | RAN5#101 (Nov-23) |  | NR_RF_TxD-UEConTest |  | Evaluation completed. TPMI does not have imapct on existing tests as UL-MIMO tests cover this aspect (endorsed by RAN5) | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-3 | 6.3B.1.4 | Minimum output power for inter-band EN-DC including FR2 (1 NR CC) | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-3 | 6.3B.2.4 | Transmit OFF Power for inter-band EN-DC including FR2 (1 NR CC) | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-3 | 6.5B.1.4 | Occupied bandwidth for inter-band EN-DC including FR2 (1 NR CC) | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-3 | 6.5B.2.4.3 | Adjacent channel leakage ratio for Inter-band EN-DC including FR2 (1 NR CC) | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-3 | 6.4B.1.4 | Frequency Error for inter-band EN-DC including FR2 (1 NR CC) | UL Demod Measurement Enhancements - NOTE 1 |  | RAN5#101 (Nov-23) |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-3 | 6.4B.2.4 | Transmit Modulation Quality for inter-band EN-DC including FR2 |  |  |  |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-3 | 6.4B.2.4.1 | Error Vector Magnitude for inter-band EN-DC including FR2 (1 NR CC) | UL Demod Measurement Enhancements |  | RAN5#101 (Nov-23) |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | NOTE 1 | 1 | 0% | 0% |  | 0% | 0%
|  | 38.521-3 | 7.4B.4 | Maximum Input Level for inter-band EN-DC including FR2 (1 NR CC) | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-3 | 7.5B.4 | Adjacent Channel Selectivity for inter-band EN-DC including FR2 (1 NR CC) | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-3 | 7.6B.2.4 | Inband blocking for inter-band EN-DC including FR2 (2 CCs) | High DL Power/ Low UL Power *NOTE 2* | Keysight | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 100% | 100% |  | 100% | 100%
|  | 38.521-3 | 7.9B.4 | Spurious Emissions for inter-band EN-DC including FR2 (1 NR CC) | High DL Power/ Low UL Power *NOTE 2* | Qualcomm | RAN5#99 (May-23) | FFS | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  | See NOTE2. Evaluation completed in Release 17 and further details are part of future study/release | 1 | 100% | 100% |  | 100% | 100%
Equivalent CA tests to be analyzed for applicability here
|  | 38.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
|  | 38.521-3 | Annex G | Uplink Physical Channels | TBD |  | RAN5#101 (Nov-23) |  |  |  |  | 0.1
|  | 38.521-3 | Annex H | Statistical Testing | TBD |  | RAN5#101 (Nov-23) |  |  |  |  | 0.1
|  | 38.521-3 | Annex K | EIRP, TRP, EIS Measurement Procedures | Add RSRP-B based Peak Beam Search Fast Spherical Coverage Single Link Polarization Measurement | Apple | RAN5#101 (Nov-23) |  | NR_RF_FR2_req_enh2-UEConTest/TEI15_test |  |  | 1 | 100% | 100% |  | 100% | 100%
TBD | Y | 38.521-3
TS 38.521-4: SA/NSA FR2 Demod Perf test cases - necessary updates
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [7 empty] | TBD
TBD | Y | 38.521-4 | XYZ | n262 specific MU updates | n262 Demod MU updates |  | RAN5#101 (Nov-23) |  |  |  | FFS pending N262 MU discussions | 1 | 0% | 0% |  | 0% | 0%
TS 38.533: SA/NSA FR2 RRM test cases - necessary updates
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
TBD | Y | 38.533 | XYZ | n262 specific MU updates | n262 RRM MU updates |  | RAN5#101 (Nov-23) |  |  |  | FFS pending N262 MU discussions | 1 | 0% | 0% |  | 0% | 0%
TS 38.522: Applicability for RF FR2 test cases
TBD |  | 38.522 | 4,1,2 | FR2 standalone conformance test cases | Add test case applicability statements for the test cases introduced for 38.521-2. |  | RAN5#101 (Nov-23) |  |  |  | FFS pending N262 MU discussions | 0.1 | 0% | 0% |  | 0% | 0%
TR 38.903: Test Tolerances analysis RRM and RF test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [7 empty] | TBD
TBD |  | 38.903 | Annex B | Acceptable uncertainty of test system for test cases defined in TS 38.521-2 for radiative testing | TT analysis for FR2 RF Test cases |  | RAN5#101 (Nov-23) |  |  |  | FFS pending N262 MU discussions | 0.5 | 20% | 20% |  | 20% | 20%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [7 empty] | TBD
TBD |  | 38.905 | 4.2 | Test point analysis for FR2 test cases in TS 38.521-2 | TP analysis for FR2 RF Test cases |  | RAN5#101 (Nov-23) |  |  |  | FFS pending N262 MU discussions | 0.2 | 20% | 20% |  | 20% | 20%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note 1
| AP#96e.29 | RF | Study if all the UE tolerance factors affecting the UE output power in FR2 EVM test case (peakEIRP, MBR, MPR, T(MPR), polarisation mismatch) is expected to be constant over time (10 subframes) and the correlation between the factors
| AP#96e.30 | RF | Evaluate if TT is to be made dependent on margin of UE output power in the FR2 EVM test case.
NOTE 2: Analysis of near-field (i.e. Direct Near Field (DNF), Combined Far-Field/Direct Near Field (CFFDNF), and Combined Far-Field/Near Field (CFFNF)) methods is low priority in FR2 RF Enhanced Test Methods Work Plan. Need forANY NF method analysis whatsoever in the current work plan shall be revisited once n262 testability work is complete
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on M6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.