## WP scope
Work plan for introduction of EN-DC PC2 FR1 configurations into 3GPP UE conformance test specifications
| WP template: | WP NR CA PC2 FR1 v1.7.0
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed.
Workplan scope
| Workplan Name |  | NR CA PC2 13 ENDC band combinations | [6 empty] | <= Default workplan name is the filename. To change replace the formula with preferred text.
| Company (Contact) |  | WE Certification (Aleksi Heino) | [6 empty] | <= Enter Responsible Company and Contact for the configurations in the WP
| Target completion |  | RAN5#102 | [6 empty] | <= Enter target completion date here. Format RAN5#<xx>, where <xx> is the RAN5 meeting, e.g. RAN5#94-e>
| Comments |  | Interested operator AT&T and resp company WE Certfication already in draft 1.8.0
| Overall completion |  | 100%
Target configurations
Note: A work plan can include multiple target configurations but it is recommended to create separate work plans for Intra-band continuous, Intra-band Non-Continuous and Inter-band configurations. Copy target configuration(s) for the WP from the "PRD21 NR bands and 5G NR CADC list" as values in the table below by: 1. Select and copy the complete rows of the target configuration(s) in the "PRD21 NR bands and 5G NR CADC list". 2. Select cell A15 in the table below and right-click. 3. Select paste option "Paste as values" (see picture). It may take a few seconds before the pasted information is shown. 4. To include additional configurations, repeat steps 1 to 3, but in step 2 select the cell in column A next below the last configuration in the list.
Marked config | Release introduced in TS 38.101-x | Type of configuration | TS and Source Table | Configuration | Uplink configuration | PC3 Status | PC2 completed? | RAN5 Completion Meeting (PC3) | Completion Reference (PC3) | Interested operator (PC3) | Responsible Company (contact) (PC3) | Assignment [RAN5 meeting] (PC3) | Applicable RAN5 WI code(s) for CRs | Comments | Introduced in PRD version
| Rel-17 | EN-DC FR1 (2 bands) | 38.101-3:Table 5.5B.4.1-1 | DC_2A-2A_n77A | DC_2A_n77A PC2 | Ongoing | PC2 |  |  | AT&T |  | <RAN5#94-e | ENDC_UE_PC2_R17_NR_TDD-UEConTest | DC_002A_002A_n077A | DC_002A_n077A PC002 | v1.0.0
| Rel-17 | EN-DC FR1 (2 bands) | 38.101-3:Table 5.5B.4.1-1 | DC_12A_n77A | DC_12A_n77A PC2 | Ongoing | PC2 |  |  | AT&T,Rogers |  | RAN5#94-e | ENDC_UE_PC2_R17_NR_TDD-UEConTest | DC_012A_n077A | DC_012A_n077A PC002 | v1.0.0
| Rel-17 | EN-DC FR1 (2 bands) | 38.101-3:Table 5.5B.4.1-1 | DC_14A_n77A | DC_14A_n77A PC2 | Ongoing | PC2 |  |  | AT&T |  | <RAN5#94-e | ENDC_UE_PC2_R17_NR_TDD-UEConTest | DC_014A_n077A | DC_014A_n077A PC002 | v1.0.0
| Rel-17 | EN-DC FR1 (2 bands) | 38.101-3:Table 5.5B.4.1-1 | DC_30A_n77A | DC_30A_n77A PC2 | Ongoing | PC2 |  |  | AT&T |  | <RAN5#94-e | ENDC_UE_PC2_R17_NR_TDD-UEConTest | DC_030A_n077A | DC_030A_n077A PC002 | v1.0.0
| Rel-17 | EN-DC FR1 (2 bands) | 38.101-3:Table 5.5B.4.1-1 | DC_66A-66A_n77A | DC_66A_n77A PC2 | Ongoing | PC2 |  |  | AT&T |  | <RAN5#94-e | ENDC_UE_PC2_R17_NR_TDD-UEConTest | DC_066A_066A_n077A | DC_066A_n077A PC002 | v1.0.0
| Rel-18 | EN-DC FR1 (2 bands) | 38.101-3:Table 5.5B.4.1-1 | DC_2A_n77(2A) | DC_2A_n77A PC2 | Pending | PC2 | [5 empty] | HPUE_NR_CADC_NR_LTE_DC_R18-UEConTest |  |  | v1.6.0
| Rel-18 | EN-DC FR1 (2 bands) | 38.101-3:Table 5.5B.4.1-1 | DC_5A_n77(2A) | DC_5A_n77A PC2 | Pending | PC2 | [5 empty] | HPUE_NR_CADC_NR_LTE_DC_R18-UEConTest |  |  | v1.6.0
| Rel-18 | EN-DC FR1 (2 bands) | 38.101-3:Table 5.5B.4.1-1 | DC_12A_n77(2A) | DC_12A_n77A PC2 | Pending | PC2 | [5 empty] | HPUE_NR_CADC_NR_LTE_DC_R18-UEConTest |  |  | v1.6.0
| Rel-18 | EN-DC FR1 (2 bands) | 38.101-3:Table 5.5B.4.1-1 | DC_14A_n77(2A) | DC_14A_n77A PC2 | Pending | PC2 | [5 empty] | HPUE_NR_CADC_NR_LTE_DC_R18-UEConTest |  |  | v1.6.0
| Rel-18 | EN-DC FR1 (2 bands) | 38.101-3:Table 5.5B.4.1-1 | DC_30A_n77(2A) | DC_30A_n77A PC2 | Pending | PC2 | [5 empty] | HPUE_NR_CADC_NR_LTE_DC_R18-UEConTest |  |  | v1.6.0
| Rel-18 | EN-DC FR1 (2 bands) | 38.101-3:Table 5.5B.4.1-1 | DC_66A_n77(2A) | DC_66A_n77A PC2 | Pending | PC2 | [5 empty] | HPUE_NR_CADC_NR_LTE_DC_R18-UEConTest |  |  | v1.6.0
| Rel-18 | EN-DC FR1 (3 bands) | 38.101-3:Table 5.5B.4.2-1 | DC_2A-2A_n77(2A) | DC_2A_n77A PC2 | Pending | PC2 | [5 empty] | HPUE_NR_CADC_NR_LTE_DC_R18-UEConTest |  |  | v1.6.0
| Rel-18 | EN-DC FR1 (3 bands) | 38.101-3:Table 5.5B.4.2-1 | DC_66A-66A_n77(2A) | DC_66A_n77A PC2 | Pending | PC2 | [5 empty] | HPUE_NR_CADC_NR_LTE_DC_R18-UEConTest |  |  | v1.6.0

## WP NR CA PC2 FR1
Work plan for introduction of EN-DC PC2 FR1 configurations into 3GPP UE conformance test specifications
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed. | [13 empty] | WP template: WP NR CA PC2 FR1 v1.7.0
1. Configurations covered by the work plan
|  | Type of CA configurations |  |  |  | WP item Applicability Label | CA configurations [DL/UL]
|  | New EN-DC configuration(s) with UL DC |  |  |  | DL/UL BCS0 | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2
|  | New BCS for EN-DC configuration with UL CA |  |  |  | DL/UL new BCS
|  | All configurations |  |  |  | All | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2
|  | All BCS0 configurations (No BCS included in config.name) |  |  |  | All BCS0 | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2
|  | All new BCS configurations with BCS>0 |  |  |  | All new BCS
2. Overall status vs WP steps
[7 empty] | Overall Sub-WI |  | Handling of not applicable WP item rows: - WP item rows not applicable for the target configurations are indicated as being strikethrough text. You can hide those not applicable WP items by filtering on excluding "(Blanks)" in column "Impacted config(s)". - Some WP items may still not be applicable for the target configurations based on the applicability information in the "Task" column. To NOT include those WP items in the overall status calculations You need to clear the "Detailed Completion Status" cells for the WP item row and state "N/A" in the comments field. Note: It is not recomended to completly delete not applicable WP item rows in case additional target configurations added at a later stage may require those WP Item rows.
|  | Overall completeness |  |  |  |  | 100%
|  | Step 1: Work plan pre-requisite |  |  |  |  | 100%
|  | Step 2: Complete Test Point (TP) analysis for impacted EN-DC configurations |  |  |  |  | 100%
Step 3.1: CR(s) to common test environment (TS 38.508-1)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-3)
|  | Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-3, clause 6) |  |  |  |  | 100%
|  | Step 3.4: CR(s) for RF receiver test cases (TS 38.521-3, clause 7) |  |  |  |  | 100%
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
|  | Step 4: CR(s) for new ICS/capabilities (TS 38.508-2) |  |  |  |  | 100%
3. Details
Do not edit | [7 empty] | WP item columns to be filled in |  |  |  | Do not edit |  |  | WP item columns to be filled in
Step 1: Work plan pre-requisite
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted config(s) [DL/UL] | Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | 36.101-3 completed | PC3 completed
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
All | 1-1 | Pre-requisite | 38.101-3 | 6.2B.1.1 (intra-band contiguous EN-DC) 6.2B.1.2 (intra-band non-contiguous EN-DC) 6.2B.1.3 (inter-band EN-DC) | Core requirements completed | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | Set status in column "38.101-3 completed" to 100% when all impacted configurations have been confirmed completed in 38.101-3 clause 6.2B.1.1 (intra-band contiguous EN-DC), 6.2B.1.2 (intra-band non-contiguous EN-DC) and 6.2B.1.3 (inter-band EN-DC). |  | RAN5#102 |  |  | 1 | 100% |  | 100%
All | 1-1 | Pre-requisite | PRD21 | 5G NR CADC Configurations worksheet | Corresponding configuration completed for PC3 | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | Set status in column "PC3 completed" to 100% when all impacted item have been confirmed completed in RAN5 PRD21 worksheet "5G NR CADC Configurations worksheet". |  | RAN5#102 |  |  | 1 | 100% |  |  | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 2: Complete Test Point (TP) analysis for impacted EN-DC configurations
WP item applicability | WP item ID | Area | TR | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
TP analysis
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
All | 2-1 | TP Analysis | 38.905 | 4.3.2.1 | Test point (TP) analysis for A-MPR | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | For EN-DC PC2 intra-band contiguous and non-contiguos configurations: - Check is PC2 is part of exsisting TP analysis and update existing TP analysis for the NS value if needed. - Set the status column "TP analysis" to 100% when the required A-MPR TP analysis have been included in TR 38.905 clause 4.3.2.1. For EN-DC PC2 inter-band configurations: No changes needed as the test cases for EN-DC depending on the A-MPR TP analysis falls under the LTE agnostic approach (single carrier E-UTRA and NR applies). |  | RAN5#102 |  |  | 1 | 100% |  | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3: CRs to impacted TSs areas
Step 3.1: CR(s) to common test environment (TS 38.508-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
Test Freq.
1
| 3.1-1 | [5 empty] | No changes needed |  | RAN5#102 |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-3)
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Discussion paper | Clause 7
[15 empty] | 1 | 1
All | 3.2-2 | 38.521-3 - RF Tx | 38.521-3 | 7.3B.2.0.1 | Reference sensitivity for Intra-band contiguous EN-DC | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | Add PC2 Reference sensitivity exceptions for inter-band configurations within FR1 to the relevant table. |  | RAN5#102 |  |  | 1 | 100% |  |  | 100%
All | 3.2-3 | 38.521-3 - RF Tx | 38.521-3 | 7.3B.2.0.2 | Reference sensitivity for Intra-band non-contiguous EN-DC | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | Add PC2 Reference sensitivity exceptions for inter-band configurations within FR1 to the relevant table. |  | RAN5#102 |  |  | 1 | 100% |  |  | 100%
All | 3.2-4 | 38.521-3 - RF Tx | 38.521-3 | 7.3B.2.0.3 | Reference sensitivity for Inter-band contiguous EN-DC Note: The UL harmonics exception requirements apply to both PC2 and PC3 since the LTE aggressor is always PC3 | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | Add PC2 Reference sensitivity exceptions for inter-band configurations within FR1 to the relevant table. |  | RAN5#102 |  |  | 1 | 100% |  |  | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-3, clause 6)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
All | 3.3-1 | 38.521-3- RF Tx | 38.521-3 | 6.2B.1.1 | UE maximum output power for EN-DC Intra-band contiguos | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | For configurations including any PC2 EN-DC Intra-band contiguous add the UE maximum output power requirements to Table 6.2B.1.1.3-1 and the test requirements to relevant table(s) in clause 6.2B.1.1.5. |  | RAN5#102 | R5-240885 |  | 1 | 100% |  | 100% |  |  | 100%
All | 3.3-2 | 38.521-3- RF Tx | 38.521-3 | 6.2B.1.2 | UE maximum output power for EN-DC Intra-band non-contiguos | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | For configurations including any PC2 EN-DC Intra-band non-contiguous add the UE maximum output power requirements to Table 6.2B.1.2.3-1 and the test requirements to relevant table(s) in clause 6.2B.1.2.5. |  | RAN5#102 |  | N/A | 1 | 100% |  | 100% |  |  | 100%
All | 3.3-2 | 38.521-3- RF Tx | 38.521-3 | 6.2B.1.3, 6.2B.1.3_1 | UE maximum output power for EN-DC Inter-band | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | For EN-DC PC2 inter-band configurations with 1 E-UTRA CC, 1 NR CC: - Add the UE maximum output power requirements to Table 6.2B.1.3.3-1 ; and - Add test requirements to relevant table(s) in clause 6.2B.1.3.5. For EN-DC PC2 inter-band configurations with 2 E-UTRA CC, 1 NR CC: - Add the UE maximum output power requirements to Table 6.2B.1.3_1.3-1 ; and - Add test requirements to relevant table(s) in clause 6.2B.1.3_1.5. |  | RAN5#102 | R5-240885 |  | 1 | 100% |  | 100% |  |  | 100%
All | 3.4-1 | 38.521-3- RF Tx | 38.521-3 | 6.2B.3.1 | UE Additional Maximum Output Power reduction for Intra-band contiguous EN-DC Note! This WP item is dependent on A-MPR TP analysis (Step 2, WP item 2-1) | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | For EN-DC intra-band contiguous configurations with PC2 specific A-MPR requirements, add the minimum requirements , test comnfigurations and test requirements in clause 6.2B.3.1.x. |  | RAN5#102 |  | N/A | 1 | 100% |  | 100% |  | 100% | 100%
All | 3.4-2 | 38.521-3- RF Tx | 38.521-3 | 6.2B.3.2 | UE Additional Maximum Output Power reduction for Intra-Band Non-Contiguous EN-DC Note! This WP item is dependent on A-MPR TP analysis (Step 2, WP item 2-1) | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | For EN-DC intra-band contiguous configurations with PC2 specific A-MPR requirements, add the minimum requirements , test comnfigurations and test requirements in clause 6.2B.3.2.x. |  | RAN5#102 |  | N/A | 1 | 100% |  | 100% |  | 100% | 100%
All | 3.4-2 | 38.521-3- RF Tx | 38.521-3 | 6.2B.3.3 | UE Additional Maximum Output Power reduction for Inter-Band EN-DC within FR1 (1 NR CC) | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | No changes needed. LTE agnostic appoach applies. |  |  |  |  | 1
All | 3.5-1 | 38.521-3- RF Tx | 38.521-3 | 6.5B.4.1 | Additional Spurious Emissions for Intra-band contiguous EN-DC | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | No changes needed |  |  |  |  | 1
All | 3.5-2 | 38.521-3- RF Tx | 38.521-3 | 6.5B.4.2 | Additional Spurious Emissions for Intra-band non-contiguous EN-DC | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | No changes needed |  |  |  |  | 1
All | 3.5-2 | 38.521-3- RF Tx | 38.521-3 | 6.5B.4.3 | Additional Spurious Emissions for Inter-band EN-DC within FR1 (1 NR CC) | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | No changes needed. LTE agnostic appoach applies. |  |  |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-3, clause 7)
WP item applicability | 3.3 | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
All | 3.4-1 | 38.521-3-RF Rx | 38.521-3 | 7.3A.1_1 | Reference sensitivity power level for 2DL CA exceptions Note: The UL harmonics exception requirements apply to both PC2 and PC3 since the LTE aggressor is always PC3 | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | Add test requirements for any PC2 specific exceptional requirements for inter-band EN-DC configurations. |  | RAN5#102 |  | N/A | 1 | 100% |  |  |  |  | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
| 3.5-1 | [5 empty] | No changes needed |  | RAN5#102 |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
ICS / TC appli.
1
| 3.6-1 | [5 empty] | No changes needed |  | RAN5#102 |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
ICS / TC appli.
1
All | 4-1 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2B.2.1 | EN-DC Intra-band contiguous | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | Add PC2 RF Baseline Implementation Capabilities for Intra-band contiguous CA within FR1 to the relevant table in clause A.4.3.2B.2.1 |  | RAN5#102 |  |  | 1 | 100% |  | 100%
All | 4-2 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2B.2.2 | EN-DC Intra-band non-contiguous | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | Add PC2 iRF Baseline Implementation Capabilities for NR Intra-band non-contiguous CA within FR1 to the relevant table in clause A.4.3.2B.2.2 |  | RAN5#102 |  |  | 1 | 100% |  | 100%
All | 4-3 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2B.2.3 | EN-DC Inter-band | DC_2A-2A_n77A/DC_2A_n77A PC2, DC_12A_n77A/DC_12A_n77A PC2, DC_14A_n77A/DC_14A_n77A PC2, DC_30A_n77A/DC_30A_n77A PC2, DC_66A-66A_n77A/DC_66A_n77A PC2, DC_2A_n77(2A)/DC_2A_n77A PC2, DC_5A_n77(2A) /DC_5A_n77A PC2, DC_12A_n77(2A)/DC_12A_n77A PC2, DC_14A_n77(2A)/DC_14A_n77A PC2, DC_30A_n77(2A)/DC_30A_n77A PC2, DC_66A_n77(2A)/DC_66A_n77A PC2, DC_2A-2A_n77(2A)/DC_2A_n77A PC2, DC_66A-66A_n77(2A)/DC_66A_n77A PC2 | Add PC2 RF Baseline Implementation Capabilities for NR Inter-band CA within FR1 to the relevant table in clause A.4.3.2B.2.3 |  | RAN5#102 |  |  | 1 | 100% |  | 100%
End list sub-area WP items (insert any additional WP items for this area above this row)
Note on N29: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N37: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N45: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on N52: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N61: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N76: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N83: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N90: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N97: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.

## Revision History WP template
Revision history for WP template only Note! Cell A3 shall always include the version of the latest version of the WP as used to set the WP template version in the WP scope worksheet.
Version | Date | Comment
v1.7.0 | RAN5#101 | No changes. Same as v1.6.0.
v1.6.0 | RAN5#100 | No changes. Same as v1.5.0.
v1.5.0 | RAN5#99 | Initial version