## Cover sheet
RAN5 meeting #102 | [10 empty] | R5-240669
Athens, Greece, 26th Feb 2024 – 1st Mar 2024
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | Support of MPS Priority Indication
Work item code: | TEI16_Test
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 86% (+37%) | 5 (+5) | 6 (+3)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 79% (+79%) | 3 (+3) | 4 (+1)
FR1 |  | 79% (+79%) | 3 (+3) | 4 (+1)
FR2 |  | 79% (+79%) | 3 (+3) | 4 (+1)
LTE |  | 100% (+100%) | 2 (+2) | 2 (+2)
TDD |  | 100% (+100%) | 2 (+2) | 2 (+2)
FDD |  | 100% (+100%) | 2 (+2) | 2 (+2)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | TDD |  |  | FDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
LTE and CN protocols
Protocol test cases | 36.523-1 | 100% (+100%) | 2 (+2) | 2 (+2) | [7 empty] | 100% (+100%) | 2 (+2) | 2 (+2) | 100% (+100%) | 2 (+2) | 2 (+2)
Applicability Protocol test cases | 36.523-2 | 100% (+100%) | [9 empty] | 100% (+100%) |  |  | 100% (+100%)
Test suites (TTCN) | 36.523-3 | 100% (+100%) | [9 empty] | 100% (+100%) |  |  | 100% (+100%)
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 75% (+75%) | 3 (+3) | 4 (+1) | 75% (+75%) | 3 (+3) | 4 (+1) | 75% (+75%) | 3 (+3) | 4 (+1)
Applicability Protocol test cases | 38.523-2 | 75% (+75%) |  |  | 75% (+75%) |  |  | 75% (+75%)
Test suites (TTCN) | 38.523-3 | 90% (+90%) |  |  | 90% (+90%) |  |  | 90% (+90%)
5 References
[1] R5-233201 | Support of MPS Priority Indication
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance – Support of MPS Priority Indication | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | TEI16_Test
WP Scope: |  | <WP Scope description> | [13 empty] | vs Area
WP Resp: |  | Yogesh Tugnawat |  |  | Yogesht@qti.qualcomm.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | LTE |  | FR1 | FR2 | TDD | FDD
[15 empty] | 79% (+79%) | 79% (+79%) | 100% (+100%) | 100% (+100%)
[15 empty] | 10 (+4) | 10 (+4) | 5 (+1) | 5 (+1)
[15 empty] | 10 (+4) | 10 (+4) | 5 (+1) | 5 (+1)
0%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
RRC
2 | Y | 36.523-1 | 8.1.3.16 | RRC connection release / Redirection to another E-UTRAN frequency / MPS Priority Indication | (1) with { UE in E-UTRA RRC_CONNECTED state } ensure that { when { UE receives an RRCConnectionRelease message including IE mpsPriorityIndication-r16 and an IE redirectedCarrierInfo with eutra frequency different from UE was on in RRC_CONNECTED state} then { UE establishes an RRC connection with establishmentCause set to highPriorityAccess on the new frequency included in IE redirectedCarrierInfo } } |  | RAN5#101 (Nov-23) | R5-237314 | bcheruvu@qti.qualcomm.com | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
12 | Y | 36.523-1 | 8.1.3.17 | RRC connection release / Redirection to another E-UTRAN frequency / RRC connection establishment / 0% access probability for AC 0 to 11 and 15, AC 12 to 14 are not barred / MPS Priority Indication | with { UE in E-UTRA RRC_CONNECTED state } ensure that { when { UE receives an RRCConnectionRelease message including IE mpsPriorityIndication-r16 and an IE redirectedCarrierInfo with eutra frequency different from UE was on in RRC_CONNECTED state and and having received a SystemInformationBlockType2 indicating 0% access probability for AC 0..9, access restriction for AC 10, 15 and no restriction for AC 12..14 for both MO call and MO signalling } then { UE establishes an RRC connection with establishmentCause set to highPriorityAccess on the new frequency included in IE redirectedCarrierInfo } } |  | RAN5#102 (Feb-24) | R5-241475 | bcheruvu@qti.qualcomm.com | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
TS 36.523-2: Applicability for Protocol test cases
3 |  | 36.523-2 |  | Introduce PICS parameters and add test case applicability statements for the new test cases introduced in 36.523-1 for MPS Priority Indication | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  | RAN5#101 (Nov-23) | R5-236581, R5-240978 | bcheruvu@qti.qualcomm.com | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
16 |  | 36.523-2 |  | Introduce PICS parameters and add test case applicability statements for the new test cases introduced in 36.523-1 for MPS Priority Indication | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  | RAN5#102 (Feb-24) | R5-240978 | bcheruvu@qti.qualcomm.com | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
TS 36.523-3: Protocol test suites (TTCN)
4 |  | 36.523-3 |  | Introduction of General and Signaling Test Environment for MPS Priority Indication | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  | RAN5#102 (Feb-24) |  |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100% | 100%
5GS
5GS Common
TS 38.508-2: Common ICS
5 |  | 38.508-2 | A.4.4 | Introduction of General and Signaling Test Environment for MPS Priority Indication | Add ICS as needed for the test case applicability statements for the new test cases | Qualcomm | RAN5#99 (May-23) | R5-233320 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
TS 38.523-1: Protocol test cases
RRC
|  | 38.523-1 | 8.1 | NR RRC | [5 empty] | 0
|  | 38.523-1 | 8.1.1.3 | RRC release
6 | Y | 38.523-1 | 8.1.1.3.8 | RRC connection release / Redirection to another NR frequency / MPS Priority Indication | (1) with { UE in 5GMM-REGISTERED.NORMAL-SERVICE state and 5GMM-IDLE mode and User initiates an MMTEL call } ensure that { when { UE receives an RRCRelease message including mpsPriorityIndication-r16 and the IE redirectedCarrierInfo with nr and carrierFreq different from the frequency UE was on in RRC_CONNECTED state } then { UE establishes an RRC connection with establishmentCause set to mps-PriorityAccess on the new frequency included in IE redirectedCarrierInfo } } | Qualcomm | RAN5#100 (Aug-23) | R5-233777, R5-236622 | yogesht@qti.qualcomm.com | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
7 | Y | 38.523-1 | 8.1.1.3.10 | RRC connection release / Redirection from NR to E-UTRA / MPS Priority Indication | (1) with { UE in NR RRC_CONNECTED state } ensure that { when { UE receives an RRCRelease message including mpsPriorityIndication-r16 and the IE redirectionInformation with E-UTRA frequency } then { UE establishes an RRC connection with establishmentCause set to highPriorityAccess on the new frequency included in IE ) } | Qualcomm | RAN5#101 (Nov-23) | R5-237354 | yogesht@qti.qualcomm.com | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
8 | Y | 38.523-1 | 8.1.1.3.x | RRC connection release / Redirection to NR / From E_UTRA/ MPS Priority Indication | TS 38.331, clause 5.3.3.3 | Qualcomm | RAN5#103 (May-23) |  |  | 1 | 0% | 0% |  |  | 0% | 0%
Multi-layer and Services
|  | 38.523-1 | 11 | Multi-layer and Services
|  | 38.523-1 | 11.3 | Unified Access Control (UAC)
9 | Y | 38.523-1 | 11.3.11 | UAC / Access Identity 1/ 0% access probability / release with redirect with mpsPriorityIndication / RRC_INACTIVE | with { UE in NR RRC_INACTIVE state } ensure that { when { UE receives an RRCRelease message including mpsPriorityIndication-r16 and the IE redirectedCarrierInfo with nr and Access Identity 1 in the uac-BarringForAccessIdentity contained in the "UAC barring parameter" is set to zero in SIB1 of target cell } then { UE considers access attempt as allowed and resumes RRC connection with establishmentCause set to mps-PriorityAccess } } | Qualcomm | RAN5#100 (Aug-23) | R5-235090 | yogesht@qti.qualcomm.com | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
TS 38.523-2: Applicability for Protocol test cases
10 |  | 38.523-2 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.523-1 | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | Qualcomm | RAN5#100 (Aug-23) | R5-232685 | yogesht@qti.qualcomm.com | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
13 |  | 38.523-2 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.523-1 | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | Qualcomm | RAN5#101 (Nov-23) | R5-236588 | yogesht@qti.qualcomm.com | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
17 |  | 38.523-2 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.523-1 | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | Qualcomm | RAN5#100 (Aug-23) | R5-235091 | yogesht@qti.qualcomm.com | 1 | 100% (+100%) | 100% (+100%) |  |  | 100% | 100%
18 |  | 38.523-2 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.523-1 | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | Qualcomm | TBD |  |  | 1 | 0% | 0% |  |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
15 |  | 38.523-3 |  | Introduction of General and Signaling Test Environment for MPS Priority Indication | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  | RAN5#102 (Feb-24) |  |  | 1 | 90% (+90%) | 90% (+90%) |  |  | 90% | 90%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.