## Cover sheet
3GPP TSG-RAN5 Meeting #103 | [10 empty] | R5-242237
Fukuoka, Japan, 20 – 24 May, 2024
Agenda Item: | 7.5.2
Source: | CATT
Title: | Work plan: UE Conformance Test Aspects - NR Positioning Enhancement
Work item code: | NR_pos_enh-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to WID on NR positioning enhancements completed by RAN1, RAN2 and RAN4. This work item will cover signalling and RRM conformance test specifications aspects for NR positioning enhancements including the Applicability, Test Environment, Initial Conditions, Test Procedure, Message Exceptions, Test Setup, Connection Diagram, etc.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 56% (+18%) | 16 | 71
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 56.3% (+18.4%) | 16 | 71
FR1 |  | 56.3% (+18.4%) | 16 | 71
FR2 |  | 56.3% (+18.4%) | 16 | 71
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0% |  |  | 0%
NR RF/RRM
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 18.8% (+0%) |  |  | 18.8% (+0%) |  |  | 18.8% (+0%)
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1 | 70.1% (+33.1%) | 13 | 68 | 70.1% (+33.1%) | 13 | 68 | 70.1% (+33.1%) | 13 | 68
UE Positioning Protocol test cases | 37.571-2 | 100% | 3 | 3 | 100% | 3 | 3 | 100% | 3 | 3
Applicability and ICS UE Positioning test cases | 37.571-3 | 71% (+14.5%) |  |  | 71% (+14.5%) |  |  | 71% (+14.5%)
UE Positioning Test sutes (TTCN) | 37.571-4 | 0% |  |  | 0% |  |  | 0%
UE Positioning test scenarios and assistance data | 37.571-5 | 50% |  |  | 50% |  |  | 50%
5 References
[1] RP-222384 | UE Conformance Test Aspects for NR Positioning Enhancements
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - NR positioning enhancements | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_pos_enh-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for NR positioning enhancements | [12 empty] | vs Area
WP Resp: |  | Xiaoyang TIAN, CATT |  |  | tianxiaoyang@catt.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2 | FR1 + FR2
[14 empty] | 56.3% (+18.4%) | 56.3% (+18.4%)
[14 empty] | 160 | 160 | 0
[14 empty] | 119.9 | 119.9 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.6 | Introduction of information elements for Release-17 NR positioning enhancement | Introduction of information elements for Release-17 NR positioning enhancement |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
NR RF/RRM
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
2 |  | 38.903 | 9, Annex G | Introduction of NR positioning test cases information | Introduction of NR positioning test cases information |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
3 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement period FR1 test case 14.2.5 | Adding TT analysis for RSTD test case 14.2.5 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
4 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement period FR1 test case 14.2.6 | Adding TT analysis for RSTD test case 14.2.6 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
5 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement period FR1 test case 14.2.7 | Adding TT analysis for RSTD test case 14.2.7 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
6 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement period FR2 test case 14.2.8 | Adding TT analysis for RSTD test case 14.2.8 | CATT | TBD |  |  | 0.5 | 100% | 100% |  | 100% | 100%
7 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement period FR2 test case 14.2.9 | Adding TT analysis for RSTD test case 14.2.9 | CATT | TBD |  |  | 0.5 | 100% | 100% |  | 100% | 100%
8 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement period FR2 test case 14.2.10 | Adding TT analysis for RSTD test case 14.2.10 | CATT | TBD |  |  | 0.5 | 100% | 100% |  | 100% | 100%
9 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement accuracy FR1 test case 14.3.5 | Adding TT analysis for RSTD test case 14.3.5 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
10 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement accuracy FR1 test case 14.3.6 | Adding TT analysis for RSTD test case 14.3.6 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
11 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement accuracy FR2 test case 14.3.7 | Adding TT analysis for RSTD test case 14.3.7 | CATT | TBD |  |  | 0.5 | 100% | 100% |  | 100% | 100%
12 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement accuracy FR2 test case 14.3.8 | Adding TT analysis for RSTD test case 14.3.8 | CATT | TBD |  |  | 0.5 | 100% | 100% |  | 100% | 100%
13 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement period FR1 test case 14.4.1 | Adding TT analysis for RSTD test case 14.4.1 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
14 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement period FR1 test case 14.4.2 | Adding TT analysis for RSTD test case 14.4.2 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
15 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement period FR2 test case 14.4.3 | Adding TT analysis for RSTD test case 14.4.3 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
16 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement period FR2 test case 14.4.4 | Adding TT analysis for RSTD test case 14.4.4 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
17 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement accuracy FR1 test case 14.5.1 | Adding TT analysis for RSTD test case 14.5.1 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
18 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement accuracy FR1 test case 14.5.2 | Adding TT analysis for RSTD test case 14.5.2 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
19 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement accuracy FR2 test case 14.5.3 | Adding TT analysis for RSTD test case 14.5.3 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
20 |  | 38.903 |  | Addition test tolerance analysis for RSTD measurement accuracy FR2 test case 14.5.4 | Adding TT analysis for RSTD test case 14.5.4 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
21 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement period FR1 test case 15.2.5 | Adding TT analysis for UE Rx-Tx time difference test case 15.2.5 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
22 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement period FR1 test case 15.2.6 | Adding TT analysis for UE Rx-Tx time difference test case 15.2.6 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
23 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement period FR1 test case 15.2.7 | Adding TT analysis for UE Rx-Tx time difference test case 15.2.7 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
24 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement period FR2 test case 15.2.8 | Adding TT analysis for UE Rx-Tx time difference test case 15.2.8 | CATT | TBD | R5-241897 |  | 0.5 | 100% | 100% |  | 100% | 100%
25 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement period FR2 test case 15.2.9 | Adding TT analysis for UE Rx-Tx time difference test case 15.2.9 | CATT | TBD | R5-241900 |  | 0.5 | 100% | 100% |  | 100% | 100%
26 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement period FR2 test case 15.2.10 | Adding TT analysis for UE Rx-Tx time difference test case 15.2.10 | CATT | TBD | R5-241900 |  | 0.5 | 100% | 100% |  | 100% | 100%
27 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement accuracy FR1 test case 15.3.3 | Adding TT analysis for UE Rx-Tx time difference test case 15.3.3 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
28 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement accuracy FR1 test case 15.3.4 | Adding TT analysis for UE Rx-Tx time difference test case 15.3.4 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
29 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement accuracy FR2 test case 15.3.5 | Adding TT analysis for UE Rx-Tx time difference test case 15.3.5 | CATT | TBD |  |  | 0.5 | 100% | 100% |  | 100% | 100%
30 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement accuracy FR2 test case 15.3.6 | Adding TT analysis for UE Rx-Tx time difference test case 15.3.6 | CATT | TBD |  |  | 0.5 | 100% | 100% |  | 100% | 100%
31 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement period FR1 test case 15.4.1 | Adding TT analysis for UE Rx-Tx time difference test case 15.4.1 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
32 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement period FR1 test case 15.4.2 | Adding TT analysis for UE Rx-Tx time difference test case 15.4.2 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
33 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement period FR1 test case 15.4.3 | Adding TT analysis for UE Rx-Tx time difference test case 15.4.3 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
34 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement period FR2 test case 15.4.4 | Adding TT analysis for UE Rx-Tx time difference test case 15.4.4 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
35 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement accuracy FR1 test case 15.5.1 | Adding TT analysis for UE Rx-Tx time difference test case 15.5.1 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
36 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement accuracy FR1 test case 15.5.2 | Adding TT analysis for UE Rx-Tx time difference test case 15.5.2 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
37 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement accuracy FR1 test case 15.5.3 | Adding TT analysis for UE Rx-Tx time difference test case 15.5.3 | Nokia | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
38 |  | 38.903 |  | Addition test tolerance analysis for UE Rx-Tx time difference measurement accuracy FR2 test case 15.5.4 | Adding TT analysis for UE Rx-Tx time difference test case 15.5.4 | Nokia | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
39 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRP measurement period FR1 test case 16.2.5 | Adding TT analysis for PRS-RSRP test case 16.2.5 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
40 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRP measurement period FR1 test case 16.2.6 | Adding TT analysis for PRS-RSRP test case 16.2.6 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
41 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRP measurement period FR2 test case 16.2.7 | Adding TT analysis for PRS-RSRP test case 16.2.7 | CATT | TBD | R5-240131 |  | 0.5 | 100% | 100% |  | 100% | 100%
42 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRP measurement period FR2 test case 16.2.8 | Adding TT analysis for PRS-RSRP test case 16.2.8 | CATT | TBD | R5-240132 |  | 0.5 | 100% | 100% |  | 100% | 100%
43 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRP measurement accuracy FR1 test case 16.3.3 | Adding TT analysis for PRS-RSRP test case 16.3.3 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
44 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRP measurement accuracy FR2 test case 16.3.4 | Adding TT analysis for PRS-RSRP test case 16.3.4 | CATT | TBD | R5-240133 |  | 0.5 | 100% | 100% |  | 100% | 100%
45 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRP measurement period FR1 test case 16.4.1 | Adding TT analysis for PRS-RSRP test case 16.4.1 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
46 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRP measurement period FR1 test case 16.4.2 | Adding TT analysis for PRS-RSRP test case 16.4.2 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
47 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRP measurement period FR2 test case 16.4.3 | Adding TT analysis for PRS-RSRP test case 16.4.3 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
48 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRP measurement period FR2 test case 16.4.4 | Adding TT analysis for PRS-RSRP test case 16.4.4 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
49 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRP measurement accuracy FR1 test case 16.5.1 | Adding TT analysis for PRS-RSRP test case 16.5.1 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
50 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRP measurement accuracy FR1 test case 16.5.2 | Adding TT analysis for PRS-RSRP test case 16.5.2 | Rohde & Schwarz | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
51 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRP measurement accuracy FR2 test case 16.5.3 | Adding TT analysis for PRS-RSRP test case 16.5.3 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
52 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRP measurement accuracy FR2 test case 16.5.4 | Adding TT analysis for PRS-RSRP test case 16.5.4 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
53 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement period FR1 test case 17.2.1 | Adding TT analysis for PRS-RSRPP test case 17.2.1 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
54 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement period FR1 test case 17.2.2 | Adding TT analysis for PRS-RSRPP test case 17.2.2 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
55 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement period FR1 test case 17.2.3 | Adding TT analysis for PRS-RSRPP test case 17.2.3 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
56 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement period FR2 test case 17.2.4 | Adding TT analysis for PRS-RSRPP test case 17.2.4 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
57 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement accuracy FR2 test case 17.2.5 | Adding TT analysis for PRS-RSRPP test case 17.2.5 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
58 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement accuracy FR2 test case 17.2.6 | Adding TT analysis for PRS-RSRPP test case 17.2.6 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
59 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement accuracy FR1 test case 17.3.1 | Adding TT analysis for PRS-RSRPP test case 17.3.1 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
60 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement accuracy FR1 test case 17.3.2 | Adding TT analysis for PRS-RSRPP test case 17.3.2 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
61 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement accuracy FR2 test case 17.3.3 | Adding TT analysis for PRS-RSRPP test case 17.3.3 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
62 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement accuracy FR2 test case 17.3.4 | Adding TT analysis for PRS-RSRPP test case 17.3.4 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
63 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement period FR1 test case 17.4.1 | Adding TT analysis for PRS-RSRPP test case 17.4.1 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
64 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement period FR1 test case 17.4.2 | Adding TT analysis for PRS-RSRPP test case 17.4.2 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
65 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement period FR2 test case 17.4.3 | Adding TT analysis for PRS-RSRPP test case 17.4.3 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
66 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement period FR2 test case 17.4.4 | Adding TT analysis for PRS-RSRPP test case 17.4.4 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
67 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement accuracy FR1 test case 17.5.1 | Adding TT analysis for PRS-RSRPP test case 17.5.1 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
68 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement accuracy FR1 test case 17.5.2 | Adding TT analysis for PRS-RSRPP test case 17.5.2 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
69 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement accuracy FR2 test case 17.5.3 | Adding TT analysis for PRS-RSRPP test case 17.5.3 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
70 |  | 38.903 |  | Addition test tolerance analysis for PRS-RSRPP measurement accuracy FR2 test case 17.5.4 | Adding TT analysis for PRS-RSRPP test case 17.5.4 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
UE Positioning
TS 37.571-1: UE Positioning -Performance
|  | 37.571-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
71 |  | 37.571-1 | 2, 3 | Introduction of BDS B2a and B3I signal test contents | Adding reference of B2a and B3I ICD files and symbol of B2a and B3I | CATT | TBD | R5-231799 |  | 0.2 | 100% | 100% |  | 100% | 100%
72 |  | 37.571-1 | 4 | 1. Introduction of BDS B2a and B3I signal test conditions 2. Update the test conditions based on the Rel-17 RAN4 specification | 1. Adding BDS B2a and B3I parameters in GNSS multi-path conditions 2. Adding BDS B2a and B3I into multiple satellite signals supported by UE | CATT | TBD | R5-231799, R5-240120 |  | 0.2 | 100% | 100% |  | 100% | 100%
73 |  | 37.571-1 | 7 | Introduction of BDS B2a and B3I minimum performance requirements in E-UTRA | Adding note for B2a and B3I in E-UTRA A-GNSS minimum performance requirements | CATT | TBD | R5-231799 |  | 0.2 | 100% | 100% |  | 100% | 100%
74 |  | 37.571-1 | 13 | Introduction of BDS B2a and B3I minimum performance requirements in NR | Adding note for B2a and B3I in NR A-GNSS minimum performance requirements | CATT | TBD | R5-231799 |  | 0.2 | 100% | 100% |  | 100% | 100%
|  | 37.571-1 | 14 | NR RSTD measurement requirements
|  | 37.571-1 | 14.2 | NR RSTD measurement period test cases in RRC_CONNECTED
75 | Y | 37.571-1 | 14.2.5 | NR RSTD measurement reporting delay test case for single positioning frequency layer with reduced number of samples in FR1 SA | The purpose of the test is to verify that the RSTD measurement with the reduced samples meets the requirements specified in Clause 9.9.2 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.2.5 | Rohde & Schwarz | TBD | R5-242959 |  | 1 | 67.5% (+67.5%) | 67.5% (+67.5%) |  | 65% | 70%
76 | Y | 37.571-1 | 14.2.6 | NR RSTD measurement reporting delay test case for single positioning frequency layer without measurement gap in FR1 SA | The purpose of the test is to verify that the RSTD measurement meets the gapless RSTD measurement period requirement specified in Clause 9.9.2.7 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.2.7 | Rohde & Schwarz | TBD | R5-242123 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
77 | Y | 37.571-1 | 14.2.7 | NR RSTD measurement reporting delay test case for single positioning frequency layer with Rx TEG in FR1 SA | The purpose of the test is to verify that the RSTD measurement meets the Rx TEG based measurement period requirements specified in Clause 9.9.2.5 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.2.5 | Rohde & Schwarz | TBD | R5-242960 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
78 | Y | 37.571-1 | 14.2.8 | NR RSTD measurement reporting delay test case for single positioning frequency layer with reduced number of samples in FR2 SA | The purpose of the test is to verify that the RSTD measurement with the reduced samples meets the requirements specified in Clause 9.9.2 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.2.5 | CATT | TBD | R5-234205 |  | 1 | 100% | 100% |  | 100% | 100%
79 | Y | 37.571-1 | 14.2.9 | NR RSTD measurement reporting delay test case for single positioning frequency layer without measurement gap in FR2 SA | The purpose of the test is to verify that the RSTD measurement meets the gapless RSTD measurement period requirement specified in Clause 9.9.2.7 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.2.7 | CATT | TBD | R5-234206 |  | 1 | 100% | 100% |  | 100% | 100%
80 | Y | 37.571-1 | 14.2.10 | NR RSTD measurement reporting delay test case for single positioning frequency layer with Rx TEG in FR2 SA | The purpose of the test is to verify that the RSTD measurement meets the Rx TEG based measurement period requirements specified in Clause 9.9.2.5 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.2.5 | CATT | TBD | R5-234207 |  | 1 | 100% | 100% |  | 100% | 100%
|  | 37.571-1 | 14.3 | NR RSTD measurement accuracy test case in RRC_CONNECTED
81 | Y | 37.571-1 | 14.3.5 | NR RSTD measurement accuracy test case for single positioning frequency layer with reduced number of samples in FR1 SA | The purpose of the test is to verify that the RSTD measurement meets the accuracy requirements for reduced number of samples specified in clause 10.1.23.2 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.23.2 | Rohde & Schwarz | TBD | R5-242961 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
82 | Y | 37.571-1 | 14.3.6 | NR RSTD measurement accuracy test case for single positioning frequency layer with Rx TEG in FR1 SA | The purpose of the test is to verify that the RSTD measurement when the measurements of reference cell and neighbor cell are within the same Rx TEG meets the accuracy requirements specified in clause 10.1.23.2 in an environment with AWGN propagation conditions. TS 38.133 10.1.23.2 | Rohde & Schwarz | TBD | R5-242962 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
83 | Y | 37.571-1 | 14.3.7 | NR RSTD measurement accuracy test case for single positioning frequency layer with reduced number of samples in FR2 SA | The purpose of the test is to verify that the RSTD measurement meets the accuracy requirements for reduced number of samples specified in clause 10.1.23.2 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.23.2 | CATT | TBD | R5-234208 |  | 1 | 100% | 100% |  | 100% | 100%
84 | Y | 37.571-1 | 14.3.8 | NR RSTD measurement accuracy test case for single positioning frequency layer with Rx TEG in FR2 SA | The purpose of the test is to verify that the RSTD measurement when the measurements of reference cell and neighbor cell are within the same Rx TEG meets the accuracy requirements specified in clause 10.1.23.2 in an environment with AWGN propagation conditions. TS 38.133 10.1.23.2 | CATT | TBD | R5-234209 |  | 1 | 100% | 100% |  | 100% | 100%
|  | 37.571-1 | 14.4 | NR RSTD measurement period test cases in RRC_INACTIVE
85 | Y | 37.571-1 | 14.4.1 | NR RSTD measurement reporting delay test case for single positioning frequency layer in FR1 SA | The purpose of the test is to verify that the RSTD measurement meets the requirements specified in Clause 5.6.2.5 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 5.6.2.5 | Rohde & Schwarz | TBD | R5-242963 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
86 | Y | 37.571-1 | 14.4.2 | NR RSTD measurement reporting delay test case for single positioning frequency layer with reduced number of samples in FR1 SA | The purpose of the test is to verify that the RSTD measurement with the reduced samples meets the requirements specified in Clause 5.6.2 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 5.6.2.5 | Rohde & Schwarz | TBD | R5-242964 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
87 | Y | 37.571-1 | 14.4.3 | NR RSTD measurement reporting delay test case for single positioning frequency layer in FR2 SA | The purpose of the test is to verify that the RSTD measurement meets the requirements specified in Clause 5.6.2.5 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 5.6.2.5 | CATT | TBD | R5-240108 |  | 1 | 65% | 65% |  | 65% | 65%
88 | Y | 37.571-1 | 14.4.4 | NR RSTD measurement reporting delay test case for single positioning frequency layer with reduced number of samples in FR2 SA | The purpose of the test is to verify that the RSTD measurement with the reduced samples meets the requirements specified in Clause 5.6.2 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 5.6.2.5 | CATT | TBD | R5-240109 |  | 1 | 65% | 65% |  | 65% | 65%
|  | 37.571-1 | 14.5 | NR RSTD measurement accuracy test case in RRC_INACTIVE
89 | Y | 37.571-1 | 14.5.1 | NR RSTD measurement accuracy test case for single positioning frequency layer in FR1 SA | The purpose of the test is to verify that the RSTD measurement meets the accuracy requirements specified in clause 10.1.23.2 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.23.2 | Rohde & Schwarz | TBD | R5-242965 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
90 | Y | 37.571-1 | 14.5.2 | NR RSTD measurement accuracy test case for single positioning frequency layer with reduced number of samples in FR1 SA | The purpose of the test is to verify that the RSTD measurement meets the accuracy requirements for reduced number of samples specified in clause 10.1.23.2 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.23.2 | Rohde & Schwarz | TBD | R5-242966 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
91 | Y | 37.571-1 | 14.5.3 | NR RSTD measurement accuracy test case for single positioning frequency layer in FR2 SA | The purpose of the test is to verify that the RSTD measurement meets the accuracy requirements specified in clause 10.1.23.2 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.23.2 | CATT | TBD | R5-240110 |  | 1 | 65% | 65% |  | 65% | 65%
92 | Y | 37.571-1 | 14.5.4 | NR RSTD measurement accuracy test case for single positioning frequency layer with reduced number of samples in FR2 SA | The purpose of the test is to verify that the RSTD measurement meets the accuracy requirements for reduced number of samples specified in clause 10.1.23.2 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.23.2 | CATT | TBD | R5-241911 |  | 1 | 65% | 65% |  | 65% | 65%
|  | 37.571-1 | 15 | NR Rx-Tx Time Difference measurement requirements
93 |  | 37.571-1 | 15.2 | UE Rx-Tx time difference measurement period test cases in RRC_CONNECTED
94 | Y | 37.571-1 | 15.2.5 | UE Rx-Tx time difference measurement reporting delay test case for single positioning frequency layer with reduced number of samples in FR1 SA | The purpose of the test is to verify that the UE Rx-Tx time difference measurement with the reduced samples meets the requirements specified in Clause 9.9.4.5 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.4.5 | Rohde & Schwarz | TBD | R5-242967 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
95 | Y | 37.571-1 | 15.2.6 | UE Rx-Tx time difference measurement reporting delay test case for single positioning frequency layer without measurement gap in FR1 SA | The purpose of the test is to verify that the UE Rx-Tx time difference measurement measurement meets the gapless measurement period requirement specified in Clause 9.9.4.6 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.4.6 | Rohde & Schwarz | TBD | R5-242968 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
96 | Y | 37.571-1 | 15.2.7 | UE Rx-Tx time difference measurement reporting delay test case for single positioning frequency layer with multiple RxTx TEGs in FR1 SA | The purpose of the test is to verify that the UE Rx-Tx time difference measurement meets the RxTx TEG based measurement period requirements specified in Clause 9.9.4.5 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.4.5 | Rohde & Schwarz | TBD | R5-242969 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
97 | Y | 37.571-1 | 15.2.8 | UE Rx-Tx time difference measurement reporting delay test case for single positioning frequency layer with reduced number of samples in FR2 SA | The purpose of the test is to verify that the UE Rx-Tx time difference measurement with the reduced samples meets the requirements specified in Clause 9.9.4.5 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.4.5 | CATT | TBD | R5-2342101，R5-241897 |  | 1 | 100% | 100% |  | 100% | 100%
98 | Y | 37.571-1 | 15.2.9 | UE Rx-Tx time difference measurement reporting delay test case for single positioning frequency layer without measurement gap in FR2 SA | The purpose of the test is to verify that the UE Rx-Tx time difference measurement measurement meets the gapless measurement period requirement specified in Clause 9.9.4.6 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.4.6 | CATT | TBD | R5-234211， R5-241898 |  | 1 | 100% | 100% |  | 100% | 100%
99 | Y | 37.571-1 | 15.2.10 | UE Rx-Tx time difference measurement reporting delay test case for single positioning frequency layer with RxTx TEG in FR2 SA | The purpose of the test is to verify that the UE Rx-Tx time difference measurement meets the RxTx TEG based measurement period requirements specified in Clause 9.9.4.5 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.4.5 | CATT | TBD | R5-234212， R5-240103 |  | 1 | 100% | 100% |  | 100% | 100%
|  | 37.571-1 | 15.3 | UE Rx-Tx time difference measurement accuracy test cases in RRC_CONNECTED
100 | Y | 37.571-1 | 15.3.3 | UE Rx-Tx time difference measurement accuracy for single positioning frequency layer with reduced number of samples in FR1 SA | The purpose of the test is to verify that the UE Rx-Tx time difference measurement accuracy with reduced number of samples is within the specified limits.The test is conducted in AWGN propagation condition in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.25.2. | Rohde & Schwarz | TBD | R5-242970 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
101 | Y | 37.571-1 | 15.3.4 | UE Rx-Tx time difference measurement accuracy for single positioning frequency layer with RxTx TEG in FR1 SA | The purpose of the test is to verify that the relative UE Rx-Tx time difference measurement accuracy when the two measurements are within the same RxTx TEG is within the specified limits. This test will verify the requirements in clause 10.1.25.2. The test is conducted in AWGN propagation condition in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.25.2. | Rohde & Schwarz | TBD | R5-242971 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
102 | Y | 37.571-1 | 15.3.5 | UE Rx-Tx time difference measurement accuracy for single positioning frequency layer with reduced number of samples in FR2 SA | The purpose of the test is to verify that the UE Rx-Tx time difference measurement accuracy with reduced number of samples is within the specified limits. The test is conducted in AWGN propagation condition in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.25.2. | CATT | TBD | R5-234213 |  | 1 | 100% | 100% |  | 100% | 100%
103 | Y | 37.571-1 | 15.3.6 | UE Rx-Tx time difference measurement accuracy for single positioning frequency layer with RxTx TEG in FR2 SA | The purpose of the test is to verify that the relative UE Rx-Tx time difference measurement accuracy when the two measurements are within the same RxTx TEG is within the specified limits. This test will verify the requirements in clause 10.1.25.2. The test is conducted in AWGN propagation condition in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.25.2. | CATT | TBD | R5-234214 |  | 1 | 100% | 100% |  | 100% | 100%
|  | 37.571-1 | 15.4 | UE Rx-Tx time difference measurement period test cases in RRC_INACTIVE
104 | Y | 37.571-1 | 15.4.1 | UE Rx-Tx time difference measurement reporting delay test case for single positioning frequency layer in FR1 SA | The purpose of the test is to verify that the UE Rx-Tx measurement in RRC_INACTIVE state meets the requirements specified in clause 5.6.4 in AWGN propagation condition in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 5.6.4 | CATT | TBD | R5-242471 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
105 | Y | 37.571-1 | 15.4.2 | UE Rx-Tx time difference measurement reporting delay test case for single positioning frequency layer with reduced number of samples in FR1 SA | The purpose of the test is to verify that the UE Rx-Tx time difference measurement with the reduced samples meets the requirements specified in Clause 5.6.4 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 5.6.4.5 | CATT | TBD | R5-242472 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
106 | Y | 37.571-1 | 15.4.3 | UE Rx-Tx time difference measurement reporting delay test case for single positioning frequency layer in FR2 SA | The purpose of the test is to verify that the UE Rx-Tx measurement in RRC_INACTIVE state meets the requirements specified in clause 5.6.4 in AWGN propagation condition in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 5.6.4 | CATT | TBD | R5-242473 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
107 | Y | 37.571-1 | 15.4.4 | UE Rx-Tx time difference measurement reporting delay test case for single positioning frequency layer with reduced number of samples in FR2 SA | The purpose of the test is to verify that the UE Rx-Tx time difference measurement with the reduced samples meets the requirements specified in Clause 5.6.4 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 5.6.4.5 | CATT | TBD | R5-242474 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
|  | 37.571-1 | 15.5 | UE Rx-Tx time difference measurement accuracy test cases in RRC_INACTIVE
108 | Y | 37.571-1 | 15.5.1 | UE Rx-Tx time difference measurement accuracy for single positioning frequency layer in FR1 SA | The purpose of the test is to verify that the UE Rx-Tx time difference measurement accuracy is within the specified limits. This test will verify the requirements in clause 10.1.25.2. The test is conducted in AWGN propagation condition in FR1 in standalone scenario. TS 38.133 10.1.25.2 | Rohde & Schwarz | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
109 | Y | 37.571-1 | 15.5.2 | UE Rx-Tx time difference measurement accuracy for single positioning frequency layer with reduced number of samples in FR1 SA | The purpose of the test is to verify that the UE Rx-Tx time difference measurement accuracy with reduced number of samples in RRC_INACTIVE state is within the specified limits. This test will verify the requirements in clause 10.1.25.2. The test is conducted in AWGN propagation condition in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.25.2 | Rohde & Schwarz | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
110 | Y | 37.571-1 | 15.5.3 | UE Rx-Tx time difference measurement accuracy for single positioning frequency layer in FR2 SA | The purpose of the test is to verify that the UE Rx-Tx time difference measurement accuracy is within the specified limits. This test will verify the requirements in clause 10.1.25.2. The test is conducted in AWGN propagation condition in FR2 in standalone scenario. TS 38.133 10.1.25.2 | Nokia | TBD | R5-242613 |  | 1 | 62.5% (+62.5%) | 62.5% (+62.5%) |  | 65% | 60%
111 | Y | 37.571-1 | 15.5.4 | UE Rx-Tx time difference measurement accuracy for single positioning frequency layer with reduced number of samples in FR2 SA | The purpose of the test is to verify that the UE Rx-Tx time difference measurement accuracy with reduced number of samples in RRC_INACTIVE state is within the specified limits. This test will verify the requirements in clause 10.1.25.2. The test is conducted in AWGN propagation condition in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.25.2 | Nokia | TBD | R5-242614 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
|  | 37.571-1 | 16.2 | NR PRS-RSRP measurement period test cases in RRC_CONNECTED
112 | Y | 37.571-1 | 16.2.5 | PRS-RSRP measurement reporting delay test case for single positioning frequency with reduced number of samples in FR1 SA | The purpose of the test is to verify that the PRS-RSRP measurement meets the delay requirements for reduced number of samples specified in clause 9.9.3.5 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.3.5 | Rohde & Schwarz | TBD | R5-242972 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
113 | Y | 37.571-1 | 16.2.6 | PRS-RSRP measurement reporting delay test case for single positioning frequency layer without measurement gap in FR1 SA | The purpose of the test is to verify that the PRS-RSRP measurement measurement meets the gapless measurement period requirement specified in Clause 9.9.3.6 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.3.6 | Rohde & Schwarz | TBD | R5-242972 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
114 | Y | 37.571-1 | 16.2.7 | PRS-RSRP measurement reporting delay test case for single positioning frequency with reduced number of samples in FR2 SA | The purpose of the test is to verify that the PRS-RSRP measurement meets the delay requirements for reduced number of samples specified in clause 9.9.3.5 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.3.5 | CATT | TBD | R5-240104 |  | 1 | 100% | 100% |  | 100% | 100%
115 | Y | 37.571-1 | 16.2.8 | PRS-RSRP measurement reporting delay test case for single positioning frequency layer without measurement gap in FR2 SA | The purpose of the test is to verify that the PRS-RSRP measurement measurement meets the gapless measurement period requirement specified in Clause 9.9.3.6 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.3.6 | CATT | TBD | R5-240105 |  | 1 | 100% | 100% |  | 100% | 100%
|  | 37.571-1 | 16.3 | NR PRS-RSRP measurement accuracy test case in RRC_CONNECTED
116 | Y | 37.571-1 | 16.3.3 | PRS-RSRP measurement accuracy with PRS in FR1 with reduced sample number | The purpose of the test is to verify that the PRS-RSRP measurement accuracy with reduced number of samples is within the specified limits.The test is conducted in AWGN propagation condition in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.24.2. | Rohde & Schwarz | TBD | R5-242974 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
117 | Y | 37.571-1 | 16.3.4 | PRS-RSRP measurement accuracy with PRS in FR2 with reduced sample number | The purpose of the test is to verify that the PRS-RSRP measurement accuracy with reduced number of samples is within the specified limits.The test is conducted in AWGN propagation condition in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.24.2. | CATT | TBD | R5-241899 |  | 1 | 100% | 100% |  | 100% | 100%
|  | 37.571-1 | 16.4 | NR PRS-RSRP measurement period test cases in RRC_INACTIVE
118 | Y | 37.571-1 | 16.4.1 | PRS-RSRP measurement reporting delay test case for single positioning frequency layer in FR1 SA | The purpose of the test is to verify that the PRS-RSRP measurement in RRC_INACTIVE meets the delay requirements specified in clause 5.6.3.5 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 5.6.3.5 | Rohde & Schwarz | TBD | R5-242975 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
119 | Y | 37.571-1 | 16.4.2 | PRS-RSRP measurement reporting delay test case for single positioning frequency layer with reduced number of samples in FR1 SA | The purpose of the test is to verify that the PRS-RSRP measurement with the reduced samples meets the requirements specified in Clause 5.6.3 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 5.6.3.5 | Rohde & Schwarz | TBD | R5-242976 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
120 | Y | 37.571-1 | 16.4.3 | PRS-RSRP measurement reporting delay test case for single positioning frequency layer in FR2 SA | The purpose of the test is to verify that the PRS-RSRP measurement in RRC_INACTIVE meets the delay requirements specified in clause 5.6.3.5 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 5.6.3.5 | CATT | TBD | R5-240112 |  | 1 | 65% | 65% |  | 65% | 65%
121 | Y | 37.571-1 | 16.4.4 | PRS-RSRP measurement reporting delay test case for single positioning frequency layer with reduced number of samples in FR2 SA | The purpose of the test is to verify that the PRS-RSRP measurement with the reduced samples meets the requirements specified in Clause 5.6.3 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 5.6.3.5 | CATT | TBD | R5-240113 |  | 1 | 65% | 65% |  | 65% | 65%
|  | 37.571-1 | 16.5 | NR PRS-RSRP measurement accuracy test case in RRC_INACTIVE
122 | Y | 37.571-1 | 16.5.1 | PRS-RSRP measurement accuracy test case for single positioning frequency layer with PRS in FR1 SA | The purpose of the test is to verify that the PRS-RSRP measurement accuracy is within the specified limits. This test will verify the requirements in clause 10.1.24.2. The test is conducted in AWGN propagation condition in FR1 in standalone scenario. TS 38.133 10.1.24.2 | Rohde & Schwarz | TBD | R5-242977 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
123 | Y | 37.571-1 | 16.5.2 | PRS-RSRP measurement accuracy test case for single positioning frequency layer with PRS in FR1 with reduced sample number | The purpose of the test is to verify that the PRS-RSRP measurement accuracy with reduced number of samples in RRC_INACTIVE state is within the specified limits. This test will verify the requirements in clause 10.1.24.2. The test is conducted in AWGN propagation condition in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.24.2 | Rohde & Schwarz | TBD | R5-242978 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
124 | Y | 37.571-1 | 16.5.3 | PRS-RSRP measurement accuracy test case for single positioning frequency layer with PRS in FR2 SA | The purpose of the test is to verify that the PRS-RSRP measurement accuracy is within the specified limits. This test will verify the requirements in clause 10.1.24.2. The test is conducted in AWGN propagation condition in FR2 in standalone scenario. TS 38.133 10.1.24.2 | CATT | TBD | R5-240114 |  | 1 | 65% | 65% |  | 65% | 65%
125 | Y | 37.571-1 | 16.5.4 | PRS-RSRP measurement accuracy test case for single positioning frequency layer with PRS in FR2 with reduced sample number | The purpose of the test is to verify that the PRS-RSRP measurement accuracy with reduced number of samples in RRC_INACTIVE state is within the specified limits. This test will verify the requirements in clause 10.1.24.2. The test is conducted in AWGN propagation condition in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.24.2 | CATT | TBD | R5-240115 |  | 1 | 65% | 65% |  | 65% | 65%
|  | 37.571-1 | 17 | NR PRS-RSRPP measurement requirements
|  | 37.571-1 | 17.2 | NR PRS-RSRPP measurement period test cases in RRC_CONNECTED
126 | Y | 37.571-1 | 17.2.1 | PRS-RSRPP measurement reporting delay test case for single positioning frequency layer in FR1 SA | The purpose of the test is to verify that the PRS-RSRPP measurement meets the delay requirements specified in clause 9.9.6.5 in an environment with AWGN propagation conditions in FR1 in standalone scenario. TS 38.133 9.9.6.5 | CATT | TBD | R5-242474 |  | 1 | 65% | 65% |  | 65% | 65%
127 | Y | 37.571-1 | 17.2.2 | PRS-RSRPP measurement reporting delay test case for single positioning frequency layer with reduced number of samples in FR1 SA | The purpose of the test is to verify that the PRS-RSRPP measurement meets the delay requirements for reduced number of samples specified in clause 9.9.6.5 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.6.5 | CATT | TBD |  |  | 1 | 65% | 65% |  | 65% | 65%
128 | Y | 37.571-1 | 17.2.3 | PRS-RSRPP measurement reporting delay test case for single positioning frequency layer without measurement gap in FR1 SA | The purpose of the test is to verify that the PRS-RSRPP measurement measurement meets the gapless measurement period requirement specified in Clause 9.9.6.6 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.6.6 | CATT | TBD |  |  | 1 | 65% | 65% |  | 65% | 65%
129 | Y | 37.571-1 | 17.2.4 | PRS-RSRPP measurement reporting delay test case for single positioning frequency layer in FR2 SA | The purpose of the test is to verify that the PRS-RSRPP measurement meets the delay requirements specified in clause 9.9.6.5 in an environment with AWGN propagation conditions in FR2 in standalone scenario. TS 38.133 9.9.6.5 | CATT | TBD |  |  | 1 | 65% | 65% |  | 65% | 65%
130 | Y | 37.571-1 | 17.2.5 | PRS-RSRPP measurement reporting delay test case for single positioning frequency layer with reduced number of samples in FR2 SA | The purpose of the test is to verify that the PRS-RSRPP measurement meets the delay requirements for reduced number of samples specified in clause 9.9.6.5 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.6.5 | CATT | TBD |  |  | 1 | 65% | 65% |  | 65% | 65%
131 | Y | 37.571-1 | 17.2.6 | PRS-RSRPP measurement reporting delay test case for single positioning frequency layer without measurement gap in FR2 SA | The purpose of the test is to verify that the PRS-RSRPP measurement measurement meets the gapless measurement period requirement specified in Clause 9.9.6.6 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 9.9.6.6 | CATT | TBD |  |  | 1 | 65% | 65% |  | 65% | 65%
|  | 37.571-1 | 17.3 | NR PRS-RSRPP measurement accuracy test case in RRC_CONNECTED
132 | Y | 37.571-1 | 17.3.1 | PRS-RSRPP measurement accuracy test case for single positioning frequency layer in FR1 SA | The purpose of the test is to verify that the PRS-RSRPP measurement accuracy is within the specified limits. This test will verify the requirements in clause 10.1.38.2. The test is conducted in AWGN propagation condition in FR1 in standalone scenario. TS 38.133 10.1.38.2 | CATT | TBD | R5-240116 |  | 1 | 65% | 65% |  | 65% | 65%
133 | Y | 37.571-1 | 17.3.2 | PRS-RSRPP measurement accuracy test case for single positioning frequency layer with reduced number of samples in FR1 SA | The purpose of the test is to verify that the PRS-RSRPP measurement accuracy with reduced number of samples within the specified limits. This test will verify the requirements in clause 10.1.38.2. The test is conducted in AWGN propagation condition in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.38.2 | CATT | TBD | R5-240117 |  | 1 | 65% | 65% |  | 65% | 65%
134 | Y | 37.571-1 | 17.3.3 | PRS-RSRPP measurement accuracy test case for single positioning frequency layer in FR1 SA | The purpose of the test is to verify that the PRS-RSRPP measurement accuracy is within the specified limits. This test will verify the requirements in clause 10.1.38.2. The test is conducted in AWGN propagation condition in FR2 in standalone scenario. TS 38.133 10.1.38.2 | CATT | TBD | R5-240118 |  | 1 | 65% | 65% |  | 65% | 65%
135 | Y | 37.571-1 | 17.3.4 | PRS-RSRPP measurement accuracy test case for single positioning frequency layer with reduced number of samples in FR1 SA | The purpose of the test is to verify that the PRS-RSRPP measurement accuracy with reduced number of samples within the specified limits. This test will verify the requirements in clause 10.1.38.2. The test is conducted in AWGN propagation condition in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.38.2 | CATT | TBD | R5-240119 |  | 1 | 65% | 65% |  | 65% | 65%
|  | 37.571-1 | 17.4 | NR PRS-RSRPP measurement period test cases in RRC_INACTIVE
136 | Y | 37.571-1 | 17.4.1 | PRS-RSRPP measurement reporting delay test case for single positioning frequency layer in FR1 SA | The purpose of the test is to verify that the PRS-RSRPP measurement in RRC_INACTIVE meets the delay requirements specified in clause 5.6.5.5 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 5.6.5.5 | CATT | TBD | R5-242475 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
137 | Y | 37.571-1 | 17.4.2 | PRS-RSRPP measurement reporting delay test case for single positioning frequency layer with reduced number of samples in FR1 SA | The purpose of the test is to verify that the PRS-RSRPP measurement with the reduced samples meets the requirements specified in Clause 5.6.5.5 in an environment with AWGN propagation conditions in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 5.6.5.5 | CATT | TBD | R5-242476 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
138 | Y | 37.571-1 | 17.4.3 | PRS-RSRPP measurement reporting delay test case for single positioning frequency layer in FR2 SA | The purpose of the test is to verify that the PRS-RSRPP measurement in RRC_INACTIVE meets the delay requirements specified in clause 5.6.5.5 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 5.6.5.5 | CATT | TBD | R5-242477 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
149 | Y | 37.571-1 | 17.4.4 | PRS-RSRPP measurement reporting delay test case for single positioning frequency layer with reduced number of samples in FR2 SA | The purpose of the test is to verify that the PRS-RSRPP measurement with the reduced samples meets the requirements specified in Clause 5.6.5.5 in an environment with AWGN propagation conditions in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 5.6.5.5 | CATT | TBD | R5-242478 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
|  | 37.571-1 | 17.5 | NR PRS-RSRPP measurement accuracy test case in RRC_INACTIVE
150 | Y | 37.571-1 | 17.5.1 | PRS-RSRPP measurement accuracy test case for single positioning frequency layer in FR1 SA | The purpose of the test is to verify that the PRS-RSRPP measurement accuracy is within the specified limits. This test will verify the requirements in clause 10.1.38.2. The test is conducted in AWGN propagation condition in FR1 in standalone scenario. TS 38.133 10.1.38.2 | CATT | TBD | R5-242479 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
151 | Y | 37.571-1 | 17.5.2 | PRS-RSRPP measurement accuracy test case for single positioning frequency layer with reduced number of samples in FR1 SA | The purpose of the test is to verify that the PRS-RSRPP measurement accuracy with reduced number of samples in RRC_INACTIVE state is within the specified limits. This test will verify the requirements in clause 10.1.38.2. The test is conducted in AWGN propagation condition in FR1 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.38.2 | CATT | TBD | R5-242480 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
152 | Y | 37.571-1 | 17.5.3 | PRS-RSRPP measurement accuracy test case for single positioning frequency layer in FR2 SA | The purpose of the test is to verify that the PRS-RSRPP measurement accuracy is within the specified limits. This test will verify the requirements in clause 10.1.38.2. The test is conducted in AWGN propagation condition in FR2 in standalone scenario. TS 38.133 10.1.38.2 | CATT | TBD | R5-242481 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
153 | Y | 37.571-1 | 17.5.4 | PRS-RSRPP measurement accuracy test case for single positioning frequency layer with reduced number of samples in FR2 SA | The purpose of the test is to verify that the PRS-RSRPP measurement accuracy with reduced number of samples in RRC_INACTIVE state is within the specified limits. This test will verify the requirements in clause 10.1.38.2. The test is conducted in AWGN propagation condition in FR2 in standalone scenario when single positioning frequency layer is configured. TS 38.133 10.1.38.2 | CATT | TBD | R5-242482 |  | 1 | 65% (+65%) | 65% (+65%) |  | 65% | 65%
|  | 37.571-1 | Annex | Annex
154 |  |  | Annex C.1.6 | Addition of maximum test system uncertainty for NR PRS-based measurement requirements | Addition of maximum test system uncertainty for NR PRS-based measurement requirements for Rel-17 positioning test cases | CATT | TBD | R5-240107 |  | 1 | 10% | 10% |  | 10% | 10%
155 |  |  | Annex C.2.5 | Addition of test parameter relaxations for NR PRS-based measurement requirements | Addition of test parameter relaxations for NR PRS-based measurement requirements for Rel-17 positioning test cases | CATT | TBD | R5-240107 |  | 1 | 10% | 10% |  | 10% | 10%
156 |  |  | Annex C.4.5 | Addition of derivation of test requirements for NR PRS-based measurement requirements | Addition of derivation of test requirements for NR PRS-based measurement requirements for Rel-17 positioning test cases | CATT | TBD | R5-240107 |  | 1 | 10% | 10% |  | 10% | 10%
TS 37.571-2: UE Positioning -Protocol
|  | 37.571-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
162 |  | 37.571-2 | 2,3 | Introduction of Release-17 NR positioning protocol conformance contents | Adding Release-17 NR positioning methods associated abbreviations | CATT |  | R5-233395 |  | 0.5 | 100% | 100% |  | 100% | 100%
157 |  | 37.571-2 | 5 | Addition of BDS B2a and B3I into default conditions for E-UTRAN | Updating GNSS Auxiliary Information in Table 5.4.1.1-1 | CATT | TBD | R5-230335 |  | 0.5 | 100% | 100% |  | 100% | 100%
158 |  | 37.571-2 | 7 | Addition of BDS B2a and B3I into protocol conformance test cases for E-UTRAN | Adding B2a and B3I infoamation in MultiFreqAGNSS condition | CATT | TBD | R5-230335 |  | 1 | 100% | 100% |  | 100% | 100%
169 |  | 37.571-2 | 8 | Addition of Release-17 NR positioning enhancement default LPP message contents | Addition of Release-17 NR positioning enhancement default LPP message contents | CATT | TBD | R5-233395 |  | 1 | 100% | 100% |  | 100% | 100%
170 |  | 37.571-2 | 9.3.1.1 | Addition of Rel-17 missing IEs to LPP position capability transfer test case | Addition of Rel-17 missing IEs to LPP position capability transfer test case | CATT | TBD | R5-235341 |  | 0.5 | 100% | 100% |  | 100% | 100%
|  | 37.571-2 | 9.4 | RRC Protocol Procedures
161 | Y | 37.571-2 | 9.4.4 | Pre-configured Measurement Gap Procedures | TP(1):[TS 38.331 5.5.6] with { a NAS signalling connection existing } ensure that { when { UE has no assistance data stored and pre-configured positioning measurement gap was configured with associated ID via RRCReconfiguration message} then { UE sends a RRC Reconfiguration complete message to confirm the reception of pre-configured measurement gap configuration } } TP(2):[TS 38.331 5.5.6] with { a NAS signalling connection existing } ensure that { when { UE is configured with pre-configured measurement gap and the pre-configured measurement gap is sufficient for the location measurement and UE receives a location request messgae} then { UE sends a measurement gap activation request using UL MAC CE to activate the positioning measurement gap} } TP(3):[TS 38.321 5.18.20] with { a NAS signalling connection existing } ensure that { when { UE receives Positioning Measurement Gap Activation command containing an ID to activate the associated measurement gap } then { UE activates the positioning measurement gap and sends a PROVIDE LOCATION INFORMATION message containing a location estimate } } TP(4):[TS 38.331 5.5.6] with { a NAS signalling connection existing } ensure that { when { UE receives LPP Abort message indicate to stop performing location measurements and the preconfigured positioning measurement gap is activated} then { UE sends a Measurement Gap Deactivation Request to deactivate all the activated measurement gap} } | CATT | TBD | R5-233396 R5-234219 |  | 1 | 100% | 100% |  | 100% | 100%
168 | Y | 37.571-2 | 9.4.5 | Pre-configured PRS processing window procedures | TP(1):[TS 38.331 5.5.6] with { a NAS signalling connection existing } ensure that { when { UE has no assistance data stored and PRS processing window was configured with associated ID via RRCReconfiguration message} then { the UE sends a RRCReconfigurationComplete message to confirm the reception of pre-configured PRS processing window configuration } } TP(2):[TS 38.321 5.18.21] with { a NAS signalling connection existing } ensure that { when { UE was configured with PRS processing window and receives PPW Activation Command and then UE receives a location request from LMF} then { the UE sends a PROVIDE LOCATION INFORMATION message containing a location estimate} } | CATT | TBD | R5-233397 R5-234218 |  | 1 | 100% | 100% |  | 100% | 100%
162 | Y | 37.571-2 | 9.4.6 | UE Positioning Assistance Information | TP(1): [TS 38.331 5.7.14] with { a NAS signalling connection existing } ensure that { when { UE receives RRC Reconfiguration message requesting the association information of UL SRS resources for positioning with Tx TEGs } then { the UE sends a UEPositioningAssistanceInfo message including TxTEG information} } | CATT | TBD | R5-233398 R5-234217 |  | 1 | 100% | 100% |  | 100% | 100%
TS 37.571-3: Applicability and ICS UE Positioning test cases
|  | 37.571-3 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
164 |  | 37.571-3 | 2,3 | Addition of BDS B2a and B3I testing contents in TS 37.571-3 | Adding test case applicabilities for BDS B2a and B3I testing | CATT | TBD | R5-230336 |  | 0.1 | 100% | 100% |  | 100% | 100%
165 |  | 37.571-3 | 4 | Introduction of test case applicability for Release-17 NR positioning enhancement RF test cases | Adding test applicability and additional information for new TS 37.571-1 NR test cases | CATT | TBD | R5-234215, R5-240125 |  | 1 | 15% | 15% |  | 15% | 15%
166 |  | 37.571-3 | 4 | Introduction of test case applicability for Release-17 NR positioning enhancement signalling test cases | Adding test applicability and additional information for new TS 37.571-2 NR test cases | CATT | TBD | R5-233399 R5-235342 |  | 1 | 100% | 100% |  | 100% | 100%
166 |  | 37.571-3 | Annex A | Addition of PICS for Release-17 NR ositioning enhancement | Adding Release-17 NR positioning enhancement related PICS according to TS 37.355 | CATT | TBD | R5-233399 R5-235342 R5-242483 |  | 1 | 95% (+45%) | 95% (+45%) |  | 95% | 95%
TS 37.571-4: UE Positioning test suites (TTCN)
|  | 37.571-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
167 |  | 37.571-4 | <Clause> | Test suites for R17 NR positioning enhancement | <Describe task> |  | TBD |  | Progress of TTCN development is tracked in MCC TF160 reports to RAN5/RAN | 1 | 0% | 0% |  | 0% | 0%
TS 37.571-5: UE Positioning test scenarios and assistance data
|  | 37.571-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 37.571-5 |  | Addition of Release-17 NR ositioning enhancement test scenarios and assistance data | Addition of Release-17 NR ositioning enhancement test scenarios and assistance data |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD |  | 37.571-5 | 6 | Addition of test scenarios for BDS B2a and B3I minimum performance and signalling tests | Adding assistance data definitions and values for BDS B2a and B3I | CATT | TBD | R5-241916, R5-241577 |  | 1 | 100% | 100% |  | 100% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.