## Cover sheet
3GPP TSG-RAN WG5 Meeting #103 | [10 empty] | R5-243081
Fukuoka, Japan, May 20-24, 2024
Agenda Item: | 7.5.2
Source: | Samsung, Huawei, China Telecom
Title: | WP UE Conformance - NR MIMO Evolution for Downlink and Uplink
Work item code: | NR_MIMO_evo_DL_UL-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to WI ‘NR_MIMO_evo_DL_UL’, by analysing the test case impact, applicability and test environment, and updating the relevant conformance specifications. This work item will cover RF, Demod and RRM conformance test specifications for NR_MIMO_evo_DL_UL.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% (+5%) | 0 | 13 (+13)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 5% (+5%) | 0 | 10 (+10)
FR1 |  | 5% (+5%) | 0 | 2 (+2)
FR2 |  | 5% (+5%) | 0 | 8 (+8)
NSA Option 3 (EN-DC) |  | 5% (+5%) | 0 | 7 (+7)
FR1 |  | 5% (+5%) | 0 | 2 (+2)
FR2 |  | 5% (+5%) | 0 | 6 (+6)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2 | 0% | 0 | 4 (+4) |  |  |  | 0% | 0 | 4 (+4) |  |  |  |  | 0% | 0 | 4 (+4)
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533 | 0% | 0 | 5 (+5) | 0% | 0 | 1 (+1) | 0% | 0 | 1 (+1) |  | 0% | 0 | 2 (+2) | 0% | 0 | 2 (+2)
Applicability RF. Demod/QSI and RRM test cases | 38.522
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-240372 | New WID on UE Conformance – NR MIMO Evolution for Downlink and Uplink
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - NR MIMO Evolution for Downlink and Uplink | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_MIMO_evo_DL_UL-UEConTest
WP Scope: |  | <WP Scope description> | [13 empty] | vs Area
WP Resp: |  | Runsen Tang |  |  | runsen.tang@samsung.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | NSA Option 3 (EN-DC)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 | FR2
[15 empty] | 5% (+5%) | 5% (+5%) | 5% (+5%) | 5% (+5%)
[15 empty] | 2 (+2) | 11 (+11) | 2 (+2) | 9 (+9)
[15 empty] | 2 (+2) | 8.3 (+8.3) | 2 (+2) | 6.3 (+6.3)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.508-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-2 | <Clause> | <Title> | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | TBD |  |  | TBD
NR RF/RRM
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-2 | 3.2 | Symbols | Add new symbols for StxMP related requirements. | Samsung | TBD |  |  | 0.1 | 0% | 0% | 0% |  |  | 0% |  | 0%
TS 38.521-2: FR2 RF test cases - Tx
|  | 38.521-2 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-2 | 6.1 | General | add discription for simultaneous transmission to multiple directions |  | TBD |  |  | 0.1 | 0% | 0% | 0% |  |  | 0% |  | 0%
TBD |  | 38.521-2 | 6.2K | Transmitter power for simultaneous transmission to multiple directions | add sub-title | Samsung | TBD |  |  | 0.1 | 0% | 0% | 0% |  |  | 0% |  | 0%
TBD | Y | 38.521-2 | 6.2K.1 | UE maximum output power for simultaneous transmission to multiple directions | new test case for UE maximum output power for simultaneous transmission to multiple directions | Samsung | TBD |  |  | 1 | 0% | 0% | 0% |  |  | 0% |  | 0%
TBD | Y | 38.521-2 | 6.2K.2 | UE maximum output power reduction for simultaneous transmission to multiple directions | new test case for UE maximum output power reduction for simultaneous transmission to multiple directions | Samsung | TBD |  |  | 1 | 0% | 0% | 0% |  |  | 0% |  | 0%
TBD | Y | 38.521-2 | 6.2K.3 | UE maximum output power with additional requirements for simultaneous transmission to multiple directions | new test case for UE maximum output power with additional requirements for simultaneous transmission to multiple directions | Samsung | TBD |  |  | 1 | 0% | 0% | 0% |  |  | 0% |  | 0%
TBD | Y | 38.521-2 | 6.2K.4 | Configured transmitted power for simultaneous transmission to multiple directions | new test case for Configured transmitted power for simultaneous transmission to multiple directions | Samsung | TBD |  |  | 1 | 0% | 0% | 0% |  |  | 0% |  | 0%
|  | 38.521-2 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.521-2: FR2 RF test cases - Rx
|  | 38.521-2 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-2 Rx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-2 Rx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-2 Rx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.521-4: Demod/CSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-4 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-4 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-4 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.522 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. |  | TBD |  |  | 0.1
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
| Y | 38.533 | 4.x | [test case for TDCP] | [new test case for rel-18 MIMO TDCP ] |  | TBD |  |  | 1 | 0% |  | 0% |  |  |  | 0% | 0%
| Y | 38.533 | 4.x | [EN-DC FR1 UE transmit timing from two TRPs] | [new test case for EN-DC FR1 UE transmit timing from two TRPS] |  | TBD |  |  | 1 | 0% |  | 0% |  |  |  | 0%
| Y | 38.533 | 5.4.x | [EN-DC FR2 UE Transmit Timing From two TRPS] | [new test case for EN-DC FR2 UE transmit timing from two TRPS] |  | TBD |  |  | 1 | 0% |  | 0% |  |  |  |  | 0%
| Y | 38.533 | 6.4.x | [SA FR1 UE transmit timing from two TRPs ] | [new test case for SA FR1 UE transmit timing from two TRPS] |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
| Y | 38.533 | 7.4.x | [SA FR2 UE Transmit Timing From two TRPS] | [new test case for SA FR2 UE transmit timing from two TRPS] | Nokia | RAN5#107 (May-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
| Y | 38.533 | 5 | [sDCI mTRP, FR2 separate DL TCI state switching] | [sDCI mTRP, FR2 separate DL TCI state switching] |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
| Y | 38.533 | 5 | [sDCI mTRP, FR2 separate UL TCI state switching] | [sDCI mTRP, FR2 separate UL TCI state switching] | Nokia | RAN5#107 (May-25) |  |  | 1 | 0% | 0% |  |  |  | 0%
| Y | 38.533 | 5 | [sDCI mTRP, FR2 separate joint TCI state switching] | [sDCI mTRP, FR2 separate joint TCI state switching] |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
| Y | 38.533 | 5 | [mDCI FR1 two TA, RTD larger than CP joint TCI state switching | [mDCI FR1 two TA, RTD larger than CP joint TCI state switching |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.905 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
Layer 2
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
RRC
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
NAS
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD |  |  | 0.1
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.