## Cover sheet
RAN5 Meeting #103 | [7 empty] | R5-243199
Fukuoka, Japan, May 20-24, 2024
Agenda Item: | 7.5.2
Source: | Huawei, Hisilicon
Title: | UE Conformance - Further RF requirements enhancement for NR and EN-DC in frequency range 1
Work item code: | NR_ENDC_RF_FR1_enh2-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of this work item is to define the conformance testing aspects for the Rel-18 Further RF requirements enhancement for NR and EN-DC in frequency range 1 WI, including RF, RRM, Demod and Protocol areas.For enhancements for 4Tx, example bands considered in core WI are n41, n77/n78, n1. For enhancements for 8Rx, example bands considered in core WI are n41, n77/n78, n79, n7. In conformance test WI, example bands and example configurations would be selected from the above list based on industry interest to complete the structure of new RF test cases. For lower-MSD improvement, RAN5 needs to decide whether the test framework is per-band-combination basis or general for all band combinations. If the test framework is decided as per-band-combination basis, example band combination(s) would be selected based on industry interest to complete the relevant RF work.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% (+5%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 5% (+5%)
FR1 |  | 5% (+5%)
NSA Option 3 (EN-DC) |  | 5% (+5%)
FR1 |  | 5% (+5%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) |  |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  |  | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0% |  |  |  | 0%
Common ICS | 38.508-2 | 0% |  |  | 0% |  |  |  | 0%
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1 | 0% |  |  | 0%
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3 | 0% | [6 empty] | 0%
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533 | 0% |  |  | 0%
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0% |  |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0% |  |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-240290 | WID document title>UE Conformance - Further RF requirements enhancement for NR and EN-DC in frequency range 1
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Further RF requirements enhancement for NR and EN-DC in frequency range 1 | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_ENDC_RF_FR1_enh2-UEConTest
WP Scope: |  | The objective of this work item is to define the conformance testing aspects for the Rel-18 Further RF requirements enhancement for NR and EN-DC in frequency range 1 WI, including RF, RRM, Demod and Protocol areas. For enhancements for 4Tx, example bands considered in core WI are n41, n77/n78, n1. For enhancements for 8Rx, example bands considered in core WI are n41, n77/n78, n79, n7. In conformance test WI, example bands and example configurations would be selected from the above list based on industry interest to complete the structure of new RF test cases. For lower-MSD improvement, RAN5 needs to decide whether the test framework is per-band-combination basis or general for all band combinations. If the test framework is decided as per-band-combination basis, example band combination(s) would be selected based on industry interest to complete the relevant RF work.
WP Resp: |  | Yuxin Hao, Jingzhou Wu |  |  | haoyuxin@huawei.com;wujingzhou@chinatelecom.cn | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) | NSA Option 3 (EN-DC)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR1
[15 empty] | 5% (+5%) | 5% (+5%)
[15 empty] | 67 (+67) | 17 (+17)
[15 empty] | 60.5 (+60.5) | 15 (+15)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
TBD |  | 38.508-1 | 4.6.3 | Radio resource control information elements | Updating message contents |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
TBD |  | 38.508-1 | Annex | Set up diagrams | Introducing new connection diagrams |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
TS 38.508-2: Common ICS
TBD |  | 38.508-2 | A.x | Annex A (normative): ICS proforma for NR/5GS Generation User Equipment | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% | 0% |  | 0% | 0%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 | 3.2 | Symbols | Adding newly introduced symbols |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 4.2 | Applicability of minimum requirements | Updating the applicability of TxD minimum requirements |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% |  |  | 0%
|  | 38.521-1 | Annex.E | Global In-Channel TX-Test | Updating the method of global in-channel TX test for 4Tx |  | RAN5#109 (Nov-26) |  | E.4.8 is updated in 38101-1 F.8 | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | Annex.F | Measurement uncertainties and Test Tolerances | Updating the MU/TT for 4T or 8R if needed |  | RAN5#109 (Nov-27) |  |  | 1 | 0% | 0% |  |  | 0%
TS 38.521-1: FR1 RF test cases - Tx
TBD |  | 38.521-1 Tx | 6.2 | Transmitter power | [5 empty] | 0
|  | 38.521-1 | 6.2.2 | UE maximum output power reduction | Updating minimum requirement for 4Tx |  | RAN5#109 (Nov-25) |  |  | 1
|  | 38.521-1 | 6.2.4 | Configured transmitted power | Updating minimum requirement for 8Rx |  | RAN5#109 (Nov-25) |  |  | 1
TBD |  | 38.521-1 Tx | 6.2D | Transmitter power for UL MIMO | [5 empty] | 0
|  | 38.521-1 | 6.2D.1 | UE maximum output power for UL MIMO | Updating the minimum requirements and testing part for 4-layer UL MIMO |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.2D.2 | UE maximum output power reduction for UL MIMO | Updating the minimum requirements and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.2D.3 | UE additional maximum output power reduction for UL MIMO | Updating the minimum requirement for UE supporting 4Tx;updating the test requirement for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.2D.4 | Configured transmitted power for UL MIMO | Updating the minimum requirement for UE and the test part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 Tx | 6.2G | Transmitter power for Tx Diversity | [5 empty] | 0
|  | 38.521-1 | 6.2G.1 | UE maximum output power for Tx Diversity | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.2G.2 | UE maximum output power reduction for Tx Diversity | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.2G.3 | UE additional maximum output power reduction for Tx Diversity | Updating the test requirement for PC1.5 UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 Tx | 6.3D | Output power dynamics for UL MIMO | [5 empty] | 0
|  | 38.521-1 | 6.3D.1 | Minimum output power for UL MIMO | Updating the test applicability and minimum requirement for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.3D.2 | Transmit OFF power for UL MIMO | Updating the test applicability for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.3D.3 | Transmit ON/OFF time mask for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.3D.4.1 | Absolute power tolerance for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.3D.4.2 | Relative power tolerance for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.3D.4.3 | Aggregate power tolerance for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 Tx | 6.4D | Transmit signal quality for UL MIMO | [5 empty] | 0
|  | 38.521-1 | 6.4D.1 | Frequency error for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.4D.2.1 | Error Vector Magnitude for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.4D.2.2 | Carrier leakage for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.4D.2.3 | In-band emissions for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.4D.2.4 | EVM equalizer spectrum flatness for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.4D.4 | Requirements for coherent UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 Tx | 6.4G | Transmit signal quality for Tx Diversity | [5 empty] | 0
|  | 38.521-1 | 6.4G.2 | Transmit modulation quality for Tx Diversity | Updating the testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 Tx | 6.5D | Output RF spectrum emissions for UL MIMO | [5 empty] | 0
|  | 38.521-1 | 6.5D.1 | Occupied bandwidth for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.5D.2.1 | General | Updating the minimum requirement for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.5D.2.2 | Spectrum emission mask for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.5D.2.3 | Additional spectrum emission mask for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.5D.2.4.1 | NR ACLR for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.5D.2.4.2 | UTRA ACLR for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.5D.3 | Spurious emissions for UL MIMO | Updating the minimum requirement for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.5D.3_1.1 | General spurious emissions for UL MIMO (Rel-16 onward) | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.5D.3_1.2 | Spurious emission for UE co-existence for UL MIMO (Rel-16 onward) | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.5D.3_1.3 | Additional spurious emissions for UL MIMO (Rel-16 onward) | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 6.5D.4 | Transmit intermodulation for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 Tx | 6.5G | Output RF spectrum emissions for Tx Diversity | [5 empty] | 0
|  | 38.521-1 | 6.5G.2.1 | Spectrum emission mask for Tx Diversity | Updating the testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
TS 38.521-1: FR1 RF test cases - Rx
|  | 38.521-1 | 7.2 | Diversity characteristics | Updating this clause for 8Rx requirements |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% |  |  | 0%
|  | 38.521-1 Tx | 7.3 | Reference sensitivity | [5 empty] | 0
|  | 38.521-1 | 7.3.1 | General | Updating the general requirement for 8Rx UE |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 7.3.2 | Reference sensitivity power level | Updating the minimum requirement and testing part for 8Rx UE |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 Tx | 7.3A | Reference sensitivity for CA | [5 empty] | 0
|  | 38.521-1 | 7.3A.0 | Minimum conformance requirements | Updating the minimum requirement for 8Rx UE; adding new requirement for Lower-MSD requirement for inter-band CA in 7.3A.0.7 |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 7.3A.1 | Reference sensitivity power level for 2DL CA without exception | Updating the minimum requirement and testing part for UE supporting 8Rx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 7.3A.1_1 | Reference sensitivity power level for 2DL CA exceptions | Updating the minimum requirement and testing part for UE supporting 8Rx or Lower-MSD |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 7.3A.2 | Reference sensitivity power level for 3DL CA without exceptions | Updating the minimum requirement and testing part for 8Rx UE |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 7.3A.2_1 | Reference sensitivity power level for 3DL CA exceptions | Updating the minimum requirement and testing part for UE supporting 8Rx or Lower-MSD |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 Tx | 7.3C | Reference sensitivity for SUL | [5 empty] | 0
|  | 38.521-1 | 7.3C.0 | Minimum conformance requirements | Updating the minimum requirement for UE supporting 8Rx |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 7.3C.2 | Reference sensitivity power level for SUL | Updating testing part for UE supporting 8Rx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 Tx | 7.3D | Reference sensitivity for UL MIMO | [5 empty] | 0
|  | 38.521-1 | 7.3D.1 | General | Updating the general requirement for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 7.3D.2 | Reference sensitivity power level for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 7.3G | Reference sensitivity for Tx Diversity | Updating the general requirement for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 7.4D | Maximum input level for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 7.5D | Adjacent channel selectivity for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 Tx | 7.6D | Blocking characteristics for UL MIMO | [5 empty] | 0
|  | 38.521-1 | 7.6D.1 | General | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 7.6D.2 | In-band blocking for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 7.6D.3 | Out-of-band blocking for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 7.6D.4 | Narrow band blocking for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 7.7D | Spurious response for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
|  | 38.521-1 | 7.8D | Intermodulation characteristics for UL MIMO | Updating the minimum requirement and testing part for UE supporting 4Tx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  |  | 0%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Rx
|  | 38.521-3 | 7.1 | General | Adding general requirements for UE equipped with 8Rx |  | RAN5#109 (Nov-25) |  |  | 0.5 | 0% |  | 0% |  |  | 0%
|  | 38.521-3 | 7.3B | Reference sensitivity level for DC | [5 empty] | 0
|  | 38.521-3 | 7.3B.1 | General | Adding general requirements for UE equipped with 8Rx |  | RAN5#109 (Nov-25) |  |  | 1 | 0% |  | 0% |  |  | 0%
|  | 38.521-3 | 7.3B.2.0 | Minimum Conformance Requirements of Reference sensitivity for DC | Updating the minimum requirement for UE supporting 8Rx; adding requirements for lower-MSD for inter-band ENDC in FR1 |  | RAN5#109 (Nov-25) |  |  | 1 | 0% |  | 0% |  |  | 0%
|  | 38.521-3 | 7.3B.2.3 | Reference sensitivity for Inter-band EN-DC within FR1 (2 CCs) | Updating the testing part for UE supporting 8Rx and lower-MSD |  | RAN5#109 (Nov-25) |  |  | 1 | 0% |  | 0% |  |  | 0%
|  | 38.521-3 | 7.3B.2.3_1.1 | Reference sensitivity for EN-DC within FR1 (3 CCs) | Updating the testing part for UE supporting 8Rx and lower-MSD |  | RAN5#109 (Nov-25) |  |  | 1 | 0% |  | 0% |  |  | 0%
|  | 38.521-3 | 7.4B | Maximum Input Level for DC | Updating the test priority in case of Rx antenna ports in the test case.7.4B.1 and 7,4B.2 for 8Rx UE |  | RAN5#109 (Nov-25) |  |  | 1 | 0% |  | 0% |  |  | 0%
|  | 38.521-3 | 7.5B.1 | Adjacent Channel Selectivity for intra-band contiguous EN-DC (2 CCs) | Updating the test priority in case of Rx antenna ports in the test case for 8Rx UE |  | RAN5#109 (Nov-25) |  |  | 1 | 0% |  | 0% |  |  | 0%
|  | 38.521-3 | 7.6B.2 | Inband blocking for DC | Updating the test priority in case of Rx antenna ports in the test case 7.6B.2.1 and 7.6B.2.3_1 for 8Rx UE |  | RAN5#109 (Nov-25) |  |  | 1 | 0% |  | 0% |  |  | 0%
|  | 38.521-3 | 7.6B.3 | Out-of-band blocking for DC | Updating the test priority in case of Rx antenna ports in the test case 7.6B.3.1, 7.6B.3.3 and 7.6b.3.3_1 for 8Rx UE |  | RAN5#109 (Nov-25) |  |  | 1 | 0% |  | 0% |  |  | 0%
|  | 38.521-3 | 7.6B.4 | Narrow band blocking for DC | Updating the test priority in case of Rx antenna ports in the test case 7.6B.4.1 and 7.6B.4.3_1 for 8Rx UE |  | RAN5#109 (Nov-25) |  |  | 1 | 0% |  | 0% |  |  | 0%
|  | 38.521-3 | 7.8B.2 | Wide band Intermodulation | Updating the test priority in case of Rx antenna ports in the test case 7.8B.2.1 and 7.8B.2.3_1 for 8Rx UE |  | RAN5#109 (Nov-25) |  |  | 1 | 0% |  | 0% |  |  | 0%
TS 38.521-4: Demod/CSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  |  | TBD
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
TBD |  | 38.522 | 4.0 | Test case conditions and selection criteria | Add new ICS statements. |  | TBD |  |  | 0.5 | 0% | 0% | 0% |  | 0% | 0%
TBD |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Updating applicability for test cases in 38.521-1 |  | TBD |  |  | 0.5 | 0% | 0% |  |  | 0%
TBD |  | 38.522 | 4.1.3 | NR interworking between NR FR1 and NR FR2 and between NR and LTE conformance test cases | Updating applicability for test cases in 38.521-3 |  | TBD |  |  | 0.5 | 0% |  | 0% |  |  | 0%
TBD |  | 38.522 | 4.1.4 | Performance conformance test cases | Updating test case applicability statements for the new test cases introduced for 38.521-4 |  | TBD |  |  | 0.5 | 0% | 0% |  |  | 0%
TBD |  | 38.522 | 4.2 | RRM conformance test cases | Updating test case applicability statements for the test cases introduced for 38.533 |  | TBD |  |  | 0.5 | 0% | 0% |  |  | 0%
TS 38.533: RRM test cases
TBD |  | 38.533 | D.4B | Antenna connection for 8 Rx capable UEs | adding antenna connection description for 8Rx UE |  | TBD |  |  | 1 | 0% | 0% |  |  | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | Adding TT analysis for RRM test cases |  | TBD |  |  | 0.5 | 0% | 0% |  |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 | 4.1 | Test point analysis for FR1 test cases in TS 38.521-1 | Add TP analysis for test cases in 38.521-1 |  | TBD |  |  | 0.5 | 0% | 0% |  |  | 0%
|  | 38.905 | 4.3 | Test point analysis for test cases in TS 38.521-3 | Add TP analysis for test cases in 38.521-3 |  | TBD |  |  | 0.5 | 0% |  | 0% |  |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.