## WP scope
Work plan for introduction of NR CA PC3 FR1 configurations into 3GPP UE conformance test specifications
| WP template: | WP NR CA PC3 FR1 v1.11.0
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed.
Workplan scope
| Workplan Name |  | WP NR CA PC3 FR1 v1.11.0 | [6 empty] | <= Default workplan name is the filename. To change replace the formula with preferred text.
| Company (Contact) | [8 empty] | <= Enter Responsible Company and Contact for the configurations in the WP
| Target completion |  | RAN5#105 | [6 empty] | <= Enter target completion date here. Format RAN5#<xx>, where <xx> is the RAN5 meeting, e.g. RAN5#94-e>
Comments
Overall completion
Target configurations
Note: A work plan can include multiple target configurations but it is recommended to create separate work plans for Intra-band continuous, Intra-band Non-Continuous and Inter-band configurations. Copy target configuration(s) for the WP from the "PRD21 NR bands and 5G NR CADC list" as values in the table below by: 1. Select and copy the complete rows of the target configuration(s) in the "PRD21 NR bands and 5G NR CADC list". 2. Select cell A15 in the table below and right-click. 3. Select paste option "Paste as values" (see picture). It may take a few seconds before the pasted information is shown. 4. To include additional configurations, repeat steps 1 to 3, but in step 2 select the cell in column A next below the last configuration in the list.
Marked config | Release introduced in TS 38.101-x | Type of configuration | TS and Source Table | Configuration | Uplink configuration | PC3 Status | PC2 completed? | RAN5 Completion Meeting (PC3) | Completion Reference (PC3) | Interested operator (PC3) | Responsible Company (contact) (PC3) | Assignment [RAN5 meeting] (PC3) | Applicable RAN5 WI code(s) for CRs | Comments | Introduced in PRD version
v.1.0.0
v.1.0.0

## WP NR CA PC3 FR1
Work plan for introduction of NR CA PC3 FR1 configurations into 3GPP UE conformance test specifications
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed. | [13 empty] | WP template: WP NR CA PC3 FR1 v1.11.0
1. Configurations covered by the work plan
|  | Type of CA configurations |  |  |  | WP item Applicability Label | CA configurations [DL/UL]
|  | New NR CA configuration without UL CA |  |  |  | DL/- BCS0
|  | New NR CA configuration with UL CA |  |  |  | DL/UL BCS0
|  | New BCS for NR CA configuration without UL CA |  |  |  | DL/- new BCS
|  | New BCS for NR CA configuration with UL CA |  |  |  | DL/UL new BCS
|  | All configurations |  |  |  | All
|  | All BCS0 configurations (No BCS included in config.name) |  |  |  | All BCS0
|  | All new BCS configurations with BCS>0 |  |  |  | All new BCS
2. Overall status vs WP steps
[7 empty] | Overall Sub-WI |  | Handling of not applicable WP item rows: - WP item rows not applicable for the target configurations are indicated as being strikethrough text. You can hide those not applicable WP items by filtering on excluding "(Blanks)" in column "Impacted config(s)". - Some WP items may still not be applicable for the target configurations based on the applicability information in the "Task" column. To NOT include those WP items in the overall status calculations You need to clear the "Detailed Completion Status" cells for the WP item row and state "N/A" in the comments field. Note: It is not recomended to completly delete not applicable WP item rows in case additional target configurations added at a later stage may require those WP Item rows.
Overall completeness
Step 1: Work plan pre-requisite
Step 2: Complete Test Point (TP) analysis for impacted NR CA configurations
Step 3.1: CR(s) to common test environment (TS 38.508-1)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-1)
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-1, clause 6)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-1, clause 7)
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
3. Details
Do not edit | [7 empty] | WP item columns to be filled in |  |  |  | Do not edit |  |  | WP item columns to be filled in
Step 1: Work plan pre-requisite
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted config(s) [DL/UL] | Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Bands completed | TCs available | BSC0 completed | Impacted CBWs identified | Bands new CBWs completed
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
All BCS0 | 1-1 | Pre-requisite | PRD21 | NR bands worksheet | All NR bands completed for BCS0 |  | Set status in column "Bands completed" to 100% when all impacted NR bands have been confirmed completed in RAN5 PRD21 worksheet "NR bands". |  | RAN5#105 |  |  | 1 |  |  | 0%
All new BCS | 1-2 | Pre-requisite | 38.101-1 | 5.5A.1 | BCS0 commpleted for the NR CA configuration |  | Set status in column "BCS0 completed" to 100% when the BCS0 of all the new BCS configurations have been confirmed completed in RAN5 PRD21 worksheet "5G NR CADC configurations". BCS0 configuration is listed in PRD21 as NR CA configuration without "BCS" suffix in the name. |  | RAN5#105 |  |  | 1 |  |  |  |  | 0%
All new BCS | 1-3 | Pre-requisite | 38.101-1 | 5.5A.1 | Bandwidth included in the new BCS |  | Set status in column "Impacted CBWs identified" to 100% when all new CBWs added by the new BCS of the configuration(s) have been identified and listed in the "Comments" column. |  | RAN5#105 |  |  | 1 | [5 empty] | 0%
All new BCS | 1-4 | Pre-requisite | 38.101-1 PRD21 | NR bands worksheet | All NR bands completed for new BCS |  | Set status in column "Bands new CBWs completed" to 100% when all channel bandwidths of the involved NR bands for the new BCS of the configuration have been confirmed completed in RAN5 PRD21 worksheet "NR bands". |  | RAN5#105 |  |  | 1 | [6 empty] | 0%
All BCS0 | 1-5 | Pre-requisite | 38.521-1 | 6, 7 | All applicable Transmitter (clause 6) and Receiver (clause 7) for the type of NR CA configuration completed |  | Set status in column "TCs available" to 100% when all applicable test cases in 38.521-1 are completed for at least one of the same NR CA type of CA configuration. If the relevant test cases are not completed then contact the responsible for the test case as indicated in the relevant WI WP and consider to support to get the test case(s) completed. |  | RAN5#105 |  |  | 1 |  |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 2: Complete Test Point (TP) analysis for impacted NR CA configurations
WP item applicability | WP item ID | Area | TR | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
TP analysis
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
DL/UL BCS0 | 2 | TP Analysis | 38.905 | 4.1.1 | Test point (TP) analysis for MOP |  | For each UL CA configuration perform an MOP TP analysis as described in TR 38.905. The TP analysis is documented by a CR to 38.905 clause 4.1.x including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required A-MPR TP analysis have been included in TR 38.905. |  | RAN5#105 |  |  | 1 |  |  | 0%
All | 2-1 | TP Analysis | 38.905 | 4.1.2 | Test point (TP) analysis for A-MPR |  | For each UL CA configuration perform an A-MPR TP analysis as described in TR 38.905 clause 4.1.2 for intra-band contiguous UL CA and in clause 4.1.3 for inter-band UL CA. The TP analysis is documented by a CR to 38.905 clause 4.1.x including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required A-MPR TP analysis have been included in TR 38.905. |  | RAN5#105 |  |  | 1 |  |  | 0%
All BCS0 | 2-2a | TP Analysis | 38.905 | 4.1.3.1 | Test point (TP) analysis for reference sensitivity for BCS0 |  | For each NR CA configuration >=2DL perform reference sensitivity TP analysis as described in TR 38.905, Annex B.9. Document the TP analysis by a CR to TR 38.905. The status column "TP analysis" is set to 100% when all required TP analysis have been included in TR 38.905. |  | RAN5#105 |  |  | 1 |  |  | 0%
All new BCS | 2-2b | TP Analysis | 38.905 | 4.1.3.1 | Test point (TP) analysis for reference sensitivity for new BCS > 0 |  | For each NR CA configuration >= 2DL update the reference sensitivity TP analysis as described in TR 38.905, Annex B.9 for the new BCSs. Document the TP analysis by a CR to TR 38.905. The status column "TP analysis" is set to 100% when all required TP analysis for the new BCSs have been included in TR 38.905. |  | RAN5#105 |  |  | 1 |  |  | 0%
DL/UL BCS0 | 2-3 | TP Analysis | 38.905 | 4.1.3.2 | Test point (TP) analysis for UE co-existence test cases for inter-band UL CA |  | For each two band UL CA inter-band configuration perform UE co-existence spurious emission TP analysis as described in TR 38.905. Document the TP analysis by a CR to TR 38.905 including the details of the TP analysis in an attached zip-file. The status column "TP analysis" is set to 100% when all required TP analysis have been included in TR 38.905. |  | RAN5#105 |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3: CRs to impacted TSs areas
Step 3.1: CR(s) to common test environment (TS 38.508-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
Test Freq.
1
All BCS0 | 3.1-1a | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.1.2 to 4.3.1.1.5 | Test frequencies BSC0 |  | - Add the NR CA configuration to the relevant test frequency table in clause 4.3.1.1.2 to 4.3.1.1.5. - Check that the involved bands have single carrier test frequencies specified in 4.3.1.x - For NR CA configurations including any intra-band contiguous CCs or any intra-band non-contiguous CCs check if existing test frequencies can be re-used or if new test frequencies need to be specified in clause 4.3.1.1.3 and 4.3.1.1.5 respectively. |  | RAN5#105 |  |  | 1 |  |  | 0%
All new BCS | 3.1-1b | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.1.3 and 4.3.1.1.5 | Test frequencies BCS>0 |  | - For NR CA configurations including any intra-band contiguous CCs or any intra-band non-contiguous CCs check if existing test frequencies can be re-used or if new test frequencies need to be specified for the new BCS CBW combinations in clause 4.3.1.1.3 and 4.3.1.1.5 respectively. |  | RAN5#105 |  |  | 1 |  |  | 0%
All new BCS | 3.1-2 | 38.508-1 - (4) Common | 38.508-1 | 4.6.3 | Radio resource control information elements |  | Add Radio resource control information elements for new type of CA combination configurations |  | RAN5#105 |  |  | 1 |  |  | 0%
All BCS0 | 3.1-3 | 38.508-1 - (6) Common SIG | 38.508-1 | 6.2.3.4 | Test frequencies for NR CA signalling test |  | For Intra-band contiguous or intra-band non-contiguous configurations with 2CC add test frequencies in clause 6.2.3.4 (protocol testing limited to 2CC NR CA configurations) |  | RAN5#105 |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-1)
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Clause 5 | Discussion paper
[15 empty] | 1 | 1
All BCS0 | 3.2-0.0 | 38.521-1 - General | PRD21 | 4.1 | Discussion paper on adding configuration to chapter 5 without changes to RF transmitter and receiver test cases. |  | If it is thought there are no configuration specific changes needed for Chapter 6/7 or only the changes to ΔTIB,c and ΔRIB,c are needed in Chapter 6/7, a paper shall be submitted to justify why no such changes are needed to Chapter 6/7 or why only the changes to ΔTIB,c and ΔRIB,c are needed in Chapter 6/7. If deemed that no discussion paper is needed then set status to 100% and add comment in the comments column why no discussion paper is needed. |  | RAN5#105 |  |  | 1 |  |  |  | 0%
All BCS0 | 3.2-0 | 38.521-1 - General | 38.521-1 | 3.2 | Symbols |  | Check if new symbols need to be added for the new CADC band combos. |  | RAN5#105 |  |  | 1 |  |  | 0%
All BCS0 | 3.2-1 | 38.521-1 - General | 38.521-1 | 5.2A.1 | Configurations including any intra-band contiguous CCs or any intra-band non-contiguous CCs. |  | For intra-band contiguous and non-contiguos CA configrurations add the CA operating bands to the relevant table in clause 5.2.A.1. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | RAN5#105 |  |  | 1 |  |  | 0%
All BCS0 | 3.2-2 | 38.521-1 - General | 38.521-1 | 5.2A.2 | Inter-band CA operating bands |  | For inter-band CA configurations add the CA operating bands to the relevant table in clause 5.2A.2. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | RAN5#105 |  |  | 1 |  |  | 0%
All BCS0 | 3.2-3a | 38.521-1 - General | 38.521-1 | 5.5A.1 | Configurations for intra-band contiguous CCs for BCS0 |  | For intra-band contigous CA configurations add the CA configuration to the relevant table in clause 5.5A.1. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | RAN5#105 |  |  | 1 |  |  | 0%
All new BCS | 3.2-3b | 38.521-1 - General | 38.521-1 | 5.5A.1 | Configurations for intra-band contiguous CCs for new BCS >0 |  | For intra-band contigous CA configurations add the new BCS CBW combinations for the CA configuration to the relevant table in clause 5.5A.1. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | RAN5#105 |  |  | 1 |  |  | 0%
All BCS0 | 3.2-4a | 38.521-1 - General | 38.521-1 | 5.5A.2 | Configurations for intra-band non-contiguous CCs for BCS0 |  | For intra-band non-contigous CA configurations add the CA configuration to the relevant table in clause 5.5A.2. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | RAN5#105 |  |  | 1 |  |  | 0%
All new BCS | 3.2-4b | 38.521-1 - General | 38.521-1 | 5.5A.2 | Configurations for intra-band non-contiguous CCs for new BCS > 0 |  | For intra-band non-contigous CA configurations add the new BCS CBW combination for the CA configuration to the relevant table in clause 5.5A.2. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | RAN5#105 |  |  | 1 |  |  | 0%
All BCS0 | 3.2-5a | 38.521-1 - General | 38.521-1 | 5.5A.3 | configurations for inter-band CCs for BCS0 |  | For inter-band CA configurations add the CA configurationto the relevant table in clause 5.5A.3. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | RAN5#105 |  |  | 1 |  |  | 0%
All new BCS | 3.2-5b | 38.521-1 - General | 38.521-1 | 5.5A.3 | configurations for inter-band CCs fo rnew BCS > 0 |  | For inter-band CA configurations add the new BCS CBW combinations for the CA configurationto the relevant table in clause 5.5A.3. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | RAN5#105 |  |  | 1 |  |  | 0%
DL/UL BCS0 | 3.2-6 | 38.521-1 - General | 38.521-1 | 6.2A.4.0.2 | ΔTIB,c for CA |  | For inter-band CA configurations add ΔTIB,c for the CA configuration to the relevant table in clause 6.2A.4.0.2. |  | RAN5#105 |  |  | 1 |  |  | 0%
All | 3.2-7 | 38.521-1 - General | 38.521-1 | 7.3A.0.3 | ΔRIB,c for CA |  | For inter-band CA configurations add ΔRIB,c for the CA configuration to the relevant table in clause 7.3A.0.3. |  | RAN5#105 |  |  | 1 |  |  | 0%
All | 3.2-8 | 38.521-1 - General | 38.521-1 | 7.3A.0.4 | Reference sensitivity exceptions due to UL harmonic interference for CA |  | For inter-band CA configurations add the reference sensitivity exceptions, Uplink configuration and MSD for inter-band CA to the relevant table in clause 7.3A.0.4. |  | RAN5#105 |  |  | 1 |  |  | 0%
All | 3.2-9 | 38.521-1 - General | 38.521-1 | 7.3A.0.5 | Reference sensitivity exceptions due to intermodulation interference due to 2UL CA |  | For inter-band CA configurations add Reference sensitivity and Uplink/Downlink configurations for the CA configuration to the relevant table in clause 7.3A.0.5. |  | RAN5#105 |  |  | 1 |  |  | 0%
All | 3.2-10 | 38.521-1 - General | 38.521-1 | 7.3A.0.6 | Reference sensitivity exceptions due to cross band isolation for CA |  | For inter-band CA configurations add Reference sensitivity and Uplink/Downlink configurations for the CA configuration to the relevant table in clause 7.3A.0.6. |  | RAN5#105 |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-1, clause 6)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
DL/UL BCS0 | 3.3-1 | 38.521-1- RF Tx | 38.521-1 | 6.2A.1.0.3 | UE maximum output power for Inter-band CA Note! This WP item is dependent [UDL/UL] on MOP TP analysis (Step 2, WP item 2) |  | For configurations including any inter-band UL CA CCsc add the UE maximum output power for inter-band UL CA to Table 6.2A.1.0.3-1. |  | RAN5#105 |  |  | 1 |  |  | 0% |  | 0% | 0%
DL/UL BCS0 | 3.1-2 | 38.521-1- RF Tx | 38.521-1 | 6.2A.1.0.4 | UE maximum output power for Intra-band contiguous CA |  | For configurations including any Intra-band contiguous UL CA add the UE maximum output power for Intra-band contiguous UL CA to Table 6.2A.1.0.4-1. |  | RAN5#105 |  |  | 1 |  |  | 0% |  | 0% | 0%
DL/UL BCS0 | 3.3-3 | 38.521-1- RF Tx | 38.521-1 | 6.2A.1.1 | UE maximum output power for CA (2UL CA) |  | For any FR1 Inter-band/Intra-band non-contiguous 2UL CA configurations add the test requirements for Inter-band/Intra-band non-contiguous 2UL CA to Table 6.2A.1.1.5-1. |  | RAN5#105 |  |  | 1 |  |  | 0% |  | 0% | 0%
DL/UL BCS0 | 3.3-4 | 38.521-1- RF Tx | 38.521-1 | 6.2A.3.1 | UE additional maximum output power reduction for CA (2 UL CA) |  | For inter-band CA (2 UL CA) add the Initial Conditions to Table 6.2A.3.1.4.1-1; Add tables for inter-band CA (2 UL CA) in Section 6.2A.3.1.5 Test requirement. |  | RAN5#105 |  |  | 1 |  |  | 0% |  | 0% | 0% | 0%
DL/UL BCS0 | 3.3-5 | 38.521-1- RF Tx | 38.521-1 | 6.5A.3.2 | Inter-band spurious emission for UE co-existence Note! This WP item is dependent [UDL/UL] on spurious emission TP analysis (Step 2, WP item 2-3) |  | For configurations with inter-band UL CA: - Add the minimum conformance requirements - If the TP analysis in Step 2 (WP item 5) shows that additional TPs more than the default TP#1 and TP#2 are needed add all test points (including default TPs if applicable) based on the TP analysis done in Step 2 (WP item 5). - Add test requirement based on the TP analysis done in Step 2 (WP item 4-2). |  | RAN5#105 |  |  | 1 |  |  | 0% |  | 0% | 0% | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-1, clause 7)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
All BCS0 | 3.4-1a | 38.521-1-RF Rx | 38.521-1 | 7.3A.1~4 | Reference sensitivity power level for 2DL to 5DL CA for BCS0 Note! This WP item is dependent on Reference Sensitivity TP analysis (Step 2, WP item 2-2a) |  | Add test configuration and test requirements for any exceptional/non-exceptional requirements based on TR 38.905 reference sensitivity TP analysis in Step 2 (WP item 2-2a). |  | RAN5#105 |  |  | 1 |  |  | 0% |  | 0% | 0%
All new BCS | 3.4-1b | 38.521-1-RF Rx | 38.521-1 | 7.3A.1~4 | Reference sensitivity power level for 2DL to 5DL CA for new BCS > 0 Note! This WP item is dependent on Reference Sensitivity TP analysis (Step 2, WP item 2-2b) |  | Update test configuration and test requirements for any new exceptional/non-exceptional requirements based on TR 38.905 reference sensitivity TP analysis in Step 2 (WP item 2-2b). |  | RAN5#105 |  |  | 1 |  |  | 0% |  | 0% | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.5: CR(s) for RF Performance test cases (TS 38.521-4)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
| 3.5-1 | [5 empty] | No changes needed |  | RAN5#105 |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.6: CRs to protocol test cases (TS 38.523-1, TS 38.523-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
ICS / TC appli.
1
| 3.6-1 | [5 empty] | No changes needed |  | RAN5#105 |  |  | 1
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) [UDL/UL] | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
ICS / TC appli.
1
All | 4-1 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2A.2.1 | NR CA Intra-band contiguous |  | Add configurations for Intra-band contiguous CA within FR1 to the relevant table in clause A.4.3.2A.2.1 |  | RAN5#105 |  |  | 1 |  |  | 0%
All | 4-2 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2A.3.1 | NR CA Intra-band non-contiguous |  | Add configurations for NR Intra-band non-contiguous CA within FR1 to the relevant table in clause A.4.3.2A.3.1 |  | RAN5#105 |  |  | 1 |  |  | 0%
All | 4-3 | 38.508-2 - ICS | 38.508-2 | Annex A.4.3.2A.4 | NR Inter-band CA |  | Add CA configurations for NR Inter-band CA within FR1 to the relevant table in clause A.4.3.2A.4 |  | RAN5#105 |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Note on N31: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N42: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N54: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on N64: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N85: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N96: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N104: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N111: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N118: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.

## Revision History WP template
Revision history for WP template only Note! Cell A3 shall always include the version of the latest version of the WP as used to set the WP template version in the WP scope worksheet.
Version | Date | Comment
v1.11.0 | RAN5#105 | Editorial correction to clause number in Step 2 WP item 2 and 2-1
v1.10.0 | RAN5#104 | No changes. Same as v1.9.0.
v1.9.0 | RAN5#103 | Add "Test point (TP) analysis for A-MPR" to Step 2 WP item 2-1
v1.8.0 | RAN5#102 | No changes. Same as v1.7.0.
v1.7.0 | RAN5#101 | No changes. Same as v1.6.0.
v1.6.0 | RAN5#100 | No changes. Same as v1.5.0.
v1.5.0 | RAN5#99 | No changes. Same as v1.4.0.
v1.4.0 | RAN5#98 | No changes. Same as v1.3.0.
v1.3.0 | RAN5#97 | No changes. Same as v1.2.0.
v1.2.0 | RAN5#96-e | 1. Extended the number of rows in the input table to cope with the case when multiple cut and paste of configurations from PRD21 CADC list are done. 2. Clarify references to TP analysis in dependent test cases.
v1.1.0 | RAN5#95-e | 1. Updated WP template version in WP scope worksheet to get version number from cell A3 in the "Revision History WP template" worksheet. 2. Correcting TS for WP item 1-5 3. Correcting formulas in cells I5 to I7 on WP worksheet to handle the case when configuration table includes empty cells for the configuration columns. 4. Correcting clause reference for WP item 3.1-3 from 6.2.3.2 to 6.2.3.4. 5. Correcting TS reference in "area" and "TS" columns from 36.521-1 to 38.521-1. 6. Added "set to 100% when..." for WP Item 1-3 taks text. 7. Clarified for WP items 3.4-1a and 3.4-1b that the task is also for non-exceptional requirements. 8. Added a note to WP items 3.2-1 to 3.2-8 to remind about merge with "jumbo" CR. 9. Added WP item 3.2-0.0 about need for discussion paper to add configuration information to chapter 5. Renumbered current WP item 3.2-0 to 3.2-0.1. 1. Clarify references to TP analysis in dependent test cases.
v1.0.0 | RAN5#94-e | Initial version