## ChHist
Source | 3GPP MCC TF160
Change history
Date | Summary of changes
2024-09-18 | Creation of consolidated spreadsheet
2024-10-22 | Addition of initial 2025 schedule
2024-11-22 | Added Partial upgrade to Rel-18 Dec'24 baseline in iwd-25wk11

## 2025
Version: 22-November-2024
3GPP RAN5 TTCN Delivery Schedule 2025
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk03 |  |  | 2025-01-17 |  | GCF CAG#81 (21-22 Jan)
wk09 |  |  | 2025-02-28 |  | PTCRB PVG#108 (4-6 Mar)
wk11 | 2025-03-14 | 2025-03-10 | 2025-03-14 | TTCN-3 Rel-18 phase2 baseline upgrade | Partial upgrade to Rel-18 Dec'24 baseline for NR+5GC+E-UTRA+LPP
wk17 |  |  | 2025-04-25 |  | GCF CAG#82 (29-30 Apr)
wk19 |  |  | 2025-05-09 |  | PTCRB PVG#109 (13-15 May)
wk24 | 2025-06-13 | 2025-06-09 | 2025-06-13 | TTCN-3
wk29 |  |  | 2025-07-18 |  | GCF CAG#83 (22-23 Jul)
wk32 |  |  | 2025-08-08 |  | PTCRB PVG#110 (12-14 Aug)
wk38 | 2025-09-19 | 2025-09-15 | 2025-09-19 | TTCN-3
wk41 |  |  | 2025-10-10 |  | GCF CAG#84 (14-15 Oct)
wk44 |  |  | 2025-10-31 |  | PTCRB PVG#111 (4-6 Nov)
wk49 | 2025-12-05 | 2025-12-01 |  | TTCN2 (FDD)
wk50 | 2025-12-12 | 2025-12-08 | 2025-12-12 | TTCN-3
3GPP RAN5 TTCN Workshop Schedule 2025
Workshop number | Week number | Date | Type | Place | Comment
#68 | wk05 | 2025-01-30 | eMeeting | online | Thursday
#69 | wk17 | 2025-04-24 | eMeeting | online | Thursday
#70 | wk27 | 2025-07-03 | eMeeting | online | Thursday
#71 | wk43 | 2025-10-21 | eMeeting | online | Tuesday
Notes:
1. One TTCN2 full delivery (FDD) and four TTCN-3 full deliveries / year.
2. Type definitions baseline upgrade required in 2025: None.
Rel-18 Phase2: partial upgrade to Rel-18 Dec'24 baseline for NR+5GC+E-UTRA+LPP due to new/updated ASN.1+tabular IEs required by Rel-18 NR/5GC, NB-IoT & POS test cases.

## 2024
Version: 08-August-2024
3GPP RAN5 TTCN Delivery Schedule 2024
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk03 |  |  | 2024-01-19 |  | GCF CAG#77 (24-25 Jan)
wk09 |  |  | 2024-03-01 |  | PTCRB PVG#104 (5-7 Mar)
wk12 | 2024-03-22 | 2024-03-18 | 2024-03-22 | TTCN-3
wk16 |  |  | 2024-04-19 |  | GCF CAG#78 (23-24 Apr)
wk19 |  |  | 2024-05-10 |  | PTCRB PVG#105 (14-16 May)
wk22 |  |  | 2024-05-31 |  | GCF CAG#78bis (4 Jun)
wk24 | 2024-06-14 | 2024-06-10 | 2024-06-14 | TTCN-3
wk29 |  |  | 2024-07-19 |  | GCF CAG#79 (23-24 Jul)
wk32 | 2024-08-09 | 2024-07-31 |  | TTCN-3 Rel-18 Baseline upgrade | Move to Rel-18 Jun'24 baseline
wk32 |  |  | 2024-08-09 |  | PTCRB PVG#106 (13-15 Aug)
wk37 | 2024-09-13 | 2024-09-09 | 2024-09-13 | TTCN-3
wk41 |  |  | 2024-10-11 |  | GCF CAG#80 (15-16 Oct)
wk44 |  |  | 2024-11-01 |  | PTCRB PVG#107 (5-7 Nov)
wk49 | 2024-12-06 | 2024-12-02 |  | TTCN2 (FDD)
wk50 | 2024-12-13 | 2024-12-09 | 2024-12-13 | TTCN-3
3GPP RAN5 TTCN Workshop Schedule 2024
Workshop number | Week number | Date | Type | Place | Comment
#64 | wk06 | 2024-02-08 | eMeeting | online | Thursday
#65 | wk16 | 2024-04-18 | eMeeting | online | Thursday
#66 | wk27 | 2024-07-04 | eMeeting | online | Thursday
#67 | wk43 | 2024-10-22 | eMeeting | online | Tuesday
Notes:
1. One TTCN2 full delivery (FDD) and five TTCN-3 full deliveries / year.
2. Type definitions baseline upgrade to 3GPP Release 18 required in 2024:
Rel-18 Stage3 freeze declared by 3GPP in March 2024.
Rel-18 ASN.1 freeze declared by 3GPP in June 2024.

## 2023
Version: 20-November-2023
3GPP RAN5 TTCN Delivery Schedule 2023
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk05 |  |  | 2023-02-03 |  | GCF CAG#73 (7-9 Feb)
wk07 |  |  | 2023-02-17 |  | PTCRB PVG#100 (21-23 Feb)
wk12 | 2023-03-24 | 2023-03-20 | 2023-03-24 | TTCN-3
wk16 |  |  | 2023-04-21 |  | GCF CAG#74 (25-28 Apr)
wk19 |  |  | 2023-05-12 |  | PTCRB PVG#101 (16-18 May)
wk24 | 2023-06-16 | 2023-06-12 | 2023-06-16 | TTCN-3
wk29 |  |  | 2023-07-21 |  | GCF CAG#75 (25-27 Jul)
wk32 |  |  | 2023-08-11 |  | PTCRB PVG#102 (15-17 Aug)
wk37 | 2023-09-15 | 2023-09-11 | 2023-09-15 | TTCN-3 Rel-17 phase2 baseline upgrade | Partial upgrade to Rel-17 Jun'23 baseline for NR+5GC+E-UTRA+LPP
wk41 |  |  | 2023-10-13 |  | GCF CAG#76 (17-19 Oct)
wk44 |  |  | 2023-11-03 |  | PTCRB PVG#103 (7-9 Nov)
wk48 | 2023-11-30 | 2023-11-27 |  | TTCN2 (FDD)
wk49 | 2023-12-08 | 2023-12-04 | 2023-12-08 | TTCN-3
3GPP RAN5 TTCN Workshop Schedule 2023
Workshop number | Week number | Date | Type | Place | Comment
#60 | wk05 | 2023-02-02 | eMeeting | online | Thursday
#61 | wk16 | 2023-04-20 | eMeeting | online | Thursday
#62 | wk27 | 2023-07-06 | eMeeting | online | Thursday
#63 | wk43 | 2023-10-24 | eMeeting | online | Tuesday
Notes:
1. One TTCN2 full delivery (FDD only) and four TTCN-3 full deliveries / year.
2. Type definitions baseline upgrade planned in 2023:
Rel-17 Phase2: partial upgrade to Rel-17 Jun'23 baseline for NR+5GC+E-UTRA+LPP due to new/updated ASN.1+tabular IEs required by Rel-17 NR/5GC, NB-IoT & POS test cases.

## 2022
Version: 05-July-2022
3GPP RAN5 TTCN Delivery Schedule 2022
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk04 |  |  | 2022-01-21
wk12 | 2022-03-25 | 2022-03-21 | 2022-03-25 | TTCN-3
wk16 |  |  | 2022-04-14 |  | GCF CAG#70 (19-22 Apr)
wk19 |  |  | 2022-05-06 |  | PTCRB PVG#97 (10-12 May)
wk23 | 2022-06-10 | 2022-06-06 | 2022-06-10 | TTCN-3
wk30 |  |  | 2022-07-22 |  | GCF CAG#71 (26-29 Jul)
wk32 |  |  | 2022-07-22 |  | PTCRB PVG#98 (9-11 Aug)
wk37 | 2022-09-16 | 2022-09-12 | 2022-09-16 | TTCN-3
wk42 |  |  | 2022-10-14 |  | GCF CAG#72 (18-21 Oct)
wk43 | 2022-10-28 | 2022-10-19 | 2022-10-28 | TTCN-3 Rel-17 Baseline upgrade | Move to Rel-17 Sep'22 baseline
wk45 |  |  | 2022-11-04 |  | PTCRB PVG#99 (8-10 Nov)
wk48 | 2022-12-01 | 2022-11-28 |  | TTCN2 (FDD)
wk48 | 2022-12-02 | 2022-11-28 |  | TTCN2 (LCR TDD)
wk49 | 2022-12-09 | 2022-12-05 | 2022-12-09 | TTCN-3
3GPP RAN5 TTCN Workshop Schedule 2022
Workshop number | Week number | Date | Type | Place | Comment
#56 | wk05 | 2022-02-03 | eMeeting | online | Thursday
#57 | wk17 | 2022-04-28 | eMeeting | online | Thursday
#58 | wk27 | 2022-07-06 | eMeeting | online | Wednesday
#59 | wk43 | 2022-10-25 | eMeeting | online | Tuesday
Notes:
1. One TTCN2 full delivery (FDD & TDD) and five TTCN-3 full deliveries / year.
2. Type definitions baseline upgrade to 3GPP Release 17 required in 2022:
Rel-17 Stage3 freeze declared by 3GPP in March 2022.
Rel-17 ASN.1 freeze declared by 3GPP in June 2022.

## 2021
Version: 21-September-2021
3GPP RAN5 TTCN Delivery Schedule 2021
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
wk03 |  |  | 2021-01-22 |  | GCF CAG#65 (26-29 Jan)
wk12 | 2021-03-26 | 2021-03-22 | 2021-03-26 | TTCN-3
wk15 |  |  | 2021-04-16 |  | GCF CAG#66 (20-23 Apr)
wk24 | 2021-06-18 | 2021-06-14 | 2021-06-18 | TTCN-3 Rel-16 phase2 baseline upgrade | Partial upgrade to Rel-16 Mar'21 baseline for NR+5GC
wk28 |  |  | 2021-07-16 |  | GCF CAG#67 (20-23 Jul)
wk37 | 2021-09-17 | 2021-09-13 | 2021-09-17 | TTCN-3
wk40 |  |  | 2021-10-08 |  | GCF CAG#68 (12-15 Oct)
wk49 | 2021-12-10 | 2021-12-06 | 2021-12-10 | TTCN-3 Rel-16 phase3 baseline upgrade | Partial upgrade to Rel-16 Sep'21 baseline for NR
3GPP RAN5 TTCN Workshop Schedule 2021
Workshop number | Week number | Date | Type | Place | Comment
#52 | wk05 | 2021-02-02 | eMeeting | online | Tuesday
#53 | wk17 | 2021-04-27 | eMeeting | online | Tuesday
#54 | wk27 | 2021-07-05 | eMeeting | online | Monday
#55 | wk42 | 2021-10-18 | eMeeting | online | Monday
Notes:
1. Four TTCN-3 full deliveries / year.
2. Type definitions baseline upgrade planned in 2021:
Rel-16 Phase2: partial upgrade to Rel-16 Mar'21 baseline for NR+5GC due to several NBC changes.
Rel-16 Phase3: partial upgrade to Rel-16 Sep'21 baseline for NR due to new NR ASN.1 IEs required by Rel-16 NR/5GC test cases.

## 2020
Version:11-September-2020
3GPP RAN5 TTCN Delivery Schedule 2020
Week | Delivery Date | TTCN CR Cut-Off-Date | Status Report | Type of Delivery | Comment
wk03 |  |  | 2020-01-13 |  | GCF CAG#61 (14th/15th-Jan)
wk11 | 2020-03-13 | 2020-03-09 | 2020-03-13 | TTCN3
wk17 |  |  | 2020-04-17 |  | GCF CAG#62 (20th/23rd-Apr)
wk25 | 2020-06-19 | 2020-06-15 | 2020-06-19 | TTCN3
wk28 |  |  | 2020-07-06 |  | GCF CAG#63 (7th/8th-Jul)
wk38 | 2020-09-18 | 2020-09-14 | 2020-09-18 | TTCN3
wk42 |  |  | 2020-10-12 |  | GCF CAG#64 (13th/14th-Oct)
wk43 | 2020-10-22 | 2020-10-13 | 2020-10-22 | TTCN3 Rel-16 Baseline upgrade | Move to Rel-16 Sep'20 baseline
wk49 | 2020-12-03 | 2020-11-30 |  | TTCN2 (FDD)
wk49 | 2020-12-04 | 2020-11-30 |  | TTCN2 (LCR TDD)
wk50 | 2020-12-11 | 2020-12-07 | 2020-12-11 | TTCN3
3GPP RAN5 TTCN Workshop Schedule 2020
Number | Week | Date | Type | Place | Comment
#48 | wk06 | 2020-02-04 | eMeeting |  | Tuesday
#49 | wk16 | 2020-04-17 | eMeeting |  | Friday
#50 | wk28 | 2020-07-06 | eMeeting |  | Monday
#51 | wk43 | 2020-10-20 | eMeeting |  | Tuesday
1. One TTCN-2 full delivery (FDD & TDD) and five TTCN-3 full deliveries / year.
2. Type definitions baseline upgrade to 3GPP Release 16 required in 2020:
Rel-16 ASN.1 freeze scheduled by 3GPP in June 2020.

## 2019
3GPP RAN5 TTCN Delivery Schedule 2019
Version:21-August-2019
Week | Delivery Date | TTCN CR Cut-Off-Date | Status Report | Type of Delivery | Comment
wk03 |  |  | 2019-01-14 |  | GCF CAG#57 (15th/16th-Jan)
wk05 | 2019-02-01 | 2019-01-28 | 2019-02-01 | TTCN3 Rel-15 Phase4 Baseline upgrade | Special 5GS delivery Partial upgrade to Rel-15 Dec'18 (main drop part2) baseline for NR+LTE+5GC
wk08 |  |  | 2019-02-21 |  | GCF CAG#57bis (21st-Feb)
wk11 | 2019-03-14 | 2019-03-11 |  | TTCN2 (FDD)
wk11 | 2019-03-15 | 2019-03-11 |  | TTCN2 (LCR TDD)
wk12 | 2019-03-22 | 2019-03-18 | 2019-03-22 | TTCN3
wk15 |  |  | 2019-04-08 |  | GCF CAG#58 (9th/10th-Apr)
wk23 | 2019-06-07 | 2019-06-03 | 2019-06-07 | TTCN3 Rel-15 Phase5 Baseline upgrade | Partial upgrade to Rel-15 Mar'19 (main drop part3) baseline for 5GC
wk29 |  |  | 2019-07-15 |  | GCF CAG#59 (16th/17th-Jul)
wk37 | 2019-09-12 | 2019-09-09 |  | TTCN2 (FDD)
wk37 | 2019-09-13 | 2019-09-09 |  | TTCN2 (LCR TDD)
wk38 | 2019-09-20 | 2019-09-16 | 2019-09-20 | TTCN3 Rel-15 Phase6 Baseline upgrade | Partial upgrade to Rel-15 Jun'19 (late drop) baseline for NR+LTE+5GC+LPP
wk43 |  |  | 2019-10-21 |  | GCF CAG#60 (22nd/23rd-Oct)
wk50 | 2019-12-13 | 2019-12-09 | 2019-12-13 | TTCN3
3GPP RAN5 TTCN Workshop Schedule 2019
Number | Week | Date | Type | Place | Comment
#44 | wk06 | 2019-02-07 | eMeeting |  | Thursday
#45 | wk16 | 2019-04-16 | F2F | ETSI, Sophia | Tuesday
#46 | wk27 | 2019-07-02 | eMeeting |  | Tuesday
#47 | wk42 | 2019-10-17 | F2F | ETSI, Sophia | Thursday
1. Two TTCN-2 full deliveries (FDD & TDD) and four TTCN-3 full deliveries / year.
2. Type definitions baseline upgrade to 3GPP Release 15 required in 2019:
Main Drop part2: scheduled by 3GPP in December 2018 for 5GS SA Option 2.
Main Drop part2: scheduled by 3GPP in March 2019 for 5GS SA Option 2.
Late Drop: scheduled by 3GPP in June 2019 for 5GS NSA Options 4 & 7.
3. One special (non-full) TTCN-3 delivery for 5GS.
FFS whether additional special 5GS deliveries will be needed.

## 2018
3GPP RAN5 TTCN Delivery Schedule 2018
Version:21-June-2018
Week | Delivery Date | TTCN CR Cut-Off-Date | Status Report | Type of Delivery | Comment
wk03 |  |  | 2018-01-15 |  | GCF CAG#53 (16th/17th-Jan)
wk11 | 2018-03-15 | 2018-03-12 |  | TTCN2 (FDD)
wk11 | 2018-03-16 | 2018-03-12 |  | TTCN2 (LCR TDD)
wk12 | 2018-03-23 | 2018-03-19 | 2018-03-23 | TTCN3
wk17 |  |  | 2018-04-23 |  | GCF CAG#54 (24th/25th-Apr)
wk18 | 2018-05-04 | 2018-04-27 |  | TTCN3 Rel-15 Phase1 Baseline upgrade | Partial upgrade to Rel-15 Mar'18 baseline for NR+LTE+EPC
wk18 | 2018-05-04 | n/a |  | TTCN3 | Special 5GS delivery
wk24 | 2018-06-15 | 2018-06-11 | 2018-06-15 | TTCN3
wk26 | 2018-06-29 | 2018-06-22 |  | TTCN3 Rel-15 Phase2 Baseline upgrade | Special 5GS delivery Upgrade to Rel-15 Jun'18 baseline for NR+LTE
wk30 |  |  | 2018-07-23 |  | GCF CAG#55 (24th/25th-Jul)
wk36 | 2018-09-06 | 2018-09-03 |  | TTCN2 (FDD)
wk36 | 2018-09-07 | 2018-09-03 |  | TTCN2 (LCR TDD)
wk37 | 2018-09-14 | 2018-09-10 | 2018-09-14 | TTCN3
wk43 |  |  | 2018-10-22 |  | GCF CAG#56 (23rd/24th-Oct)
wk44 | 2018-10-31 | 2018-10-24 |  | TTCN3 Rel-15 Phase3 Baseline upgrade | Full upgrade to Rel-15 Sep'18 baseline
wk44 | 2018-10-31 | n/a |  | TTCN3 | Special 5GS delivery
wk49 | 2018-12-07 | 2018-12-03 | 2018-12-07 | TTCN3
3GPP RAN5 TTCN Workshop Schedule 2018
Number | Week | Date | Type | Place | Comment
#40 | wk06 | 2018-02-08 | eMeeting |  | Thursday
#41 | wk18 | 2018-05-03 | F2F | ETSI, Sophia | Thursday
#42 | wk27 | 2018-07-04 | eMeeting |  | Wednesday
#43 | wk44 | 2018-10-30 | F2F | ETSI, Sophia | Tuesday
1. Two TTCN-2 full deliveries (FDD & TDD) and six TTCN-3 full deliveries / year.
2. Type definitions baseline upgrade to 3GPP Release 15 required in 2018:
Special Rel-15 ASN.1 freeze scheduled by 3GPP in March 2018 for 5GS NSA Option3.
Special Rel-15 ASN.1 freeze scheduled by 3GPP in June 2018 for 5GS NSA Option3.
Full Rel-15 ASN.1 freeze scheduled by 3GPP in September 2018.
3. Three special (non-full) TTCN-3 deliveries for 5GS.

## 2017
3GPP RAN5 TTCN Delivery Schedule 2017
Version:11-April-2017
Week | Delivery Date | TTCN CR Cut-Off-Date | Status Report | Type of Delivery | Comment
wk02 |  |  | 2017-01-16 |  | CAG#49 (17th/18th-Jan)
wk04 | 2017-01-27 | n/a |  | TTCN3 | Special IoT delivery
wk09 | 2017-03-02 | 2017-02-27 |  | TTCN2 (FDD)
wk09 | 2017-03-03 | 2017-02-27 |  | TTCN2 (LCR TDD)
wk10 |  |  | 2017-03-06 |  | CAG#49ter (8th-Mar)
wk10 | 2017-03-10 | 2017-03-06 | 2017-03-06 | TTCN3
wk16 |  |  | 2017-04-21 |  | CAG#50 (25th/26th-Apr)
wk23 | 2017-06-09 | 2017-06-05 | 2017-06-05 | TTCN3
wk30 |  |  | 2017-07-24 |  | CAG#51 (25th/26th-Jul)
wk32 | 2017-08-08 | 2017-07-30 |  | TTCN3 Rel-14 Baseline upgrade | Move to Rel-14 Jun'17 baseline
wk36 | 2017-09-07 | 2017-09-04 |  | TTCN2 (FDD)
wk36 | 2017-09-08 | 2017-09-04 |  | TTCN2 (LCR TDD)
wk37 | 2017-09-15 | 2017-09-11 | 2017-09-11 | TTCN3
wk42 |  |  | 2017-10-20 |  | CAG#52 (24th/25th-Oct)
wk51 | 2017-12-22 | 2017-12-18 | 2017-12-18 | TTCN3
3GPP RAN5 TTCN Workshop Schedule 2017
Number | Week | Date | Type | Place | Comment
#36 | wk04 | 2017-01-25 | eMeeting |  | Wednesday
#37 | wk15 | 2017-04-11 | F2F | ETSI, Sophia | Thursday
#38 | wk27 | 2017-07-05 | eMeeting |  | Wednesday
#39 | wk42 | 2017-10-19 | F2F | ETSI, Sophia | Thursday
1. Two TTCN-2 full deliveries (FDD & TDD) and five TTCN-3 full deliveries / year.
2. Type definitions baseline upgrade to 3GPP Release 14 required in 2017:
Rel-14 ASN.1 freeze scheduled by 3GPP in June 2017.
3. One special (non-full) TTCN-3 delivery for IoT (eMTC, NB-IoT).

## 2016
3GPP RAN5 TTCN Delivery Schedule 2016
Version:26-October-2016
Week | Delivery Date | TTCN CR Cut-Off-Date | Status Report | Type of Delivery | Comment
wk03 |  |  | 2015-01-22 |  | CAG#45 (26th/27th-Jan)
wk09 | 2016-03-03 | 2016-02-29 |  | TTCN2 (FDD)
wk09 | 2016-03-04 | 2016-02-29 |  | TTCN2 (LCR TDD)
wk10 | 2016-03-11 | 2016-03-07 | 2016-03-07 | TTCN3
wk16 |  |  | 2016-04-22 |  | CAG#46 (26th/27th-Apr)
wk24 | 2016-06-17 | 2016-06-13 | 2016-06-13 | TTCN3 | CAG#47 10DR: 13th-Jun
wk25 |  |  | 2016-06-24 |  | CAG#47 (28th/29th-Jun)
wk32 | 2016-08-09 | 2016-07-31 |  | TTCN3 Rel-13 Baseline upgrade | Move to Rel-13 Jun'16 baseline
wk36 | 2016-09-08 | 2016-09-05 |  | TTCN2 (FDD)
wk36 | 2016-09-09 | 2016-09-05 |  | TTCN2 (LCR TDD)
wk37 | 2016-09-16 | 2016-09-12 | 2016-09-12 | TTCN3
wk41 |  |  | 2016-10-14 |  | CAG#48 (18th/19th-Oct)
wk44 | 2016-11-04 | n/a |  | TTCN3 | Special IoT delivery
wk49 | 2016-12-09 | 2016-12-05 | 2016-12-05 | TTCN3
3GPP RAN5 TTCN Workshop Schedule 2016
Number | Week | Date | Type | Place | Comment
#32 | wk03 | 2016-01-21 | eMeeting |  | Thursday
#33 | wk15 | 14th April | F2F | ETSI, Sophia | Thursday
#34 | wk27 | 7th July | eMeeting |  | Thursday
Iot#1 | wk39 | 27th September | eMeeting |  | Tuesday
#35 | wk44 | 2nd November | F2F | ETSI, Sophia | Wednesday
1. Two TTCN-2 full deliveries (FDD & TDD) and five TTCN-3 full deliveries / year.
2. Type definitions baseline upgrade to 3GPP Release 13 required in 2016:
Rel-13 ASN.1 freeze scheduled by 3GPP in March 2016, except for NB-IOT scheduled in June 2016.
3. One special (non-full) TTCN-3 delivery for IoT (eDRX, eMTC, NB-IoT).

## 2015
TTCN Delivery Schedule 2015
Version: 06-July-2015
Week | Delivery date | CR Cut-Off-date | Status Report | Type of delivery | Comment
wk04 |  |  | 2015-01-23 |  | CAG#41 (27th/28th-Jan)
wk09 | 2015-02-26 | 2015-02-23 |  | TTCN2 (FDD)
wk10 | 2015-03-05 | 2015-03-02 |  | TTCN2 (LCR TDD)
wk10 | 2015-03-06 | 2015-03-02 | 2015-03-02 | TTCN3
wk16 |  |  | 2015-04-17 |  | CAG#42 (21th/22nd-Apr)
wk18 | 2015-04-28 | 2015-04-20 |  | TTCN3 Baseline upgrade | Move to Rel-12 Mar'15 baseline
wk25 | 2015-06-19 | 2015-06-15 | 2015-06-15 | TTCN3
wk27 |  |  | 2015-07-03 |  | CAG#43 (7th/8th-Jul)
wk37 | 2015-09-10 | 2015-09-07 |  | TTCN2 (FDD)
wk38 | 2015-09-17 | 2015-09-14 |  | TTCN2 (LCR TDD)
wk38 | 2015-09-18 | 2015-09-14 | 2015-09-14 | TTCN3
wk43 |  |  | 2015-10-23 |  | CAG#44 (27th/28th-Oct)
wk50 | 2015-12-11 | 2015-12-07 | 2015-12-07 | TTCN3
TTCN Workshop Schedule 2015
Number | Week | Date | Type | Place | Comment
#28 | wk03 | 2015-01-15 | eMeeting |  | Thursday
#29 | wk15 | 2015-04-10 | F2F | ETSI, Sophia | Friday
#30 | wk27 | 2015-07-03 | eMeeting |  | Friday
#31 | wk42 | 15/16-Oct | F2F | ETSI, Sophia | Thirsday PM / Friday AM
1. Two TTCN-2 full deliveries and five TTCN-3 full deliveries / year.
2. Type definitions baseline upgrade to 3GPP Release 12 required in 2015:
Rel-12 ASN.1 freeze scheduled by 3GPP in March 2015.

## 2014
TTCN Delivery Schedule 2014
Version: 27-May-2014
Week | Delivery date | CR Cut-Off-date | Status-Report | Type of deliveries | Comment
wk09 | 2014-02-27 | 2014-02-24 | 2014-02-28 | TTCN2 (FDD)
wk10 | 2014-03-06 | 2014-03-03 |  | TTCN2 (LCR TDD)
wk10 | 2014-03-07 | 2014-03-03 |  | TTCN3
wk23 |  |  | 2014-06-06
wk24 | 2014-06-11 | 2014-06-02 |  | TTCN3
wk27 |  |  | 2014-07-04
wk36 | 2012-09-04 | 2012-09-01 | 2014-09-05 | TTCN2 (FDD)
wk37 | 2012-09-11 | 2012-09-08 |  | TTCN2 (LCR TDD)
wk37 | 2014-09-12 | 2014-09-08 |  | TTCN3
wk41 |  |  | 2014-10-10
wk49 | 2014-12-05 | 2014-12-01 | 2014-12-05 | TTCN3
TTCN workshop Schedule 2014
Number | Week | Date | Type | Place | Comment
#24 | wk03 | 2014-01-16 | eMeeting
#25 | wk14 | 2014-04-03 | F2F | Sophia
#26 | wk27 | 2014-07-03 | eMeeting
#27 | wk43 | 2014-09-30 | F2F | Sophia
1. Two TTCN-2 full delieveries and four TTCN-3 full deliveries / year.
2. 3GPP Release baseline upgrade is not foreseen in 2014.

## 2013
Delivery Schedule 2013
Version: 18-Sept-2012
Week | Delivery date | CR Cut-Off-date | Status-Report | Type of deliveries | Comment
wk03 |  |  | 2013-01-18
wk07 | 2013-02-14 | 2013-02-11 | 2013-02-21 | TTCN2 | Baseline March-12 frozen
wk08 | 2013-02-22 | 2013-02-18 |  | TTCN3
wk15 | 2013-04-12 | 2013-04-08 |  | TTCN3 | Baseline March-13 in Rel-11
wk16 |  |  | 2013-04-19
wk23 | 2013-06-06 | 2013-06-03 | 2013-06-06 | TTCN2
wk24 | 2013-06-14 | 2013-06-10 |  | TTCN3
wk25 |  |  | 2012-06-21
wk34 | 2012-08-22 | 2013-08-19 |  | TTCN2
wk35 | 2013-08-30 | 2013-08-26 | 2013-08-29 | TTCN3
wk40 |  |  | 2012-10-04
wk43 | 2013-10-25 | 2013-10-21 |  | TTCN3
wk48 | 2013-11-28 | 2013-11-25 | 2012-11-28 | TTCN2
wk49 | 2013-12-06 | 2013-12-02 |  | TTCN3

## 2012
Delivery Schedule 2012
Version: 14-Feb-2012
Week | Delivery date | CR Cut-Off-date | Status-Report | Type of deliveries provided | Comment
wk05 | 2012-02-03 | 2012-01-30 | 2011-01-27 | EUTRA, IMS, UE positioning | 1300 CET
wk08 | 2012-02-23 | 2012-02-20 | 2011-02-24 | UTRA FDD
wk09 | 2012-03-02 | 2011-02-27 |  | EUTRA, IMS, UE positioning, LCR TDD | 1300 CET
wk16 | 2012-04-19 | 2012-04-16 |  | UTRA FDD | Baseline March-12 in Rel-10
wk17 | 2012-04-27 | 2012-04-23 | 2011-04-13 | EUTRA, IMS, UE positioning, LCR TDD | Baseline March-12 in Rel-10
wk23 | 2012-06-07 | 2012-06-04 | 2011-06-08 | UTRA FDD
wk24 | 2012-06-15 | 2011-06-11 |  | EUTRA, IMS, UE positioning, LCR TDD | 1300 CET
wk35 | 30_Aug | 2012-08-27 | 2011-08-31 | UTRA FDD
wk36 | 2012-09-07 | 2012-09-03 |  | EUTRA, IMS, UE positioning, LCR TDD | 1300 CET
wk42 | 2012-10-19 | 2012-10-15 |  | EUTRA, IMS, UE positioning | 1300 CET
wk47 | 2011-11-22 | 2012-11-19 |  | UTRA FDD
wk48 | 2012-11-30 | 2012-11-26 | 2011-11-30 | EUTRA, IMS, UE positioning, LCR TDD | 1300 CET

## 2011
TTCN Delivery Schedule 2011
Version: 11-March-2011
Week | Delivery date | CR Cut-Off-date | Type of deliveries provided | Comment
wk03 | 2011-01-22 |  | Report
wk04 | 2011-01-28 | 2011-01-24 | LTE
wk07 | 2011-02-18 |  | Report
wk10 | 2011-03-10 | 2011-03-07 | UTRA DfM
wk10 | 2011-03-11 |  | Report
wk11 | 2011-03-17 | 2011-03-14 | LCR_TDD
wk11 | 2011-03-18 | 2011-03-14 | LTE
wk13 | 2011-04-01 |  | Report
wk15 | 2011-04-15 | 2011-04-08 | LTE | Base line move
wk16 | 2011-04-19 | 2011-04-13 | UTRA DfM | Base line move
wk16 | 2011-04-21 | 2011-04-13 | LCR_TDD | Base line move
wk18 | 2011-05-06 |  | Report
wk21 | 2011-05-26 | 2011-05-23 | UTRA DfM
wk22 | 2011-06-01 |  | Report
wk22 | 2011-06-02 | 2011-05-30 | LCR_TDD
wk23 | 2011-06-01 | 2011-05-25 | LTE
wk26 | 2011-07-02 |  | Report
wk27 | 2011-07-08 | 2011-07-04 | LTE
wk33 | 2011-08-19 |  | Report
wk36 | 2011-09-08 | 2011-09-05 | UTRA DfM
wk36 | 2011-09-09 |  | Report
wk37 | 2011-09-16 | 2011-09-12 | LCR_TDD
wk37 | 2011-09-16 | 2011-09-12 | LTE
wk41 | 2011-10-15 |  | Report
wk42 | 2011-10-21 | 2011-10-17 | LTE
wk45 | 2011-11-11 |  | Report
wk48 | 2011-12-01 | 2011-11-28 | UTRA DfM
wk48 | 2011-12-02 |  | Report
wk49 | 2011-12-08 | 2011-12-05 | LCR_TDD
wk49 | 2011-12-09 | 2011-12-05 | LTE

## 2010
Delivery Schedule 2010
Version: 12-October-2010
Week | Delivery date | CR Cut-Off-date | Status-Report | Type of deliveries provided | Comment
wk03 | 2010-01-22 | 2010-01-18 | yes | LTE
wk04 | 2010-01-28 | 2010-01-25 |  | UTRA DfV
wk07 | 2010-02-19 | 2010-02-15 | yes | LTE
wk10 | 2010-03-11 | 2010-03-08 | yes | UTRA DfM
wk11 | 18-Mar 19-Mar | 2010-03-15 |  | LCR_TDD LTE Formal
wk15 | 2010-04-16 |  | yes
wk16 | 2010-04-22 | 2010-04-19 |  | UTRA DfM | Base line move
wk17 | 2010-04-30 | 2010-04-26 |  | LTE | Base line move
wk21 | 2010-05-28 | 2010-05-24 | yes | UTRA DfM
wk22 | 03-Jun 04-Jun | 2010-05-31 |  | LCR_TDD LTE Formal
wk26 | 2010-07-02 | 2010-06-28 | yes | LTE
wk27 | cancelled | cancelled |  | UTRA DfV
wk33 | 2010-08-20 | 2010-08-16 | yes | LTE
wk36 | 2010-09-09 | 2010-09-06 | yes | UTRA DfM
wk37 | 16-Sep 17-Sep | 2010-09-13 |  | LCR_TDD LTE Formal
wk42 | 2010-10-22 | 2010-10-18 | yes | LTE
wk43 | 2010-10-28 | 2010-10-25 |  | UTRA DfV
wk45 | 2010-11-12 |  | yes
wk48 | 2010-12-03 | 2010-11-29 |  | UTRA DfM
wk49 | 09-Dec 10-Dec | 2010-12-06 | yes | LCR_TDD LTE
wk50 | 2010-12-17 | 2010-12-13 |  | Formal