## Slide 1: SA2 Rel-19 planning considerations
Andy Bennett
SA2 Chair
TSG SA Meeting #102 SP-231511
December 11 – 15, 2023

## Slide 2: Rel-19 planning for SA2
Previous guidance regarding planning the Rel-19 content for SA2 stated
  The Max number of TUs available for Rel-19 SIs/WIs is estimated to be = 134 TUs
  Should limit to 14 TUs available for any SI/WI.
    Note: TU estimates is for the whole work done in Rel-19 (i.e. SID only, WID only, or SID + WID together).
  The recommended maximum number of Rel-19 SIs/WIs = 10 - 14 SIDs/WIDs
This was based on the following plan, assuming 8 ordinary SA2 meetings until Rel-19 Stage 2 freeze
5 Study Items were approved in SA#101 to start work in Q4 2023, and time was allocated to them (9.25 TU’s) in October and November
In addition time was required in Q4 to discuss the remaining candidate WIDs/SIDs (online discussion and drafting sessions)
 | Oct, 23 | Nov, 23 | Feb, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24 | 
 | #159 | #160 | #161 | #162 | #163 | #164 | #165 | #166 | 
Rel-19 |  |  |  |  |  |  |  |  | 
Planned | 9 | 9 | 14 | 18 | 20 | 20 | 22 | 22 | 134

## Slide 3: Rel-19 planning for SA2
So the actual TU’s used so far is as follows
Of the 10 TU’s used in the October meeting, 4 were allocated to approved SIDs, the others were for candidate SID discussions
So we have consumed 9.25 TU’s out of a planned 18 TU’s
 | Oct, 23 | Nov, 23 | Feb, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24 | 
 | #159 | #160 | #161 | #162 | #163 | #164 | #165 | #166 | 
Rel-19 |  |  |  |  |  |  |  |  | 
Planned | 9 | 9 | 14 | 18 | 20 | 20 | 22 | 22 | 134
Actual | 10 | 5.25 |  |  |  |  |  |  | 

## Slide 4: Rel-19 planning for SA2
Over the same period the plan for topics other than Rel-19 is as shown right
Rel-18 maintenance input paper numbers remain high, but difficult to forecast
Pre-Rel-18 maintenance will continue to consume the planned TU’s
 | Aug, 23 | Oct, 23 | Nov, 23 | Feb, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24
 | #158 | #159 | #160 | #161 | #162 | #163 | #164 | #165 | #166
Total (for planning purposes) | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Pre-Rel-18 maintenance |  |  |  |  |  |  |  |  | 
Planned | 4 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2
Actual | 5 | 3 | 2.9 |  |  |  |  |  | 
Rel-18 Maintenance |  |  |  |  |  |  |  |  | 
Planned | 20 | 18 | 18 | 14 | 10 | 8 | 8 | 6 | 6
Actual | 22 | 22 | 20.6 |  |  |  |  |  | 
Buffer (TEI19, overflow, other) |  |  |  |  |  |  |  |  | 
Planned | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Actual | 0 | 1 | 6 |  |  |  |  |  | 
Total of Maintenance + Buffer |  |  |  |  |  |  |  |  | 
Planned | 30 | 27 | 27 | 22 | 18 | 16 | 16 | 14 | 14
Actual | 27 | 26 | 29.5 |  |  |  |  |  | 
Rel-19 |  |  |  |  |  |  |  |  | 
Planned | 6 | 9 | 9 | 14 | 18 | 20 | 20 | 22 | 22
Actual | 9 | 10 | 5.25 |  |  |  |  |  | 

## Slide 5: Rel-19 planning for SA2
We have an ad hoc e-meeting in January where TU’s will be allocated to Rel-19 (as well as to the other topics)
These TU’s are excluded from consideration when planning the release, but should allow additional progress for the 5 SA#101-approved study items and provide a good start to those approved in SA#102
If necessary some consumption of the buffer TU’s over the next 6 meetings so it is still reasonable to use 134 as the number of TU’s for release planning purposes
 | Oct, 23 | Nov, 23 | Jan, 24 | Feb, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24 | 
 | #159 | #160 | #160AH | #161 | #162 | #163 | #164 | #165 | #166 | 
Rel-19 |  |  |  |  |  |  |  |  |  | 
Planned | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22 | 134 (excluding Jan AH)