## Slide 1: Evaluations on ISAC_ARC Timeline
Sherry Shen (Moderator)
SP-231583

## Slide 2: Background
All the WTs are technically stable and in a good shape.
Major open issues
  Due to RAN dependency, especially the demand of channel modeling study for sensing, the time schedule of the SA2 SID has to be based on RAN coordination
  Whether and how to document normative work in the SID
Since the start of 5G work in 3GPP, 2 channel modeling studies have been identified
  5G NR
  Physical Layer Enhancements for NR URLLC
This DP attempts to evaluate the time schedule of the stage 2 work for ISAC by referring to how the timelines of “5G NR” and “Physical Layer Enhancements for NR URLLC” were managed.

## Slide 3: 5G NR Timeline
Q4/2015
RAN Rel-14
RAN
SA2
Study on New Radio (NR) Access Technology
Study on channel model for frequency spectrum above 6 GHz
SA2 Rel-14
SA2 Rel-15
SA2 aspects on Study on Architecture and Security for next Generation System
Stage 2 of 5G System - Phase 1
Core part: New Radio Access Technology
Q1/2016
Q2/2016
Q3/2016
Q4/2016
Q1/2017
Q2/2017
Q3/2017
Q4/2017
Q1/2018
Q2/2018
Q3/2018
Q4/2018
RAN Rel-15
Observations:
RAN Channel model study can be completed within 3Q
RAN technical study can take place earlier than the completion of channel model study
SA2 technical study can take place earlier than RAN technical study (1Q after the start of RAN channel model study)
SA2 technical study can be completed earlier than RAN technical study
SA2 technical study and technical specification can be spread over 2 releases

## Slide 4: 5G_URLLC timeline
Q3/2018
RAN Rel-16
RAN
SA2
Q4/2018
Q1/2019
Q2/2019
Q3/2019
Q4/2019
Q1/2020
Q2/2020
Study on channel modeling for indoor industrial scenarios
Study on physical layer enhancements for NR UR Low Latency Cases
Q2/2018
SA2 Rel-16
SA2 Rel-17
Study on enhancement of URLLC supporting in 5GC
Stage 2 of 5G_URLLC
Core part: Physical Layer Enhancements for NR URLLC
Observations:
RAN Channel model study can be completed within 4Q
RAN technical study can take place earlier than the channel model study
SA2 technical study can take place earlier than RAN channel model study and technical study
SA2 technical study can be completed earlier than RAN technical study
SA2 technical study and technical specification can be completed within 1 release

## Slide 5: ISAC status in RAN prior to RAN#102
Observations:
RAN ISAC Channel model study will start from Q2 of 2024 for 15 months
It will be checked in Sep. of 2024 to determine if additional study beyond channel model can be considered

## Slide 6: Proposed FS_ISAC_ARC timeline (Option 1)
Q1/2024
RAN Rel-19
RAN
SA2
ISAC use case selection
Q2/2024
Q3/2024
Q4/2024
Q1/2025
RAN Rel-20
Q2/2025
Q3/2025
Q4/2025
RAN 1 Channel Modelling
Technical Study
Q4/2023
FS_ISAC_ARC study
SA2 Rel-19
SA2 Rel-20
Normative Phase
ISAC_ARC normative work
9 TU
4 TU
Assuming TR work will start from Sep of 2024
1Q earlier completion than the RAN technical study

## Slide 7: Proposed FS_ISAC_ARC timeline (Option 2)
Q1/2024
RAN Rel-19
RAN
SA2
ISAC use case selection
Q2/2024
Q3/2024
Q4/2024
Q1/2025
RAN Rel-20
Q2/2025
Q3/2025
Q4/2025
RAN 1 Channel Modelling
Technical Study
Q4/2023
FS_ISAC_ARC study
SA2 Rel-19
SA2 Rel-20
Normative Phase
ISAC_ARC normative work
7 TU
6 TU
Assuming TR work will start from Dec of 2024
1Q earlier completion than the RAN technical study

## Slide 8: Proposed FS_ISAC_ARC timeline (Option 3)
Q1/2024
RAN Rel-19
RAN
SA2
ISAC use case selection
Q2/2024
Q3/2024
Q4/2024
Q1/2025
RAN Rel-20
Q2/2025
Q3/2025
Q4/2025
RAN 1 Channel Modelling
Technical Study
Q4/2023
FS_ISAC_ARC study
SA2 Rel-19
SA2 Rel-20
Normative Phase
ISAC_ARC normative work
11 TU (reducing WT-5)
2 TU
9 TU
Assuming TR work will start from Sep of 2024
Assuming TS work will start from Dec of 2024
1Q earlier start than the RAN normative work

## Slide 9: Proposed way fwd
It is proposed to adopt Option 1: 9 TUs in R19 for the study
  Since at most 2 TUs are assigned for one topic per meeting, the 9 TUs can be spread over 7 meetings in 2024
Example | SA2#160 Ad hoc-e | SA2#161 | SA2#162 | SA2#163 | SA2#164 | SA2#165 | SA2#166
Example A | 1 | 1 | 1 | 1 | 1 | 2 | 2
Example B | 0 | 1 | 1 | 1 | 2 | 2 | 2
Example C | 0 | 0 | 1 | 2 | 2 | 2 | 2
TU allocation examples