## Slide 1: Views on 6G timeline planning in 3GPP
3GPP TSG SA Meeting #102
Edinburgh, Scotland, December 11-15, 2023
Agenda Item: 7.4
Source: Xiaomi
Document for: Discussion
SP-231584

## Slide 2: Introduction
In TSG#101, an LS from ITU-R WP 5D was sent to 3GPP (RP-231518, SP-230790) informing the completion of IMT-2030 Framework
During TSG#102, a joint CT/RAN/SA session is planned focusing on 6G time line and REL-19 coordination
Like for previous generations, 3GPP shall submit a candidate technology for IMT 2030
    Planning in 3GPP for the submission to IMT 2030 would be necessary
In this contribution, our view on “6G” timeline in 3GPP is provided

## Slide 3: Views on Timeline
 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Technical performance requirement
Evaluation criteria & performance
Requirements, evaluation criteria, and submission template
Circular letter (and later addenda)
workshop
Technology proposals
Evaluation
Consensus building
Outcome & decision
“IMT 2030” specifications
ITU
ASN.1 freezing
6G SA1 SI
6G SA1 WI
6G SA2 SI
6G SA2 WI
6G CT Stage 3 WI
5GA SA1 SI
SA1: Rel-20 (24 months)
SA1: Rel-21 (12 months)
5GA SA2 SI
SA2: Rel-20 (27 months)
SA2: Rel-21 (15 months)
5GA CT Stage 3 WI
CT: Rel-21 (21 months)
CT: Rel-20 (18 months)
5GA SA1 WI
5GA SA2 WI

## Slide 4: Proposals
3GPP SA shall start the 6G work from Rel-20
    SA1 study on 6G requirements in Rel-20
        15 months of study starting from Q1 2025 after the completion of 5G-A study
    SA2 study on 6G architecture in Rel-20
        15 months of study starting from Q1 2026 after the completion of 5G-A study
        Equal length of study phase and normative phase to allow sufficient time to stabilize normative features and to avoid maintanance work load
6G normative work starts in R21 and first 6G specification ready in R21
    Stage 1 normative work completion: Q1 2027
    Stage 2 normative work completion: Q2 2028
    Stage 3 normative work completion: Q2 2029