## Slide 1
3GPP Work Plan
Review at Plenary #102
Source: MCC / Work Plan Manager (A. Sultan)
Agenda item: Review of the Work Plan
Document for: Information
Review based on the latest available version of the Work Plan, available at: https://ftp.3gpp.org/Information/WORK_PLAN
Includes: - the progress on all WIDs, as indicated in the WG Chairs’ reports (CT & SA) and in the Status Report (RAN), - the new WIDs proposed by SA/CT WGs to TSG#102 (subject to removal if not TSG-approved)
Does not include: - the company-proposed WIDs approved at TSG#102
Warnings :
- This review is a high-level view of the 3GPP progress. It is based on the 3GPP Work Plan, a continuously updated document.
Some misalignments might temporarily appear on some individual items.
- Some WG cannot progress because of reasons beyond their control (e.g. dependencies with other groups).
These slides shall not be used to judge the “efficiency” of whatever WG.
© 3GPP 2023
RP-232718 / CP-233012 / SP-231618 - 3GPP TSG#101, 11 -15 December 2023, Edinburgh, Scotland, UK

## Slide 2: Content of this Work Plan review
Snapshot of all ongoing Releases
Ongoing Releases
  Rel-18 Timeline and Progress
  Rel-19 Timeline and Progress
  Rel-20 initial talks
Background information

## Slide 3
Ongoing Release timelines
#96
Release 19
Release 18
Note: All starting dates are indicative
#98e
#100
#102
#104
#106
#108
#110
#112
#114
2022
2023
2025
*: +3 months for RAN4
**: - 3 months for RAN1 & + 3 months for RAN4 perf
SA1 Stage 1
Stage 3 (CT & SA)
Stage 2 Normative
RAN Content def.*
RAN Completion**
Maint.*
ASN.1 & Open APIs
ASN.1
1st review
#99
#101
#103
#107
#109
#111
#113
2024
2026
SA1 Stage 1
RAN Completion**
Stage 3 (CT & SA)
ASN.1 & Open APIs
Stage 2 Normative
#105
#97-e
RAN Content Def*
SA St.2 Content Def
2021
#92-e
#94-e
#95-e
#93-e
Mar.
#91-e
TSGs
Mar.
Mar.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
Dec.
Dec.
Dec.
Now

## Slide 4: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 initial talks
Background information

## Slide 5
Release 18 timeline
#93-e
SA1 Stage 1 100%
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN4
content def.
Release 18
Note: All starting dates are indicative
#94-e
#95-e
#96
#97-e
#98-e
#99
#100
#101
#102
#103
#104
#105
RAN Content def.
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2024
Now
Maint.
Maint.
ASN.1 & Open APIs
ASN.1
1st review
TSGs
2021
RAN Completion (RAN2/3/4core)

## Slide 6: Release 18 Progress: Stages 1 & 2
Stage 1 and TSG content definition:
  Completed since TSG#94
  SA1 has 25 normative items plus 14 studies.
Stage 2 at SA2 and SA6:
  Studies :
    Completed since TSG#99
    SA2 and SA6 have 43 studies
  Normative :
    Completed since TSG#100, except for EDGEAPP_EXT (UID 960011, SA6, from 65% to 95%)
    SA2 and SA6 have 57 normative items

## Slide 7: Release 18 Progress: Stage 3 (SA/CT)
Stage 3 (CT WGs) and SA3, SA4 and SA5*: In progress.
  Studies:
    75 studies for all these WGs
    OCI (St.3 Studies) = 92% - against 84% at previous TSG
  Normative:
    239 items for all these WGs
    OCI (St.3 Norm) = 78% - against 65% at previous TSG
    Still 31 items below 50%, including:
      SA5 and CT6 aspects of 5GSATB
      CT4&6 aspects of PLMNsel
      CT1,3&4 aspects of NSCALE
      CT1&3 aspects of ADAES
    Reminder: deadline is next March meeting
OCI = Overall Completion Index =sum of all % completion divided by the number of items
*Note: For tools limitation reasons, SA3, SA4 and SA5 are reported in this slide, even if they may cover several Stages

## Slide 8: Release 18 Progress: Stage 3 (RAN)
Stage 3 in RAN: (reminder: new WIDs/SIDs approved at RAN#102 not considered here)
  RAN studies (17 items): OCI: 95% - against 85% at previous RAN
  RAN Core aspects: OCI: 88% - against 73% at previous RAN
    RAN1 Core (after “maintenance”): 8 items 100% complete, one at 99%
    RAN2 Core: 9 items 100% complete, two at 95%
    RAN 3 Core: 6 items 100% complete, one at 80%
    RAN4 Core: OCI: 84% (67 items)
  RAN Perf aspects: OCI: 55% - against 35% at previous RAN
    RAN1 Perf (after “maintenance”): 31 % (7 items)
    RAN2 Perf: 10 % (4 items)
    RAN3 Perf: 20% (1 item)
    RAN4 Perf: OCI: 61 % (60 items)
  RAN5 testing: OCI: 31% (10 items)
OCI = Overall Completion Index =sum of all % completion divided by the number of items
  RAN#102: RAN completion “nearing achievement”, now starting the “maintenance phase” for RAN2/3/4Core until March 2024

## Slide 9: Release 18 recap – text version
Release 18 Freezes and other milestones, sorted by dates :
  Sept 2021 (TSG#93): Stage 1: 80% normative work; SA Workshop; joint SA/RAN/CT meeting
  Dec 2021 (TSG#94):
    Stage 1: 100% normative work
    RAN/SA/CT joint meeting on Rel-18 content; SA2 Work Items prioritization; RAN Content Definition
  Mar 2022 (TSG#95): RAN4-lead WIDs specified
  June 2022 (#96) till March 2023 (#99): no specific deadline
  June 2023 (TSG#100): Stage 2 Functional work (SA2 and SA6) Freeze
  Sep 2023 (TSG#101):
    RAN1 freeze (before maintenance)
    Freeze for SA3 (stages 2 & 3) – maintenance to continue
  Dec 2023 (TSG#102):
    RAN1 freeze (after maintenance)
    RAN2, RAN3, RAN4Core freeze (before maintenance)
  Mar 2024 (TSG#103):
    RAN2, RAN3, RAN4Core freeze maintenance
    Stage 3 (all CT WGs; SA WGs involved with Stage 3) freeze
    (also first review of ASN.1)
  June 2024 (TSG#104):
    RAN4Perf freeze
    “coding freeze”. Freeze of:ASN-1; Open APIs
Now

## Slide 10: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 initial talks
Background information

## Slide 11
Release 19 timeline
#101
Note: All starting dates are indicative
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop

## Slide 12: Release 19 progress overview
Stage 1 (SA1):
  Studies :
    14 studies – stable for long
    All studies completed (against 94% at previous TSG)
      Except for FS_ISN, exception request submitted
  Normative :
    24 tasks, including “miniWIDs” - one new miniWID at SA#102
    All normative completed (against 92 %) except for:
      Stage 1 of Ambient power-enabled Internet of Things: 95%
      The new miniWID (Timestamp for critical IoT Applications): 0%
    See next slide on Rel-19 content
Stage 2 & 3:
  Studies :
    30 studies from SA3, SA5 and SA6 – against 4 at TSG#101
    Studies from SA2 to be discussed/approved directly at SA#102 as part of Content Definition process
  Normative :
    20 normative – against 8 at TSG#101
  OCI not really relevant (neither for studies nor for normative) since items are being introduced

## Slide 13: Release 19 Content
Unique_ID | Name | Acronym | Hyperlink
1000026 | Integrated Sensing and Communication | Sensing | SP-230750
1010024 | Ambient power-enabled Internet of Things | AmbientIoT | SP-231016
1000028 | Localized Mobile Metaverse Services | Metaverse | SP-230509
1000029 | Indirect Network Sharing | NetShare | SP-230511
1000031 | FRMCS Phase 5 | FRMCS_Ph5 | SP-230512
1000030 | AI/ML Model Transfer Phase 2 | AIML_MT_Ph2 | SP-230514
1000024 | Satellite access Phase 3 | 5GSAT_Ph3 | SP-230516
1000032 | Uncrewed Aerial System Phase 3 | UAS_Ph3 | SP-230518
1010008 | Application Architecture for UAS applications Phase 3 | UASAPP_Ph3 | SP-230991
1010023 | Upper layer traffic steering, switching and splitting over dual 3GPP access | DualSteer | SP-231032
1000033 | Energy Efficiency as Service Criteria | EnergyServ | SP-230520
990051 | Roaming Value-Added Services | RVAS | SP-230231
Stage 1 content (stable):
Stage 2 content:
Full list of SA1 normative WIDs (excluding miniWIDs):
“TSG content definition” taking place over TSG#101 and 102
Resulting WIDs to be integrated in the Work Plan after TSG#102

## Slide 14: Release 19 recap - text version
Release 19 Freezes and other milestones, sorted by dates :
  June 2023: RAN workshop on Rel-19 content, SA workshop on Rel-19 content
  Sept 2023 (TSG#101):
    Stage 1: 80% normative work
    Approve 1st part of SA Stage 2 package (SA/CT)
  Dec 2023 (TSG#102):
    Stage 1: 100% normative work
    RAN1/2/3 Content Definition
    Approve final package of SA Stage 2 with RAN/CT
  Mar 2024 (TSG#103): RAN4 Content Definition
  Dec 2024 (TSG#106): Stage 2 Functional work (SA2 and SA6) Freeze (working assumption)
  June 2025 (TSG#108): RAN1 freeze
  Sept 2025 (TSG#109):
    RAN2, RAN3, RAN4Core freeze
    Stage 3 (all CT WGs; SA WGs involved with Stage 3) freeze (working assumption)
  Dec 2025 (TSG#110):
    RAN4Perf freeze
    “coding freeze”. Freeze of:ASN-1; Open APIs (working assumption)
Now

## Slide 15: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 initial talks
Background information

## Slide 16: Release 20 initial talks
Initial talks/decisions taking place in SA1 about Rel-20:
  Studies:
    All SA1 Rel-20 SIDs to be presented between Nov. 2023 and Aug. 2024
    All SA1 Rel-20 SIDs to be approved by Sept. 2024
    The SA1 SIDs are exceptionally divided in two Parts:
      Part 1 (“full 5GA”): the Rel-20 SIDs for which corresponding normative work is anticipated to also belong to Rel-20
      Part 2 (“5GA and beyond”): the Rel-20 SIDs for which corresponding normative work is anticipated to be after Rel-20. See also SA1 Chair’s presentation in SP-231619 about a possible workshop in May 2024 to start gathering views on after Rel-20.
  Normative:
    No decision yet about Rel-20 Stage 1 normative work timeline
    Nor for any other Rel-20 activity in the other WGs/TSGs

## Slide 17: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 initial talks
Background information

## Slide 18: Background information
Dedicated e-mail list for Work Plan aspects
Open to everyone interested (rapporteus, chairs, delegates, etc.) by sending the message “Subscribe 3GPP_WORKPLAN” to the address LISTSERV@LIST.ETSI.ORG
For comments/update to the Work Plan, please use the 3GPP_WORKPLAN list
3GPP Work Plan
http://www.3gpp.org/ftp/Information/WORK_PLAN
Contains Release 1999 to Release 19; Master version in MS Project; Working versions in Excel
NEW: Tutorials on content, maintenance, etc. in subfolder \info
3GPP Releases Descriptions – R99 to Rel-17
http://www.3gpp.org/ftp/Information/WORK_PLAN/Description_Releases/
“Releases Descriptions” for Releases 8 to 13: limited to copy-paste of the WIDs.
“Releases Descriptions” for Releases 14 to 17: TR 21.9xx: “Release xx Description; Summary of Rel-xx Work Items”, written in collaboration with all the Rel-xx Features Rapporteurs
3GPP Releases Descriptions – Rel-18
Started – skeleton in RP-233919 / CP-233305 / SP-231617, call for contribution in RP-233777 / CP-233299 / SP-231516