## Sheet1
| Status | Study | Norm | Total | New Study | New Norm | New Total | Comments
FS_5GSAT_ARCH_Ph3 | SA Approved | 7 | 5.5 | 12.5 | 7 | 5.5 | 12.5
FS_NG_RTC_Ph2 | SA Approved | 6 | 5.5 | 11.5 | 6 | 5.5 | 11.5
FS_XRM Ph2 | SA Approved | 7 | 6 | 13 | 7 | 6 | 13
FS_EnergySys | SA Approved | 6.5 | 6.5 | 13 | 6.5 | 6.5 | 13
FS_MPS4msg | SA Approved | 3 | 3 | 6 | 3 | 3 | 6
FS_VMR_Ph2 | SA Agreed | 6 | 5 | 11 | 3 | 2.5 | 5.5 | Updates on WT/TU reduction agreed in SP-231770
FS_5G_ProSe_Ph3 | SA Agreed | 2 | 1.5 | 3.5 | 2 | 1.5 | 3.5
FS_SLTS | SA Noted | 0 | 0 | 0 | 0 | 0 | 0
FS_eTRS_URLLC_LAN | SA Noted | 0 | 0 | 0 | 0 | 0 | 0
FS_eUUI5 | SA Agreed | 8 | 6 | 14 | 5.25 | 4.25 | 9.5 | Updates on WT/TU reduction agreed in SP-231771
FS_eEDGE_5GC_ph3 | SA Agreed | 6 | 4.25 | 10.25 | 4.5 | 3 | 7.5 | Updates on WT/TU reduction agreed in SP-231772
FS_UAS_Ph3 | SA Agreed | 5 | 4.5 | 9.5 | 3.5 | 3 | 6.5 | Updates on WT/TU reduction agreed in SP-231773
FS_ISAC_ARC | SA Endorsed | 0 | 0 | 0 | 0 | 0 | 0
FS_UPEAS_Ph2 | SA Agreed | 2.25 | 2.25 | 4.5 | 2.25 | 2.25 | 4.5
FS_5G_Femto | SA Agreed | 2 | 3 | 5 | 2 | 3 | 5
FS_INSS | SA Agreed | 2 | 2 | 4 | 0 | 0 | 0 | Move to TEI19. SA recommend SA2 to discuss this as TEI19 poposal and bring for approval to future TSG meetings.
FS_ETM | SA Noted | 0 | 0 | 0 | 0 | 0 | 0
FS_MASSS | SA Agreed | 7.75 | 6.25 | 14 | 7.5 | 6 | 13.5 | Updates on WT/TU reduction agreed in SP-231775
FS_AmbientIoT | SA Agreed | 13 | 0 | 13 | 11.5 | 0 | 11.5 | Updates on WT/TU reduction agreed in SP-231774
FS_AIML_CN | SA Agreed | 4 | 4 | 8 | 4 | 4 | 8
RVAS_ARCH | TEI19? | 0 | 0 | 0 | 0 | 0 | 0 | Move to TEI19. SA recommend SA2 to discuss this as TEI19 poposal and bring for approval to future TSG meetings.
Total | 152.75 | 87.5 | 65.25 | 152.75 | 75 | 56 | 131 | Keep it to 131 to allow more buffer
Total number of items | 15
TEI19_Netshare: SA recommend SA2 to discuss this as TEI19 poposal and bring for approval to future TSG meetings.