## Slide 1
Agenda Item: 7.4
Source: Samsung
Title: Samsung views on 6G timeline
Document for: Discussion

## Slide 2
Introduction
TSG#102 discussed 3GPP timeline for 6G and some agreements were made.
In this contribution, we propose remaining details for discussion and agreement in TSG#103.

## Slide 3
3GPP Timeline for 6G
TSG#102 Agreement
TSG-wide 6G workshop: March 2025
IMT-2030 use cases workshop: 8-10 May 2024
6G SIs: Rel-20
  SA1 SI approval: September 2024
  RAN SI (requirements) approval: TBD
  SA2 SI approval: June 2025
  RAN WGs SI: June 2025
6G WI: Rel-21
  The release for IMT-2030 submission
  Single drop
Completion dates for SIs and WIs: TBD
Samsung Proposal for the Remaining Details
RAN SI (requirements) approval: Sep 2024
  Focus on KPI requirements until Mar 2025 for early communication with ITU-R on IMT-2030 requirements
  Update SID taking into account the outcome of TSG-wide 6G workshop in March 2025 and continue to develop 3GPP’s requirement for 6G.
RAN SI completion: June 2026
6G architecture decision : June 2026
Completion of RAN WGs SI: Dec 2026
Rel-20 schedule (18 months)
  Functional freeze : March 2027
  ASN.1/Open API freeze : June 2027
Rel-21 schedule (21 months)
  Functional freeze : Dec 2028
  ASN.1/Open API freeze : Mar 2029

## Slide 4
Overall Timeline for 6G