## Slide 1: ZTE Views on 3GPP 6G Timeline
Source: ZTE
Agenda: 7.4
3GPP TSG SA Meeting #103
Maastricht, Netherlands, March 18-21, 2024
SP-240399

## Slide 2: Endorsed 6G Timeline (RP-233985 = SP-231693 = CP-233319)
First TSG-wide 6G workshop is expected to be in March 2025
  Right before the planned Rel-19 RAN1 functional freeze (June 2025). Detailed information for the workshop is TBD
Organization of a 3GPP Stage 1 workshop on IMT-2030 use cases is being discussed separately
  Refer to SP-231619 (Set to early May 2024)
Studies for 6G in 3GPP are expected to start from Release 20
  Requirements studies:
    SA1 SID is expected to be approved in Sept’2024.
    RAN plenary SID (e.g., radio requirements and KPIs) is expected to be approved TBD (to be decided at RAN#103)
  Technology studies:
    SA2 SID is expected to be approved in June’2025. Other SA-WG SIDs (e.g., Security, etc.) are expected to be approved TBD
    RAN-WG SIDs are expected to be approved in June’2025
    CT-WG SIDs are expected to be approved TBD
IMT-2030 submission and normative work for 6G in 3GPP are expected to start from Release 21
  Release 21 is expected to produce the 1st set of 3GPP 6G technical specifications, and will be the release for IMT-2030 submission before 2030
  Release 21 is expected to be delivered with a single drop (i.e., a single code freeze)
Target TSG#103 (March’2024) for the remaining detailed 6G timeline decisions

## Slide 3: 6G timeline proposals
SA1 6G work
  SA1 umbrella SID is expected to be approved at Sep 2024 (endorsed)
  SA1 umbrella SID is expected to be 80% completed at Sep 2025
  SA1 Building Block SIDs are expected to be approved at Mar 2025 and 100% completed at Mar 2025
  SA1 Normative WIDs are expected to be approved at Dec 2025 and 100% completed at Dec 2026
SA2 6G work
  SA2 SID is expected to be approved at Jun 2026 (endorsed)
  SA2 SID is expected to be completed at Dec 2026
  SA2 WID is expected to be approved at Dec 2026 and completed at Mar 2028
CT 6G work
  CT SIDs are expected to be approved at Mar 2026, and completed at TBD
  CT WIDs are expected to be approved at TBD, and completed at Dec 2028
  ASN.1 frozen at Mar 2029

## Slide 4
5D
#40
5D
#41
5D
#42
5D
#43
5D
#44
5D
#45
5D
#46
5D
#47
5D
#48
5D
#49
5D
#50
5D
#51
5D
#52
5D
#54 #55 #56 #57 #58 #59 #60 #61 #62 #63 #64
5D
#53
5D
#37
5D
#38
2021 2022 2023 2024 2025 2026 2027 2028 2029 2030
WRC-27
#39
5D
WRC-23
5D
5D
5D
5D
5D
5D
5D
5D
5D
5D
Workshop
Technology Proposals for “IMT-2030”
Technical performance requirements
Evaluation
Modifications Resolutions 56
or/and possible new Resolution
Recommendation framework of IMT for 2030 and beyond
ITU Report
Future Technology trends
Revision of report M.2376 IMT feasibility above 6GHz `

3GPP 6G Workshop
Rel-21
Rel-20
Rel-19
Rel-18
SA1 6G umbrella SI
Evaluation criteria & methodology
Requirements, Evaluation criteria & Submission Templates
Consensus building
Outcome & Decision
IMT-2030 Specification
SA2 6G SI
SA2 6G WI
CT 6G SI
Release Timeline
Background & Process
Circular Letter (and latter addenda)
Rel-22
Spec Submission to ITU

3GPP 6G use case
workshop
SA1 6G BB SI
SA1 6G WIDs
CT 6G WI
TBD

## Slide 5: Thanks