3GPP TSG SA Meeting #103												SP-240394

Maastricht, Netherlands, March 19-21, 2024

Agenda Item:	7.4

Source:	Huawei, HiSilicon

Title:	Milestones of 6G timeline in 3GPP

Document for:	Discussion and decision

# Introduction

In this paper, we present our views on remaining milestones of 3GPP 6G timeline.

# Need of 3GPP 6G timeline

ITU-R WP5D agreed on the IMT-2030 timeline in June 2022, as shown in Figure1. Candidate IMT-2030 technologies shall be approved by ITU-R in late 2030. Furthermore, ITU-R has agreed the Framework for IMT-2030. To promptly have a clear 3GPP 6G timeline consistent with the ITU-R IMT-2030 timeline will strengthen the industry confidence toward IMT-2030 technologies.

Figure 1: ITU-R IMT-2030 timeline

In the recent OP meeting #50, the Partners approved the press release text in [1], where all OPs jointly make a statement about 3GPP’s commitment to develop 6G specification. It was also approved in OP meeting #50 that the joint statement will be released on December 04, 2023, which is the 25th anniversary of 3GPP. Therefore, a prompt decision on 3GPP 6G timeline is also needed to strengthen 3GPP commitment to 6G.

Having a clear 3GPP 6G timeline also helps all stakeholders to plan their internal/external activities (including research, prototyping, etc.), which in turn contributes to the high quality 3GPP 6G technology and specifications in the coming years. Note that quite significant amount of time is needed for companies to prepare for 3GPP 6G work. Therefore, it is beneficial to have a 3GPP 6G timeline well in advance before the actual work starts in 3GPP.

Given the above observations, we think it is time for 3GPP to have a clear 6G timeline, preferably to be decided by March 2024.

Proposal 1: Aim to agree on the 3GPP 6G timeline no later than March 2024.

# Consideration points for 3GPP 6G timeline

There are many elements to consider when deciding the 3GPP 6G timeline. From our point of view, we would like to emphasize on the following points:

- Relation to 5G and 5G-Advanced

It is noted that 5G roll-out continues increasing globally and expected so in coming years, including the commercialization of 5G-Advanced. The 3GPP 6G timeline needs to properly consider the future market development and avoid negative impacts on industry’s initiatives to further expand the 5G use cases and improve the 5G system performance. Aggressive 3GPP 6G timeline should be avoided.

- Duration of the first 6G SI/WI

It is expected that 6G will encompass technologies for conventional communications as well as “beyond” communications. Therefore, sufficient duration is warranted to produce the first 3GPP 6G release, including a SI and a WI. For 5G, the start of WG SI to the completion of non-standalone normative work was very short (i.e. close to two years), with another six months to complete the standalone normative work. The first version of 5G ASN.1 was not stable and implementable. These lessons from 5G need to be taken into account when deciding the 3GPP 6G timeline.

Given the above consideration, we prefer to avoid overly aggressive 3GPP 6G timeline.

Proposal 2: Overly aggressive 3GPP 6G timeline should be avoided.

# Agreements from TSG #102

Some milestones of 3GPP 6G timeline has been endorsed as in RP-233985, as copied below.

Figure 2: Milestones endorsed in RP-233985

In our view, the remaining major milestones of 3GPP 6G timeline to be endorsed include:

- Start and completion time for the RAN plenary 6G SI

- Completion time for the first set of 3GPP 6G technical specifications

# Completion time for first 3GPP 6G release

Looking at different proposals on 3GPP 6G timeline, it is observed that the ending time of first 3GPP 6G release (in terms of code freeze, i.e. ASN.1 for RAN and OpenAPI for CT) falls generally near either end of 2028 or end of 2029. Note that end of 2029 is almost the latest time for 3GPP to fit into the ITU-R IMT-2030 timeline, as ITU-R needs to finalize its evaluations on candidate IMT-2030 technologies in early 2030 and then complete the rest process by the end of 2030.

There are various reasons in favor of either end of 2028 or end of 2029. Our preference is end of 2029 as the completion time for the first 3GPP 6G release, as this provides more time for 3GPP to develop high quality 6G specifications. Nevertheless, observing the need to have a clear 3GPP 6G timeline, it is natural to seek a compromise from both ends, e.g. June 2029. It is also noted that the time needed to generate a stable ASN.1/OpenAPI for the first release of a generation may be longer. Therefore, it is proposed to target first ASN.1/OpenAPI for 6G in March 2029, with the understanding that a stable version may only be available in June 2029.

In summary, the following is our compromised proposal regarding the first release of 3GPP 6G specifications.

Proposal 3: Consider the following compromise for the completion time of first 3GPP 6G release

- RAN1 Stage 3 freeze: September 2028

- RAN2/3/4 Stage 3 freeze: December 2028

- CT Stage 3 freeze: December 2028

- First ASN.1/OpenAPI freeze: March 2029

# Start and completion time for RAN plenary 6G SI

Given the 3GPP TSG-wide 6G workshop is in March 2025, naturally the approval of the RAN plenary 6G SI is to occur at March 2025 or June 2025. Noticing that ITU-R WP5D is developing the IMT-2030 technical performance requirements (TPR), it is beneficial to consider the potential interactions between 3GPP and ITU-R on IMT-2030 TPR.

Figure 3 shows the interaction between 3GPP and ITU-R for IMT-2020 TPR. It is noted that ITU-R had four meetings for IMT-2020 TPR development, starting Feb.2016 to Feb 2017, and 3GPP members submitted corresponding input contributions during this process for key definitions. For IMT-2030, ITU-R scheduled seven meetings, starting Feb. 2024 to Feb. 2026.  It is beneficial for 3GPP members to have similar amount of inputs to ITU-R during the IMT-2030 TPR process for key definitions, e.g. in Jun. 2025, Oct. 2025 and Feb. 2026. Considering the time needed to form the first 3GPP input to ITU-R, approval of 3GPP RAN plenary 6G SI can be in Mar. 2025, or Dec. 2024 the earliest.

To ensure that 3GPP 6G technologies can fulfill all IMT-2030 requirements, the completion time of the RAN plenary 6G SI is preferable to be after the ITU-R IMT-2030 technical performance requirements, which is scheduled to be done by Feb 2026. Therefore, completion time of RAN plenary 6G SI can be Jun. 2026, the earliest.

Proposal 4: Consider the following start and completion time for 3GPP RAN plenary 6G SI

- Approval of RAN plenary 6G SI: March 2025, or December 2024 the earliest

- Completion of RAN plenary 6G SI: June 2026

Figure 3: 3GPP and ITU-R interaction for IMT-2020 and IMT-2030 TPR

# Conclusions

In this contribution, we share our views on remaining milestones of 3GPP 6G timeline. Our proposals are summarized as follows:

Proposal 1: Aim to agree on the 3GPP 6G timeline no later than March 2024.

Proposal 2: Overly aggressive 3GPP 6G timeline should be avoided.

Proposal 3: Consider the following compromise for the completion time of first 3GPP 6G release

  - RAN1 Stage 3 freeze: September 2028

  - RAN2/3/4 Stage 3 freeze: December 2028

  - CT Stage 3 freeze: December 2028

  - First ASN.1/OpenAPI freeze: March 2029

Proposal 4: Consider the following start and completion time for 3GPP RAN plenary 6G SI

- Approval of RAN plenary 6G SI: March 2025, or December 2024 the earliest

- Completion of RAN plenary 6G SI: June 2026

Figure 4 illustrates the above 3GPP 6G timeline.

Figure 4: Proposed 3GPP 6G timeline

# References

- 3GPP/OP#50(23)11, “Common OP message about the role of 3GPP in 6G standards”, 3GPP Marcom Officer.