## Slide 1: Additional Considerations for 6G Timeline
Source: TSG Chairs
3GPP TSG#103 Joint Session
March 20th, 2024
SP-240432
AI 7.4, AI 5.2

## Slide 2: Background: As Endorsed in TSG#102
First TSG-wide 6G workshop is expected to be in March 2025
  Right before the planned Rel-19 RAN1 functional freeze (June 2025). Detailed information for the workshop is TBD
Organization of a 3GPP Stage 1 workshop on IMT-2030 use cases is being discussed separately
  Refer to SP-231619
Studies for 6G in 3GPP are expected to start from Release 20
  Requirements studies:
    SA1 SID is expected to be approved in Sept’2024.
    RAN plenary SID (e.g., radio requirements and KPIs) is expected to be approved TBD (to be decided at RAN#103)
  Technology studies:
    SA2 SID is expected to be approved in June’2025. Other SA-WG SIDs (e.g., Security, etc.) are expected to be approved TBD
    RAN-WG SIDs are expected to be approved in June’2025
    CT-WG SIDs are expected to be approved in March’2026 (depends on SA2 SI work)
IMT-2030 submission and normative work for 6G in 3GPP are expected to start from Release 21
  Release 21 is expected to produce the 1st set of 3GPP 6G technical specifications, and will be the release for IMT-2030 submission before 2030
  Release 21 is expected to be delivered with a single drop (i.e., a single code freeze)
Target TSG#103 (March’2024) for the remaining detailed 6G timeline decisions
High-Level Considerations for 6G Timeline

## Slide 3: Proposal: Additional Details for TSG-Wide 6G Workshop
Note: TSG#102 endorsed the TSG-wide 6G workshop to be in March’2025
Proposal:
  TSG-Wide 6G Workshop: Monday – Tuesday of the TSG#107 meeting week
    Details TBD (e.g., whether to have a joint or separate workshop across TSGs, how to handle contributions, etc.)
  TSG#107 plenary meetings are to be scheduled subsequently in the same week
    RAN/SA: Wed (0900) – Friday (1800)
    CT: Wed (0900) – Thursday (1200)

## Slide 4: Proposal: Additional Details for 3GPP SIs for 6G
SA SI approvals: as endorsed in TSG#102, no new update
  SA1 SI approval: TSG#105 (Sept2024)
  SA2 SI approval: TSG#108 (June’2025)
  Other SA WGs SI approval: Details TBD
RAN
  Note: Approval of RAN WG SIs was endorsed in TSG#102 to be in TSG#108 (June’2025)
  RAN-level SI Approval
    Decide whether it’s necessary to have an early RAN-level study focusing on 3GPP input to the ITU-R KPI/TPR process
      To be discussed in RAN#103 before the joint session.
    RAN-level study approval should be ahead of RAN WGs’ SI.
      RAN-level SI approval is in Dec 2024. RAN-level SI starts in Mar 2025.
CT level SI Approval
  Plenary level: TSG#111 (March‘2026) at the latest
    Similar to 5G CT studies (e.g. Protocol selection and Protocol improvements, etc. depending on SA2 progress). Details TBD.

## Slide 5: Proposal: Additional Details for Rel-20
Critical to continue 5G-Advanced evolutions in Rel-20, in parallel with the 6G study, to address urgent commercial needs
Thus, necessary to decide the duration for Rel-20 by considering both 5G-Advanced evolution and 6G study needs
Proposal: in Rel-20
  For 5G-Advanced: 18-month. Assuming no delay of Rel-19, it implies the following dates
    Stage-1 freeze : Jun 2025
    Stage-2 freeze : Jun 2026 (80%); Sep 2026 (100%)
    Stage-3 freeze : Mar 2027
    ASN.1/OpenAPI freeze: June 2027
  For 6G SI, aim for 18 months. Can be revisited at later TSGs based on SI progress.
    SA1/SA2 6G SI may continue beyond Stage-1/Stage-2 freeze dates.
    RAN WG 6G SI may or may not be aligned with the stage-3 dates.
    CT SI will start 9 months after approval of SA2 SI.

## Slide 6: Proposal: Additional Details for Rel-21
Duration for Rel-21 requires more careful analysis
  Commercial deployment needs
  ITU-R submission needs
  Study outcome from Rel-20
  Etc.
Proposal:
  ASN.1/OpenAPI Code freeze for Rel-21 should be at least 6 months before the IMT2030 submission deadline (June’2030)
    Tentative Rel-21 ASN.1/OpenAPI Code freeze date: Mar 2029.
  To be finalized at TSG#104 along with other Rel-21 timelines.