## Slide 1: 3GPP TSG-SA meeting #103 SP-240433 Maastricht, Nederlands, March 19th – 22th, 2024 Agenda Item: 7.4 Source: Ericsson Title: Time schedule for Release 20 and Release 21 – IMT-2030 Document for: Discussion, Decision

## Slide 2: Introduction
In TSG#102 Ericsson provided a cross TSG discussion document in SP-231577.
As a follow up, this document proposes detailing the different milestone target dates for stage 1, 2 and 3 completion.
The proposal is building on a release length of 18 months for Rel-20 and 21 months for Rel-21.
The next slide is illustrating the release schedule together with the ITU-R timeline.
This contribution proposes that the full set of target dates are agreed in TSG#103 as detailed on slide 4 and slide 5 for Rel-20 and Rel-21, respectively.

## Slide 3: 6G timeline – SA/CT/RAN combined
SA1: Rel-19
SA1: Rel-20
SA1: Rel-22
SA1: Rel-21
SA1: Rel-23
SA2/6: Rel-19
SA2/6: Rel-21
SA2/6: Rel-20
SA2/6: Rel-22
Stage 1
6G requirement SI (SA1)
6G requirement SI & WI (SA1)
…
6G system study item(s) (SA2/6)
6G system work item(s) (SA2/6)
6G system evolution work item(s) (SA2/6)
…
Rel-19
Rel-21
Rel-20
Rel-22
6G work items (SA, CT, RAN)
6G evolution work items (SA, CT, RAN)
…
6G evolution SI/WI (SA1)
Stage 2
Stage 3*
2022 | 2023
2024 | 2025
2026 | 2027
2028 | 2029
2030 | 2031
SA1 workshop on 6G
3GPP workshop on 6G
ASN.1/OpenAPI Freeze Rel-21
*RAN 1 a quarter earlier
6G RAN requirements (SI)
6G study items (SA, CT, RAN)
Technical performance requirements
WRC-23
WRC-27
Framework for IMT-2030 and beyond
Workshop
Independent Evaluation
IMT-2030 Technology Proposals
Future Technology Trends
Evaluation criteria &
submission templates
Outcome & Decision

## Slide 4: Proposal : Rel-20 Timeline
The release schedule for Rel-20 is proposed to be18 months.
The completion date for stage 1 (100%) to be June 2025, with 80% completion by March 2025.
The completion date for the stage 2 (in SA2 and SA6) to be June 2026.
    As a general principle, the stage 2 study items have a general target to complete 6 months earlier than the target date for normative stage 2 completion.
    The SA3 completion date for stage 2 specifications to be September 2026.
The completion date for stage 3 specifications to be March 2027.
    This to be a coordinated stage 3 target date with RAN stage 3 functional freeze.
    OpenAPI files and ASN.1 coding is then targeted to freeze June 2027.

## Slide 5: Proposal : Rel-21 Timeline
The release schedule for Rel-21 is proposed to be 21 months.
The completion date for stage 1 (100%) to be March 2027, with 80% completion by December 2026.
The completion date for the stage 2 (in SA2 and SA6) to be March 2028.
    As a general principle, the stage 2 study items have a general target to complete 6 months earlier than the target date for normative stage 2 completion.
    The SA3 completion date for stage 2 specifications to be June 2028.
The completion date for stage 3 specifications to be December 2028.
    This to be a coordinated stage 3 target date with RAN stage 3 functional freeze.
    OpenAPI files and ASN.1 coding is then targeted to freeze March 2029.