## Slide 1: Operator views on 6G timeline Orange, Deutsche Telekom, AT&T, Bell Mobility, Bouygues Telecom, BT, CKH IOD UK LIMITED, KDDI, KPN, Odido, Rakuten Mobile, Reliance Jio, Spark NZ, Telecom Italia, Telefonica, Telenor, Telia Company, Telstra, Turkcell, T-Mobile USA, US Cellular, Verizon, Vodafone

## Slide 2: Motivations and key message
5 years after the early 5G deployments, take up of 5G-SA networks is rather slow
New use cases for verticals and the introduction of slicing are in a very early phase
One may reasonably expect 5G-SA to gain wider adoption around the time of 6G specification work in 3GPP
Given the above considerations, we propose to use our time appropriately, in order to deliver high quality 6G 3GPP specifications

## Slide 3: 6G timeline – reminder of proposals endorsed at TSG #102
At TSG #102, high-level considerations for the 6G timeline were provided in RP-233985/SP-231693/CP-233307
The following proposals were endorsed
      First TSG-wide 6G workshop is expected to be in March 2025
      Studies for 6G in 3GPP are expected to start from Release 20
        Requirements studies:
          SA1 SID is expected to be approved in Sept. 2024.
          RAN plenary SID (e.g., radio requirements and KPIs) is expected to be approved TBD (to be decided at RAN#103)
        Technology studies:
          SA2 SID is expected to be approved in June 2025. Other SA-WG SIDs (e.g., Security, etc.) are expected to be approved TBD
          RAN-WG SIDs are expected to be approved in June 2025
          CT-WG SIDs are expected to be approved TBD
      IMT-2030 submission and normative work for 6G in 3GPP are expected to start from Release 21
        Release 21 is expected to produce the 1st set of 3GPP 6G technical specifications, and will be the release for IMT-2030 submission before 2030
        Release 21 is expected to be delivered with a single drop (i.e., a single code freeze)
      Target TSG#103 (March 2024) for the remaining detailed 6G timeline decisions

## Slide 4: 6G timeline – operator proposal
1st set of 3GPP 6G specifications target completion by Q4 2029
6G work in Rel-20 to be 21-month & Rel-21 to be 24-month
Rel-20 plan should balance the work for 5G-Advanced enhancements and 6G related studies
2024
2025
2026
2027
2028
2029
2030
Rel-20 – 6G SI – RAN1
Rel-20 – SA2 6G SI
Rel-20 – SA1 6G SI
Rel-21 – SA1 6G SI/WI
Rel-21 – SA2 6G WI
Rel-20 – 6G RAN Req SI
SA1 6G workshop
(8 – 10 May)
6G RAN/SA workshop
March TSG
6G studies
6G specs
ASN.1 + Open API
Rel-20 – 6G SI – RAN2/3/4 / SA / CT
Rel-21 – 6G WI – RAN1
Rel-21 – 6G WI – RAN2/3/4 / SA / CT

## Slide 5: Summary - 6G Timeline (1/2)
6G work in Rel-20 to be 21-month & Rel-21 to be 24-month
6G Studies in Rel-20
      The SA aspects
        SA1 SID to be approved in September 2024
        SA2 SID to be approved in June 2025
        SA3/4/5/6 SIDs to be approved in March 2026
      The RAN Aspects
        RAN Requirements SID to be approved in June 2025
        RAN1/2/3 SIDs to be approved in December 2025
        RAN4 SID to be approved in March 2026
      The CT Aspects
        CT WGs SIDs to be approved in March 2026
6G Studies may continue in Rel-21 timeframe

## Slide 6: Summary - 6G Timeline (2/2)
6G Specifications in Rel-21
      The SA aspects
        SA1 WID to be approved in December 2025
        SA2 WID to be approved in September 2026
        SA3/4/5/6 WIDs are expected to be approved in December 2027
      The RAN aspects
        RAN1/2/3 WID to be approved in September 2027
        RAN4 WIDs to be approved in December 2027
      The CT aspects
        CT WGs WIDs to be approved in December 2027
      Stage 3 Functional Freeze in December 2029