## Slide 1
3GPP Work Plan
Review at Plenary #104
Source: MCC / Work Plan Manager (A. Sultan)
Agenda item: Review of the Work Plan
Document for: Information
Review based on the latest available version of the Work Plan, available at: https://ftp.3gpp.org/Information/WORK_PLAN
Includes: - the progress on all WIDs, as indicated in the WG Chairs’ reports (CT & SA) and in the Status Report (RAN), - the new WIDs proposed by SA/CT WGs to TSG#104 (will be removed if not TSG-approved)
Does not include: - the company-proposed WIDs approved at TSG#104, the RAN#104 new WIDs
Warnings :
- This review is a high-level view of the 3GPP progress. It is based on the 3GPP Work Plan, a continuously updated document.
Some misalignments might temporarily appear on some individual items.
- Some WG cannot progress because of reasons beyond their control (e.g. dependencies with other groups).
These slides shall not be used to judge the “efficiency” of whatever WG.
© 3GPP 2024
SP-240992 (rev. of CP-241309 , CP-241012/RP-240876/SP-240926) - 3GPP TSG#104, 17 -21 June 2024, Shanghai, China

## Slide 2: Content of this Work Plan review
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 3
Release 18 timeline
#93-e
SA1 Stage 1 100%
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN4
content def.
Note: All starting dates are indicative
#94-e
#95-e
#96
#97-e
#98-e
#99
#100
#101
#102
#103
#104
#105
RAN Content def.
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2024
Now
Maint.
Maint.
ASN.1 & Open APIs
ASN.1
1st review
TSGs
2021
RAN Completion (RAN2/3/4core)

## Slide 4: Release 18 Progress: SA & CT
462 items for Rel-18 Stages 1, 2 and 3 in SA & CT. All completed, except:
Unique_ID | Name | Acronym | WG | %Complete
990097 | CT3 aspects of Application Data Analytics Enablement Service | ADAES | C3 | 96%
Work-Plan clean-up needed for:
Unique_ID | Name | Acronym | WG | %Complete
920003 | Lawful Interception Rel-18 | LI18 | S3LI | 20%
Unique_ID | Name | Acronym | WG | %Complete
1040002 | Update of conformance test specifications to Rel-18 | UEConTest_R18 | C6 | 0%
Testing – for completion by June 2025:
Moved to Rel-19:
Unique_ID | Name | Acronym | WG | %Complete
1010003 | Study on IMS Disaster Prevention and Restoration Enhancement | FS_IMS_RES | C4 | 85%
1000001 | Study on Reducing Information Exposure over SBI | FS_RedInfExp_SBI | C4 | 95%

## Slide 5: Release 18 Progress: Stage 3 (RAN)
230 items for Rel-18 RAN work. All completed, except (not showing RAN5 testing):
Unique_ID | Name | Acronym | WG | %Complete
991241 | Perf. part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN | IoT_NTN_extLband-Perf | R4 | 0%
991043 | Introduction of FDD LTE band (L+S band) for IoT NTN operation | IoT_NTN_FDD_LS_band | R4 | 99%
981138 | Core part: Expanded and improved NR positioning | NR_pos_enh2-Core | R1 | 99%
981238 | Perf. part: Expanded and improved NR positioning | NR_pos_enh2-Perf | R4 | 90%
941110 | Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN | NR_AIML_NGRAN-Core | R3 | 80%
991145 | Core part: NR channel raster enhancement | NR_channel_raster_enh-Core | R4 | 95%
970285 | Perf. part: High power UE (power class 1.5) for NR FR1 TDD single band | HPUE_NR_FR1_TDD_R18-Perf | R4 | 0%
970289 | Perf. part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) | HPUE_FR1_TDD_NR_CADC_SUL_R18-Perf | R4 | 0%
970081 | Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirement for NR UEs | NR_MIMO_OTA_enh | R4 | 99%
941212 | Perf. part: NR support for dedicated spectrum less than 5MHz for FR1 | NR_FR1_lessthan_5MHz_BW-Perf | R4 | 70%
950181 | Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment | NonCol_intraB_ENDC_NR_CA-Core | R4 | 95%
941001 | Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR | NR_DualTxRx_MUSIM | R2 | 78%
991042 | Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76 | NR_FDD_ULn28_DLn75_n76 | R4 | 99%
991044 | Complete the specification support for BandWidth Part operation without restriction in NR | NR_BWP_wor | R4 | 99%
1010055 | Introduction of NR bands n31 and n72 | NR_bands_n31_n72 | R4 | 99%
981145 | Core Part: Introduction of 900 MHz NR band in the US | NR_900MHz_US-Core | R4 | 25%
981245 | Perf. part: Introduction of 900 MHz NR band in the US | NR_900MHz_US-Perf | R4 | 25%
961113 | Core part: High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe | NR_RAIL_HPUE_n100_n101-Core | R4 | 0%
960293 | Perf. part: Enhancements of NR shared spectrum bands | NR_unlic_enh-Perf | R4 | 99%
970282 | Perf. Part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) | NR_FR1_TRP_TRS_enh-Perf | R4 | 98%
961202 | Perf. part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) | DC_R18_xBLTE_yBNR_zDL3UL-Perf | R4 | 70%
981246 | Perf. part: Introduction of 900 MHz LTE band in the US | LTE_900MHz_US-Perf | R4 | 10%
991140 | Core part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths | LTE600_US_lowCBW-Core | R4 | 0%
991240 | Perf. part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths | LTE600_US_lowCBW-Perf | R4 | 0%
Pre-RAN#104 status

## Slide 6: Release 18 recap – text version
Release 18 Freezes and other milestones, sorted by dates :
  Sept 2021 (TSG#93): Stage 1: 80% normative work; SA Workshop; joint SA/RAN/CT meeting
  Dec 2021 (TSG#94):
    Stage 1: 100% normative work
    RAN/SA/CT joint meeting on Rel-18 content; SA2 Work Items prioritization; RAN Content Definition
  Mar 2022 (TSG#95): RAN4-lead WIDs specified
  June 2022 (#96) till March 2023 (#99): no specific deadline
  June 2023 (TSG#100): Stage 2 Functional work (SA2 and SA6) Freeze
  Sep 2023 (TSG#101):
    RAN1 freeze (before maintenance)
    Freeze for SA3 (stages 2 & 3) – maintenance to continue
  Dec 2023 (TSG#102):
    RAN1 (after maintenance) declared frozen
    RAN2, RAN3, RAN4Core (before maintenance) declared frozen
  Mar 2024 (TSG#103):
    RAN2, RAN3, RAN4Core freeze maintenance
    Stage 3 (all CT WGs; SA WGs involved with Stage 3) freeze
    (also first review of ASN.1)
  June 2024 (TSG#104):
    RAN4Perf freeze - done
    “coding freeze”. Freeze of:ASN-1; Open APIs - done
Now

## Slide 7: Content of this Work Plan review
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 8
Release 19 timeline
#101
Note: All starting dates are indicative
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop

## Slide 9: Release 19 progress overview
SA1 (Stage 1)
  Studies : 14 studies – stable for long, All studies completed (including last exception: FS_ISN)
  Normative : 25 tasks, including “miniWIDs” - All normative work completed (including new MonsTra)
SA2, SA6 (Stage 2)
  SA & RAN Content defined at TSG#101 & 102 (considering SA1 outputs)
  Studies: was 23 studies at previous TSG → now still 23 studies*, OCI was 38% at previous TSG → now OCI = 97%
  Normative: was 22 items → now 44 items*, OCI was 17% → now 30%
RAN
  RAN1, 2,3, 4 content definition completed by TSG#103
  RAN studies: 3 → 8 studies*, OCI : 0% → 32%
  RAN Core: 10 → 20 items*, OCI: 4% → 18 %
  RAN Perf: 9 → 19 items*, still not started
SA 3/4/5 & CT
  SA3/4/5:
    SA3: 16 → 18 studies; OCI=7% → 42%; normative: 7 → 10 items; OCI=0% → 40%
    SA4: 7 → 12 studies; OCI=0% → 28%; normative: 2 → 3 items; OCI=0% → 8%
    SA5: 17 → 21 studies; OCI=0% → 41%; normative: 4 → 7 items; OCI=0% → 16%
  CT WG: 0 → 1 study; not started; normative: 0 → 27 items; still not started
OCI = Overall Completion Index
* For RAN WIDs counting, this is as per pre-TSG meeting, i.e. in this case from pre-RAN#103 to pre-RAN#104. The OCI is as per the Status Reports presented at RAN#104.
* The SA&CT WIDs counting actually refers to the WIDs proposed by WGs to SA&CT.

## Slide 10: Release 19 timeline recap - text version
Release 19 Freezes and other milestones, sorted by dates :
  June 2023: RAN workshop on Rel-19 content, SA workshop on Rel-19 content
  Sept 2023 (TSG#101):
    Stage 1: 80% normative work
    Approve 1st part of SA Stage 2 package (SA/CT)
  Dec 2023 (TSG#102):
    Stage 1: 100% normative work
    RAN1/2/3 Content Definition
    Approve final package of SA Stage 2 with RAN/CT
  Mar 2024 (TSG#103): RAN4 Content Definition
  June 2024: no specific milestone
  Dec 2024 (TSG#106): Stage 2 Functional work (SA2 and SA6) Freeze (working assumption)
  June 2025 (TSG#108): RAN1 freeze
  Sept 2025 (TSG#109):
    RAN2, RAN3, RAN4Core freeze
    Stage 3 (all CT WGs; SA WGs involved with Stage 3) freeze (working assumption)
  Dec 2025 (TSG#110):
    RAN4Perf freeze; “coding freeze”. Freeze of:ASN-1; Open APIs (working assumption)
Now

## Slide 11: Content of this Work Plan review
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 12: Release 20: introduction
Rel-20 has 2 components: “Rel-20_5GA” and “Rel-20_6G”
  Rel-20_5GA covers 5GA studies and normative;
  Rel-20_6G covers 6G studies only (6G normative in Rel-21)
  Each component has its own timeline
  Up to each TSG/WG how to split their time on each component (e.g. in SA1, it is 50%-50%)
Note: next slide has been slightly updated for corrections between TSG#103 and TSG#104

## Slide 13
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
SA1 5GA SID definition
Workshop 6G TSGs
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA St.+Norm 80%
Stage 3 5GA St + Norm
Stage 3 6G SID def.
#113
Sep.
#114
Dec.
#115
Mar.
Jun
Workshop IMT-2030 use cases
RAN1
RAN Completion (RAN2/3/4core)
#116
SA1 6G Study
RAN4 C.def.
RAN4 Perf
RP Content def.
SA1 6G SID def.
RP IMT-2030 disc.
RP ITU Study
RP 6G Study(ies)
RAN1 6G Study(ies)
SA2 6G Study(ies)
Stage 3 6G Study(ies)
Rel-20 - 5GA part
Rel-20 - 6G part
2025
2026
2027
SA2 & RAN WGs 6G SID def.
SA3/4/5/6 SID def. and compl. TBD
5GA ASN.1 & Open APIs
RAN2/3/4 6G Study(ies)
St.2 SID def. TBD
St.3 SID def. TBD
Release 20 timeline
or
TBD
Note: All starting dates are indicative

## Slide 14: Release 20_5GA – text version
The Rel-20_5GA endorsed deadlines are: (assuming no delay on Rel-19)
  Stage 1 approval of SIDs: Jun 2024; Stage 1 normative freeze : Jun 2025
  Stage 2 approval of SIDs: NYD*; Stage 2 normative freeze : Jun 2026 (80%); Sep 2026 (100%)
  Stage 3 (CT) approval of SIDs: Mar 2026 or earlier; Stage 3 CT normative freeze : Mar 2027
  Stage 3 RAN approval of SIDs:NYD*; Stage 3 RAN normative freeze : NYD*
  ASN.1/OpenAPI freeze: June 2027
  Other WGs : + 18 months compared to Rel-19 dates, i.e. for RAN:
    Content def: June 2025
    Ran1: Dec 2026
    RAN2/3/4Core: March 2027
    RAN4 Perf: June 2027
* NYD = Not Yet Defined

## Slide 15: Release 20_6G – text version
Rel-20_6G (only studies) endorsed deadlines: (assuming no delay on Rel-19)
  Stage 1 approval of SIDs: Sep 2024 (TSG 105); Stage 1 (study) freeze: Mar 2026
  March 2025 (TSG#107): First TSG-wide 6G workshop
  RAN IMT-2030 discussion is expected in RAN from 09/24 to 12/24
  RP SI Rel-20 focusing on ITU– IMT-2030: approval 12/24 until 06/25
  RP SI Rel-20 focusing on 6G General: approval 03/25 (after WS), until 06/26
  SA2 and RAN-WG SIDs approval: June 2025 (TSG 108); SA2 (study) freeze: Dec 2026 or Mar 2027
  SA1/SA2 6G SI may continue beyond Stage-1/Stage-2 freeze dates for 5G-Advanced
  Other SA WG (SA3, SA4, SA5, SA6) SIDs approval: TBD at future TSG meeting
  CT WG SIDs approval: March 2026
  RAN1 starts in 3Q/25 until 1Q/27; RAN2/3/4 start in 4Q/25 until 2Q/27
  CT WG 6G SI will start 9 months after approval of SA2 SI.
Sources: SP-240192 (SA1 chair), SP-240432 from TSG Chairs

## Slide 16: Release 20 progress overview (5GA & 6G)
Stage 1 (SA1):
  5GA Studies: remaining at 3 studies, all approved at TSG#103 (no new one at SA#104):
    Study on Satellite Access Phase 4 – 30%
    Study on FRMCS Phase 6 – 20%
    Study on Energy Efficiency as Service Criteria Phase 2 - 25%
  5GA Normative :
    Not started
  6G Study:
    Not started (only discussions)
    Decided to go for only one “basket” SID for 6G, targeted to be presented to TSG SA#105 (September 2024)
  (reminder: 6G Normative targeted to Rel-21)
Stage 2, Stage 3, RAN:
  Not started (except for a generic Rel-20 LI in SA3LI)

## Slide 17: Content of this Work Plan review
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 18: Release 21 placeholder
#124
#126
#104
#106
#108
#110
#112
#114
2024
2025
2027
#123
#125
#103
#107
#109
#111
#113
2026
2028
#105
Mar.
Mar.
Mar.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
Dec.
Dec.
Dec.
Now
Release 20_6G
Release 21
Rel-21 = 6G (study &) normative
Workshop Stage 1
Workshop Stages 2&3
Rel-20 = 6G Studies
#115
#117
#119
#116
#118
timeline to be defined by June 2026
Normative shall be ready for 2030
Stage 1 6G Studies
Definition then completion
Stage 3 and RAN 6G Studies
Definition then completion
Stage 2 6G Studies
Definition then completion
2029
#128
#130
#129
Jun.
Sep.
Dec.
2030
Mar.
#120
#121
#122
#127
Highlight only
or
TBD
TBD

## Slide 19: Release 21
Release 21 is the release for submission to IMT-2030*, aka 6G
Consequently, 3GPP (normative) work shall be submitted in time for ITU (2030)
  ASN.1/OpenAPI freeze date is no earlier than March 2029
Release 21 Freezing dates and other milestones TBD
  Rel-21 timeline is to be decided no later than June 2026
Note that, as usual in 3GPP, previous Generations will in parallel continue to be maintained & enhanced in Rel-21 and after
* source: TSG#103-endorsed CT-240307/SP-240458/RP-240823

## Slide 20: Content of this Work Plan review
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 21: Background information (1/2): overall background information
Dedicated e-mail list for Work Plan aspects
Open to everyone interested (rapporteus, chairs, delegates, etc.) by sending the message “Subscribe 3GPP_WORKPLAN” to the address LISTSERV@LIST.ETSI.ORG
For comments/update to the Work Plan, please use the 3GPP_WORKPLAN list
3GPP Work Plan
http://www.3gpp.org/ftp/Information/WORK_PLAN
Contains Release 1999 to Release 20; Master version in MS Project; Working versions in Excel
Tutorials on content, maintenance and other info on the Work Plan in subfolder /info
3GPP Releases Descriptions – R99 to Rel-17
http://www.3gpp.org/ftp/Information/WORK_PLAN/Description_Releases/
“Releases Descriptions” for Releases 8 to 13: limited to copy-paste of the WIDs.
“Releases Descriptions” for Releases 14 to 17: TR 21.9xx: “Release xx Description; Summary of Rel-xx Work Items”, written in collaboration with all the Rel-xx Features Rapporteurs
3GPP Releases Descriptions – Rel-18
Progressing – v.0.4.0 at TSG#104
v.1.0.0, that will include TSG1#04 inputs will be created before July 15th

## Slide 22: Background information (2/2): Relationship between WGs, Stages and deadlines
Most 3GPP Working Groups handle only one Stage:
  SA1  Stage 1
  SA2  Stage 2; SA6  Stage 2
  CT WGs  Stage 3 (also Stage 2 for some specific items)
SA3, SA4 and SA5 handle several Stages for some or all their WIDs:
  SA3: handles Stages 2 and 3 for all its WIDs. Stage 2 at SA3 is one quarter after SA2/SA6’s deadline, but this date is an SA3-internal date since there is no dependency (i.e. SA3 is not expecting work from any other WGs)
  SA4: handles Stage 2 for some WIDs (for which SA4 might rely on CT WGs for Stage 3), and Stage 3 for a majority of its WIDs. Stage 2 WIDs in SA4 are clearly identified as such and have the same deadline as SA2/SA6’s date.
  SA5: handles Stages 1, 2 and 3 for all its WIDs. Stage 1 for SA5 is 4 quarters after SA1’s date. Stage 2 for SA5 is 2 quarters after SA2/SA6’s date. Stage 3 for SA5 is same date as CT WGs’ date.
  For SA3, SA4 and SA5, the completion date for all WIDs dealing with Stage 3 (fully or partially) is the same as for CT WGs.
  In this Work Plan review slides, SA3, SA4 and SA5 are reported in the “Stage 3” slides since their overall completion date is aligned with (CT’s) Stage 3. Except for SA4’s Stage 2-only WIDs but this cannot be handled by the present tools.
RAN has a slightly different process. RAN defines two dates:
  The “RAN Content Definition”, which is the same date as SA Stage 1 and SA content definition
  The “RAN Completion”, which is the same date as SA/CT’s Stage 3
  Note that there is no specific RAN-equivalent date for SA/CT’s Stage 2