## Slide 1: SP-180568 Visualisation of Focus Area time planning Qualcomm Incorporated

## Slide 2: SA Focus Areas
SA2 is in overload
SA leadership has committed that “SA will strive to identify and agree to the most essential system-level focus areas (with impacts both on RAN and non-RAN aspects of the system) to include in Release 16”
Sufficient contributions have been received at SA#80 to at least agree on a set of Focus Areas and the corresponding existing or predicted SA2 studies and work items
Can SA do more?
What are our objectives?

## Slide 3: Key issues
SA wants to ensure alignment with RAN and to ensure the optimal output from the WGs in Release 16
SA want to ensure that certain features are guaranteed* to be delivered by the WGs
SA would like to avoid:
  SA2 spending such limited time on every agreed Study that nothing concludes
  No time for further SA1 output to be supported in SA2
  Continuing SA2 overload
* Guarantee means that sufficient time is allocated to ensure that all documents can be handled at each WG meeting,
What goals does SA have?

## Slide 4: Fundamental points
SA2 has a finite time budget
  For the next quarter, maximum number of sessions available is 168 (42 sessions per meeting, 4 meetings)
  This remains constant despite any prioritisation
Maintenance needs protected time
  TEI = 2 TU
  5GS_Ph1 = 44 TU
  Other = 12 TU
  This should not be reduced to accommodate studies
There are SA1 work & study items which will likely produce normative requirements by SA#82
  LUCIA QoS_Mon
  FS_ID_UAS BMNS
  FS_5GMSG

## Slide 5: Option 1
SA selects the minimum set of work items corresponding to the Focus Areas with (almost) universal support
All other work remains open for SA2 leadership to allocate resources
SA plenary agrees the following work items to be corresponding to system-level Focus Areas:
    FS_5WWC
    FS_5G_URLLC
    FS_eSBA
    FS_CIoT_5G
    FS_Vertical_LAN
    FS_eV2XARC
Lightest touch
Focus Areas:
FS_5WWC 7
FS_5G_URLLC 8
FS_eSBA 12
FS_CIoT_5G 14
FS_Vertical_LAN 8
FS_eV2XARC 10

## Slide 6: Option 1
Lightest touch
Focus Areas:
FS_5WWC 7
FS_5G_URLLC 8
FS_eSBA 12
FS_CIoT_5G 14
FS_Vertical_LAN 8
FS_eV2XARC 10
168 TU
Other maintenance
12 TU
TEI
2 TU
5GS_Ph1 maintenance
44 TU
59 TU
35%
34%
31%
Focus Areas
SA2 freedom
Maintenance
& TEI

## Slide 7: Option 2
SA selects the minimum set of work items corresponding to the Focus Areas with strong vendor support
All other work remains open for SA2 leadership to allocate resources
SA plenary agrees the following work items to be corresponding to system-level Focus Areas:
  FS_5G_URLLC FS_eSBA
  FS_Vertical_LAN FS_CIoT_5G
  FS_eV2XARC FS_ETSUN
  FS_5WWC FS_eNS
  FS_ATSSS FS_eNA
  FS_eLCS FS_RACS
Vendor paper
Focus Areas:
FS_5G_URLLC 8
FS_Vertical_LAN 8
FS_eV2XARC 10
FS_5WWC 7
FS_ATSSS 4
FS_CIoT_5G 14
FS_eSBA 12
FS_ETSUN 5.5
FS_eNS 6
FS_eLCS 4
FS_eNA 10
FS_RACS 4

## Slide 8: Option 2
Vendor paper
168 TU
Other maintenance
12 TU
TEI
2 TU
5GS_Ph1 maintenance
44 TU
92.5 TU
55%
34%
11%
Focus Areas
SA2 freedom
Maintenance
& TEI
Focus Areas:
FS_5G_URLLC 8
FS_Vertical_LAN 8
FS_eV2XARC 10
FS_5WWC 7
FS_ATSSS 4
FS_CIoT_5G 14
FS_eSBA 12
FS_ETSUN 5.5
FS_eNS 6
FS_eLCS 4
FS_eNA 10
FS_RACS 4

## Slide 9: Option 3
SA selects the minimum set of work items corresponding to the Focus Areas with strong vendor support
SA then selects a set of non-Focus Area topics to prioritise in the next quarter, all other items are not allocated time until SA#81
Full SA2 pipeline
Focus Areas:
FS_5WWC 7
FS_5G_URLLC 8
FS_eSBA 12
FS_CIoT_5G 14
FS_Vertical_LAN 8
FS_eV2XARC 10
Priority topics:
FS_eNS
FS_ATSSS
FS_eNA
FS_eLCS
FS_RACS
FS_ETSUN
FS_5GSAT_ARC

## Slide 10: Option 3
Full SA2 pipeline
Focus Areas:
FS_5WWC 7
FS_5G_URLLC 8
FS_eSBA 12
FS_CIoT_5G 14
FS_Vertical_LAN 8
FS_eV2XARC 10
168 TU
Other maintenance
12 TU
TEI
2 TU
5GS_Ph1 maintenance
44 TU
59 TU
35%
34%
30%
Focus Areas
Priority topics
Maintenance
& TEI
Priority topics:
FS_eNS 6
FS_ATSSS 4
FS_eNA 10
FS_eLCS 4
FS_eIMS5G 6
FS_FLADN 3
FS_RACS 4
FS_ETSUN 5.5
FS_5GSAT_ARC 6
SRVCC 2
50.5 TU

## Slide 11: Observations
SA2 cannot progress everything to completion
Focus Area item agreement is essential to protect critical work
Somewhere, some studies will not receive the time allocation that they need for their current scope
There are some low-hanging fruit of work which can be completed with limited time allocation
Filling the SA2 pipeline completely until SA#81 will require that certain studies have no time allocated in the next quarter, for example:
    xBDT FS_AAI_LTE_NR
    FS_UDM_Migrate FS_LLC_Mob
    FS_NG_RTC FS_ENTRADE
    FS_EPS_URACE

## Slide 12: Proposal
SA2 rapporteurs can downscope non-Focus Area items to allow more studies to be progressed
  Not on the table for SA#80
The SA2 leadership should have the freedom to schedule work beyond the Focus Areas for the next quarter which could deliver RAN alignments, quick wins, early study conclusions, downscoping agreements, or other progress
Therefore taking an approach at SA#80 which allows the rapporteurs and SA2 leadership the latitude to discuss the scope of any ongoing work whilst guaranteeing time for Focus Area items provides the best compromise between SA commitment and SA2 freedom
How do we achieve our goals?

## Slide 13: Proposal
Option 1 has the potential for chaos in SA2 outside of the reserved time for Focus Area topics and maintenance
  Too much time interleaving over too many agreed projects will lead to a lack of concrete progress
Option 3 requires SA approval to put many agreed SA2 items on hold (no allocated time units)
  This looks like SA micromanagement and companies have not prepared input contributions to this level of detail
Therefore SA should proceed with Option 2 as detailed in this paper
How do we achieve our goals?