## Slide 1
Puneet Jain
SA2 Chairman, Intel
SA2 Rel-17 Prioritization
Way Forward

## Slide 2: Rel-17 High Level Principles
Prioritization is based on 15-Month timeline agreed in SA#83 i.e. targeting Stage 2 completion in Sep, 2020.
    NOTE 1: The Rel-17 timeline can be adjusted in Dec, 19. Any adjustment in Rel-17 prioritization due to change in Rel-17 timeline will be discussed in Dec, 19.
Prioritization is based on SA2 TU estimates endorsed (in S2-1908590) for Rel-17 prioritization.
    NOTE 2: Any necessary adjustments (e.g. reshuffling of TUs between quarters) and down-scoping of prioritized WIDs can be left to SA2.
Rel-17 prioritization adjustment may be discussed at SA#86 (e.g. due to change in Rel-17 timeline and/or new WID approval between SA#85 and SA#86 and cross RAN/SA Rel-17 alignment).
pre-Rel-17 maintenance work (i.e. essential corrections and alignment work with other WGs) shall be highest priority.

## Slide 3: WIDs - IN
Following items are proposed to be included as part of Rel-17 work in SA2
WI Code | TUs Requested | TU Granted
FS_enh_EC | 19 | 19
FS_eNPN | 10.5 | 10.5
FS_eNS_Ph2 | 9 | 9
FS_IIoT | 9 | 9
5G_AIS | 2 | 2
FS_MUSIM | 7 | 7
Total TUs | 56.5 | 56.5
FS_5GSAT_ARCH is allocated 2 TUs for normative work that were not originally estimated.
Total TU = 56.5

## Slide 4: WIDs – IN (with rescoping)
Following items are proposed to be included as part of Rel-17 work in SA2
SA2 will undertake rescoping exercise to limit scope of WIDs to the TU granted
FS_eNA_ph2 is limited to 20 TU though as part of Work task estimate was 23 TU.
FS_5GSAT_ARCH is allocated 2 TUs for normative work that were not originally estimated.
Total TUs = 75
WI Code | TUs Requested | TU Granted
FS_5MBS | 26 | 20 (?)
FS_5G_ProSe | 32* | 20
FS_eNA_ph2 | 23* | 20
FS_5GSAT_ARCH | 3+2* | 5
UPCAS | 17 | 10
Total TUs | 86 | 75

## Slide 5
Thank You!