## Slide 1
Puneet Jain
SA2 Chairman, Intel
Maurice Pope
SA2 Support, MCC
SA2 Status Report to
TSG SA#86

## Slide 2: Contents
1) General aspects (events since SA#85, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Study/Work
  2.5) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA

## Slide 3: Contents
1) General aspects (events since SA#85, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Study/Work
  2.5) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 4: 1) General Aspects (1/7)
SA2 meetings held since SA#85
  SA2#135: 14 – 18 Oct 2019, Split, Croatia
  SA2#136: 18 – 22 Nov 2019, Reno, NV, USA
Future SA2 meetings
  SA2#136AH: 13 – 17 Jan 2020, Incheon, Korea
  SA2#137: 24 – 28 Feb 2020, New Delhi, India

## Slide 5: 1) General Aspects (2/7)
SA2 WG leadership
  Chairman: Puneet Jain (Intel)
  Vice Chairmen: Tao Sun (CMCC), Andrew Bennett (Samsung)
  Secretary: Maurice Pope (MCC)
Parallel sessions held in the last plenary cycle
  SA2 has one main session and 2 parallel sessions for most part.
  Many thanks to Maurice Pope and parallel session chairs, Andrew Bennett, Tao Sun, and LaeYoung Kim for their outstanding support!

## Slide 6: 1) General Aspects (3/7)
Statistics at SA WG2 #135:
189 delegates ‘attended’ (checked-in) SA WG2 #135
  2116 documents, 1767 Tdocs handled (including revisions), including
    1152 CRs (including revisions)
    113 Incoming LSs, of which 32 were postponed
    42 Outgoing LSs Approved
  473 Tdocs postponed / not handled
Total CRs agreed: 251 (of which, 39 were further revised/agreed at SA WG2#136)
Statistics at SA WG2 #136:
241 delegates ‘attended’ (checked-in) SA WG2 #136
  1876 documents, 1527 Tdocs handled (including revisions), including
    1024 CRs (including revisions)
    76 Incoming LSs, of which 25 were postponed
    32 Outgoing LSs Approved
  349 Tdocs postponed / not handled
Total CRs agreed: 272 (of which, 11 received objections)
753 people registered on the SA WG2 e-mail reflector on 29 November 2019

## Slide 7: 1) General Aspects (4/7)
Chart: SA WG2 meeting attendance
| 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 113AH | 114 | 115 | 116 | 116bis | 117 | 118 | 118bis | 119 | 120 | 121 | 122 | 122bis | 123 | 124 | 125 | 126 | 127 | 127bis | 128 | 128bis | 129 | 129bis | 130 | 131 | 132 | 133 | 134 | 135 | 136
attended | 135 | 142 | 139 | 173 | 181 | 165 | 158 | 153 | 189 | 146 | 133 | 145 | 142 | 144 | 195 | 159 | 175 | 182 | 113 | 137 | 200 | 137 | 107 | 157 | 168 | 169 | 143 | 157 | 233 | 182 | 175 | 191 | 188 | 156 | 154 | 156 | 222 | 196 | 174 | 149 | 140 | 152 | 149 | 165 | 191 | 153 | 178 | 279 | 280 | 229 | 189 | 241

## Slide 8: 1) General Aspects (5/7) Resource usage
SA2 meetings
Number of Sessions
Chart: 
| #117 Oct | #118 Nov | #118bis Jan | #119 Feb | #120 Mar | #121 May | #122 Jun | #122bis Aug | #123 Oct | #124 Nov | #125 Jan | #126 Feb | #127 Apr | #127bis May | #128 Jul | #128bis Aug | #129 Oct | #129bis Nov | #130 Jan | #131 Feb | #132 Apr | #133 May | #134 Jun | #135 Oct | #136 Nov
maintenance | 5 | 6 | 5 | 6 | 6.7 | 6.5 | 6 | 3.4 | 5 | 3 | 4.5 | 3.8 | 4 | 4 | 1.5 | 1.2 | 3 | 1.5 | 0.9 | 0.9 | 2 | 0.9 | 3.5 | 2.1 | 1.6
Rel-15 5GS / maintenance | 18 | 23 | 24 | 27 | 31 | 32.5 | 36 | 37 | 24 | 25 | 19 | 19 | 15 | 15 | 13.7 | 11.5 | 9 | 9.3 | 8.2 | 7.2 | 6 | 8.9 | 7.7
Rel-16 work | 3.7 | 13.5 | 12 | 19.5 | 20 | 26.4 | 28.6 | 31.2 | 34.9 | 34.9 | 34.4 | 35.3 | 37.7 | 33 | 21 | 23.2
Rel-17 work | 10.8 | 11

## Slide 9: 1) General Aspects (6/7) Document Handling / Meeting
Number of Tdocs
Rel-12
Rel-11
Rel-14
Rel-13
Rel-15
Rel-16
Rel-17
Chart: 
| 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 101b | 102 | 103 | 104 | 105 | 106 | 107+E | 108 | 109 | 110 | 110AH | 111 | 112 | 113 | 113AH | 114 | 115 | 116 | 116bis | 117 | 118 | 118bis | 119 | 120 | 121 | 122 | 122bis | 122e | 123 | 124 | 125 | 126 | 127 | 127bis | 128 | 128bis | 129 | 129bis | 130 | 131 | 132 | 133 | 134 | 135 | 136
#approved/endorsed/merged (total) | 108 | 117 | 115 | 134 | 147 | 170 | 168 | 165 | 134 | 123 | 56 | 145 | 150 | 130 | 212 | 198 | 162 | 162 | 168 | 161 | 61 | 151 | 175 | 180 | 87 | 86 | 224 | 278 | 317 | 158 | 210 | 151 | 224 | 269 | 264 | 311 | 368 | 67 | 414 | 467 | 399 | 516 | 483 | 434 | 364 | 423 | 427 | 503 | 407 | 432 | 417 | 561 | 446 | 508 | 480
#not handled, postponed | 77 | 149 | 91 | 138 | 144 | 124 | 101 | 131 | 117 | 23 | 3 | 49 | 63 | 72 | 70 | 66 | 73 | 74 | 65 | 27 | 34 | 145 | 112 | 120 | 35 | 120 | 90 | 53 | 52 | 166 | 108 | 122 | 178 | 254 | 254 | 188 | 200 | 2 | 148 | 85 | 176 | 154 | 186 | 189 | 170 | 185 | 188 | 160 | 133 | 193 | 274 | 154 | 265 | 473 | 351
#noted | 120 | 139 | 155 | 131 | 123 | 121 | 110 | 165 | 172 | 141 | 62 | 95 | 137 | 143 | 143 | 143 | 141 | 120 | 77 | 65 | 38 | 103 | 78 | 124 | 43 | 112 | 137 | 119 | 131 | 70 | 97 | 95 | 101 | 138 | 142 | 119 | 109 | 7 | 163 | 137 | 142 | 137 | 132 | 183 | 113 | 90 | 132 | 158 | 124 | 138 | 216 | 198 | 181 | 177 | 187

## Slide 10: 1) General Aspects (7/7) SA2 Agreed CRs by Release / Meeting
Rel-12
Rel-11
Rel-14
Rel-13
Rel-15
Rel-16
Rel-17
Chart: 
| 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107+E | 108 | 109 | 110 | 110AH | 111 | 112 | 113 | 113AH | 114 | 115 | 116 | 116bis | 117 | 118 | 118bis | 119 | 120 | 121 | 122 | 122bis | 122e | 123 | 124 | 125 | 126 | 127 | 127bis | 128 | 128bis | 129 | 129bis | 130 | 131 | 132 | 133 | 134 | 135 | 136
Rel-12 CR | 2 | 2 | 4 | 11 | 8 | 19 | 21 | 35 | 50 | 38 | 64 | 55 | 39 | 35 | 34 | 21 | 11 | 10 | 9 | 1 | 9 | 3 | 3 | 3 | 1
Rel-13 CR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 10 | 19 | 13 | 14 | 6 | 9 | 56 | 25 | 58 | 73 | 41 | 11 | 35 | 29 | 25 | 25 | 9 | 11 | 2 | 5 | 2 | 4 | 2 | 5 | 3 | 1 | 1 | 1 | 1 | 0 | 1
Rel-14 CR | 4 | 21 | 69 | 81 | 33 | 56 | 23 | 13 | 17 | 18 | 20 | 10 | 8 | 10 | 8 | 1 | 7 | 2 | 1 | 2 | 5 | 1 | 1 | 1
Rel-15 PCR/draftCR | 63 | 126 | 117 | 121 | 171 | 214 | 62 | 287 | 328 | 182 | 4 | 0 | 0
Rel-15 CR | 19 | 19 | 27 | 27 | 12 | 351 | 201 | 213 | 119 | 159 | 100 | 102 | 78 | 74 | 50 | 40 | 17 | 6 | 10
Rel-16 PCR/draftCR | 43 | 80 | 170 | 147 | 181 | 171 | 207 | 250 | 88 | 87 | 71 | 103 | 26 | 39 | 30
Rel-16 CR | 2 | 3 | 66 | 133 | 117 | 233 | 279 | 205 | 260
Rel-17 PCR/draftCR | 48 | 55
Number of CRs

## Slide 11: Contents
1) General aspects (events since SA#84, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Study/Work
  2.5) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 12: 2.1) Rel-14 and before Maintenance (1/1)
Work Progress on Corrections (Category A CRs are not counted)
  R12: none
  R13: 1 CR
  R14: 2 CRs

## Slide 13: Contents
1) General aspects (events since SA#84, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2 Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Study/Work
  2.5) IETF Dependency Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 14: 2.2) Rel-15 Work and Maintenance (1/2)
WI | Work Item | WP | CRs approved
VoWLAN | Complementary Features for Voice services over WLAN | 100% | 0
ProSe_WLAN_DD_Stage2 | Inclusion of WLAN direct discovery technologies as an alternative for ProSe direct discovery | 100% | 0
NAPS | Northbound APIs for SCEF – SCS/AS Interworking | 100% | 1
eVoLP | enhanced VoLTE performance | 100% | 0
USOS | Unlicensed spectrum offloading system enhancements | 100% | 0
EDCE5 | EPC enhancements to support 5G New Radio via Dual Connectivity | 100% | 4
PS_Data_Off_Phase2 | PS Data Off Feature Phase 2 | 100% | 0
EPS_URLLC | EPC support for E-UTRAN Ultra Reliable Low Latency Comm. | 100% | 0

## Slide 15: 2.2) Rel-15 Work and Maintenance (2/2)
Progress since SA#85:
  CRs agreed for TS 23.501 (46 CRs), TS 23.502 (45 CRs), TS 23.503 (13 CRs)
  2 CRs agreed for TS 23.401
Next steps:
  FASMO corrections
  Further aligning with the work from other WGs
WI Code | Work Item Title | WP | Target Date | WID#
5GS_Ph1 | 5G System – Phase 1 | 100% | Dec, 17 | SP-160958

## Slide 16: Contents
1) General aspects (events since SA#84, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Study/Work
  2.5) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 17: 2.3) Rel-16 Work and Maintenance (1/17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_PARLOS_SA2 | Study on System enhancements for Provision of Access to Restricted Local Operator Services by Unauthenticated UEs | 100 > 100% | Sep, 18 | SP-180501
PARLOS | System enhancements for Provision of Access to Restricted Local Operator Services by Unauthenticated UEs | 100 > 100% | Mar, 19 | SP-180738
Progress since SA#85:
  5 CRs agreed at SA2
  RAN impacts or dependencies:
  None identified
Next steps:
  Maintenance

## Slide 18: 2.3) Rel-16 Work and Maintenance (2/17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5WWC | Study on the Wireless and Wireline Convergence for the 5G system architecture | 100 > 100% | Dec, 18 | SP-170380
5WWC | Wireless and Wireline Convergence for the 5G system architecture | 100 > 100% | Jun, 19 | SP-181117
Progress since SA#85:
  Exception requested at SA#84 were completed.
  Procedures for the Non-3GPP device not supporting NAS connected to a Trusted Non-3GPP Access Network.
  for 5G-RG the specification related to Policy management as defined in TS 23.503
  Complete support of FN-RG
  Completed definition of support of IPTV
  RAN impacts or dependencies:
  specification of N2 (NGAP) extension
Next steps:
  Maintenance

## Slide 19: 2.3) Rel-16 Work and Maintenance (3/17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_ATSSS | Study on Access Traffic Steering, Switch and Splitting support in the 5G system architecture | 100 > 100% | Dec, 18 | SP-180732
ATSSS | Access Traffic Steering, Switch and Splitting support in the 5G system architecture | 100 > 100% | Jun,19 | SP-181124
Progress since SA#85:
  The following 3 out of 4 controversial issues have been resolved and agreed
    MPTCP Link-local Multi-path IP Addressing clarifications and assignment
    Support for Non MPTCP traffic
    Policy control for ATSSS functionalities.
  RAN impacts and dependencies:
  None identified
Next steps:
  Resolve the remaining controversial issue (CT1 is awaiting SA2’s decision) - inter-release compatibility support for ATSSS during inter-PLMN home routed scenario
  Maintenance

## Slide 20: 2.3) Rel-16 Work and Maintenance (4/17)
Progress since SA#85:
  Maintenance work and alignments with the work from other WGs.
  28 CRs to TS 23.287, 3 CRs to TS 23.285 and 8 CRs to TS 23.501/502/503 agreed.
  1 CR to TS 23.502 (with 5G_URLLC & eV2XARC WI code) and 1 CR to TS 23.288 (with eNA & eV2XARC WI code) agreed regarding Uu QoS.
RAN impacts or dependencies:
  NR PC5 unicast/groupcast/broadcast (e.g. PC5 QoS handling details)
  Enhancements to QoS handling for Uu communication
Next steps:
  Maintenance and aligning with the work from other WGs.
WI Code | Work Item Title | WP | Target Date | WID#
FS_eV2XARC | Study on architecture enhancements for 3GPP support of advanced V2X services (FS_eV2XARC) | 100 > 100% | Dec, 18 | SP-180733
eV2XARC | Architecture enhancements for 3GPP support of advanced V2X services (eV2XARC) | 90 > 96% | Jun, 19 | SP-181121

## Slide 21: 2.3) Rel-16 Work and Maintenance (5/17)
Progress since SA#85:
  Made good progress in resolving Editor's notes and only one Editor's notes remains related to SA WG5
RAN impacts or dependences:
  None identified
Next steps:
  Maintenance
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNA | Study of enablers for Network Automation for 5G | 100 > 100% | Dec, 18 | SP-180792
eNA | Enablers for Network Automation for 5G | 92 > 97% | Jun, 19 | SP-181123

## Slide 22: 2.3) Rel-16 Work and Maintenance (6/17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_CIoT_5G | Study on Cellular IoT support and evolution for the 5G System | 100 > 100% | Dec, 18 | SP-180614
5G_CIoT | Cellular IoT support and evolution for the 5G System | 100 > 100% | Jun, 19 | SP-181118
Progress since SA#85:
  All outstanding issues reported during SA#85 (EDT for 5GS UP optimisation, LTE-M identification and event exposure for downlink data delivery failure when buffering in UPF) have been addressed
  RAN impacts or dependencies:
  Support of NB-IoT/eMTC connected to 5GC, impacts due to Data over NAS and UP optimisation, MO/MT EDT, eDRX, Inter-UE QoS for CP Optimisation, Enhanced Coverage, Expected UE behavior signaling to RAN, signaling of CIoT feature support, LTE-M identification.
Next steps:
  Maintenance

## Slide 23: 2.3) Rel-16 Work and Maintenance (7/17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_ETSUN | Study on Enhancing Topology of SMF and UPF in 5G Networks | 100 > 100% | Dec, 18 | SP-180731
ETSUN | Enhancing Topology of SMF and UPF in 5G Networks | 100 > 100% | Jun, 19 | SP-181116
Progress since SA#85:
  15 CR(s) agreed at SA2
  RAN impacts and dependencies:
  None identified
Next steps:
  Maintenance

## Slide 24: 2.3) Rel-16 Work and Maintenance (8/17)
Progress since SA#85:
  Corrections to procedures and NF service, e.g. Deferred 5GC-MT LR procedures; and resolved Editor’s Notes.
  Topic “Using slice information for LMF selection” discussed in both 2 meetings, No conclusion reached on solutions.
RAN impacts or dependencies:
  None Identified
Next steps:
  Maintenance
WI Code | Work Item Title | WP | Target Date | WID#
FS_eLCS | Study on Enhancement to Service Based Architecture for Location Services | 100 > 100% | Mar, 19 | SP-180734
5G_eLCS | Enhancement to Service Based Architecture for Location Services | 100 > 100% | Jun, 19 | SP-181119

## Slide 25: 2.3) Rel-16 Work and Maintenance (9/17)
Progress since SA#84:
  Outstanding issue of UCMF-AMF interaction for deletion/revocation of PLMN assigned UE Radio Capability IDs is resolved. TAC is replaced with vendor id as part of manufacturer assigned UE Radio Capability and version ID added in UE Radio Capability ID.
  Related LSs send to CT4
RAN impacts or dependencies:
  As per SA2 agreed CRs
Next steps:
  Maintenance
WI Code | Work Item Title | WP | Target Date | WID#
FS_RACS | Study on optimisations on UE radio capability signalling | 100 > 100% | Dec, 18 | SP-180599
RACS | Optimisations on UE radio capability signalling | 100 > 100% | Jun, 19 | SP-190180

## Slide 26: 2.3) Rel-16 Work and Maintenance (10/17)
Progress since SA#85:
  5G-LAN (100%) – Corrections and clarifications related to AF influence, SMF/UPF management and selection for 5G VN groups.
  NPN (100%) - Extensive time and effort spent in responding to LS from other WGs for further clarity on features supported with SNPN, PNI-NPN. Also, added support of IMSI for SNPN.
  TSC (100%) – Resolved opens related to IEEE TSN specification (for which SA2 sent an LS to IEEE), and LLDP and bridge management aspects were also resolved.
RAN impacts or dependencies:
  Presence of CAG ID in the AS signaling is an open item to be resolved for clarity and alignment between various groups (RAN2, RAN3, SA2, SA3).
Next steps:
  Maintenance. Response and resolution to potential LS from SA3, CT1, RAN2/3, IEEE on NPN and TSC aspects, maintenance and alignment work expected.
WI Code | Work Item Title | WP | Target Date | WID#
FS_Vertical_LAN | Study on 5GS Enhanced support of Vertical and LAN Services | 100 > 100% | Dec, 18 | SP-180507
Vertical_LAN | 5GS Enhanced support of Vertical and LAN Services | 97 > 100% | Jun, 19 | SP-181120

## Slide 27: 2.3) Rel-16 Work and Maintenance (11/17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_URLLC | Study on enhancement of URLLC supporting in 5GC | 100 > 100% | Jun, 19 | SP-180118
5G_URLLC | Enhancement of URLLC supporting in 5GC | 100 > 100% | Jun, 19 | SP-181122
Progress since SA#85:
  14 CRs were approved.
  LSs with CT WGs and RAN3 on stage 3 work and coordination.
RAN impacts and dependencies:
  An LS from RAN3 on Redundant use plane based on DC was discussed in SA2 and concluded without additional enhancement in Rel-16.
Next steps:
  Maintenance

## Slide 28: 2.3) Rel-16 Work and Maintenance (12/17)
Progress since SA#85:
  Correction of context transfer, Notification, Group ID and Set ID, Notification receiver information in a subscription
  UDR group ID mapping
  Response to SA3(token-based authorization), CT4 (on Binding indication for subscribe/notify), Consumer/Producer binding for subscribe/notify
RAN impacts or dependencies:
  None identified
Next steps:
  Maintenance
WI Code | Work Item Title | WP | Target Date | WID#
FS_eSBA | Study on Enhancements to the Service-Based 5G System Architecture | 100 > 100% | Dec, 18 | SP-180231
5G_eSBA | Enhancements to the Service-Based 5G System Architecture | 100 > 100% | Jun, 19 | SP-181125

## Slide 29: 2.3) Rel-16 Work and Maintenance (13/17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNS | Study on Enhancement of Network Slicing | 100 > 100% | Dec. 18 | SP-180503
eNS | Enhancement of Network Slicing | 100 > 100% | Jun. 19 | SP-181232
Progress since SA#85:
  Completed stage-2 procedure for slice-specific security support based on feedback from SA3
  RAN impacts and dependencies:
  None
Next steps:
  Maintenance
  Resolve remaining EN based on feedback from SA3

## Slide 30: 2.3) Rel-16 Work and Maintenance (14/17)
Progress since SA#85:
  1 CR to 23.502 agreed.
RAN impacts or dependencies:
  None identified
Next steps:
  Maintenance
WI Code | Work Item Title | WP | Target Date | WID#
FS_UDICoM | Study on User data interworking, Coexistence and Migration | 100 > 100% | Jun, 19 | SP-190148
UDICoM | User data interworking, Coexistence and Migration | 100 > 100% | Jun, 19 | SP-190182

## Slide 31: 2.3) Rel-16 Work and Maintenance (15/17)
Progress since SA#85:
  1 CR to TS 23.502 and 1 CR to TS 23.503 agreed.
RAN impacts or dependencies:
  None identified
Next steps:
  Maintenance
WI Code | Work Item Title | WP | Target Date | WID#
xBDT | 5GS Transfer of Policies for Background Data Transfer | 100 > 100% | Dec, 19 | SP-180509

## Slide 32: 2.3) Rel-16 Work and Maintenance (16/17)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eIMS5G | Study on Enhanced IMS to 5GC Integration | 70 > 100% | Jun, 19 | SP-180736
eIMS5G_SBA | SBA aspects of enhanced IMS to 5GC integration | 100 > 100% | Jun, 19 | SP-190181
Progress since SA#85:
  UDR service for HSS discovery agreed and CRs produced.
  Maintenance conducted to clarify SBA aspects of IMS (including cleanup of service names).
  Remaining FS_eIMS5G study items transitioned to CT (based on SA release 17 prioritization) and TR 23.794 sent to SA for approval at this meeting with only minor update since last presentation.
  RAN impacts and dependencies:
  None.
Next steps:
  Maintenance.

## Slide 33: 2.3) Rel-16 Work and Maintenance (17/17)
WI Code | Work Item Title | WP | Target Date | WID#
IABARC | Architecture enhancements for the support of Integrated access and backhaul (IAB) | 33 > 100% | Dec, 19 | SP-190627
Progress since SA#85:
  IAB support in Registration procedure and corresponding subscription information in 5GS were added;
  IAB support in Attach procedure and corresponding subscription information in EPS were added;
  Reuse of the existing 5QI and QCI for OAM traffic;
  Limit the mobility support (system level service continuity is not guaranteed to UE when IAB-node changes donor-gNBs);
  Rename the MT in IAB node to IAB-UE.
  RAN impacts and dependencies:
  None. (RAN WGs may provide further feedbacks.)
Next steps:
  Maintenance based on inputs from other working groups.

## Slide 34: Contents
1) General aspects (events since SA#84, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Work and Maintenance
  2.3) Rel-16 Work and Maintenance
  2.4) Rel-17 Study/Work
  2.5) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 35: 2.4) Rel-17 Study/Work (1/10)
Progress since SA#85:
  A new KI agreed on Regulatory services with super-national satellite ground station
  40 pCRs agreed on updating solutions, evaluations and conclusions
  TR 23.737 (SP-191095) is submitted for Approval
  New WID (SP-191101) on Integration of satellite systems in the 5G architecture is submitted for Approval
RAN impacts or dependencies:
  Conclusions for some KI issues (such as Mobility for Large coverage areas or with moving tracking areas, or , Regulatory services with super-national satellite ground station) have to be evaluated by RAN2/RAN3 and SA3-LI, in particular for what concerns mobility management (Earth fixed or Moving Tracking areas) and handling of Regulatory Services.
Next steps:
  Address dependencies from RAN through following evaluation of solutions as requested in corresponding LSs.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5GSAT_ARCH | Study on architecture aspects for using satellite access in 5G | 70 > 85% | Dec, 19 | SP-181253

## Slide 36
WI Code | Work Item Title | WP | Target Date | WID#
FS_enh_EC | Study on enhancement of support for Edge Computing in 5GC | 0 > 20% | Mar, 2020 | SP-190185
Progress since SA#85:
  Architecture assumption and 5 key issues are captured in the TR 23.748.
RAN impacts and dependencies:
  None identified
Next steps:
  Collect further key issues and refine existing key issues.
  Develop solutions.
2.4) Rel-17 Study/Work (2/10)

## Slide 37: 2.4) Rel-17 Study/Work (3/10)
Progress since SA#85:
  4 Key Issues agreed in TR 23.700-20
  3 Solutions agreed for two Key Issues.
  Revised WID submitted for Approval (SP-191098).
RAN impacts or dependencies:
  Possible impacts to be determined based on solution discussion, especially related to distributed model and/or Time Sync.
Next steps:
  Completion of Key Issues in January.
  Complete solution, evaluation and conclusion(s) for each Key Issue.
WI Code | Work Item Title | WP | Target Date | WID#
FS_IIoT | Study on enhanced support of Industrial IoT - TSC/URLLC enhancements | 0 > 20% | Mar, 20 | SP-180932

## Slide 38: 2.4) Rel-17 Study/Work (4/10)
Progress since SA#85:
  Work assumptions to take Rel16 V2X as baseline was agreed.
  8 key isues were agreed for inclusion in TR 23.752.
  7 solutions covering direct discovery, direct communication and UE-to-Network Relay were captured in TR 23.752.
  Revised WID (SP-191096) submitted for Approval to include REFEC requirements.
RAN impacts or dependencies:
  Layer-2 Relay depends on RAN#86 decision.
Next steps:
  Continue the study.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 0 > 30% | June, 20 | SP-190443

## Slide 39: 2.4) Rel-17 Study/Work (5/10)
WI Code | Work Item Title | WP | Target Date | WID#
FS_MUSIM | Study on system enabler for Multi-USIM devices | 0 > 29% | Mar, 20 | SP-190248
Progress since SA#85:
  4 key issues and 3 solutions agreed for inclusion in TR 23.761.
  RAN impacts and dependencies:
  At least one key issue (Handling of MT service) has RAN dependency.
Next steps:
  Continue the study.
  Conclude whether the study should include optimizations for the case where multiple USIMs are served by the same network.

## Slide 40: 2.4) Rel-17 Study/Work (6/10)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 0 > 15% | Jun, 2020 | SP-190625
Progress since SA#85:
  TR 23.757 skeleton, scope, main architectural assumptions and 8 key issues were agreed.
  RAN impacts and dependencies:
  To be determined: Potential impacts on RAN depend on solutions.
Next steps:
  Completion of Key Issues in January.
  Complete solution(s), evaluation and conclusion(s) for each Key Issue.

## Slide 41: 2.4) Rel-17 Study/Work (7/10)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNS_Ph2 | Study on Enhancement of Network Slicing Phase 2 | 0 > 15% | Mar, 20 | SP-190628
Progress since SA#85:
  5 Key Issues have been agreed for inclusion in TR 23.700-40
  4 solutions for KI#1 agreed.
  LS has been sent to GSMA to seek clarification and to state SA2’s architecture working assumptions.
  RAN impacts and dependencies:
  None identified
Next steps:
  Continue the study

## Slide 42: 2.4) Rel-17 Study/Work (8/10)
Progress since SA#85:
  4 use cases and 12 Key Issues agreed in TR 23.700-91
  Lengthy discussion of NWDAF-assisted energy saving occurred and Liaison Statement sent to SA plenary for guidance
RAN impacts or dependencies:
  Regarding KI#8: UE data as an input for analytics generation, the method of collection of RAN impacting parameters from the UE will be investigated after the MDT work of TSG RAN is completed
Next steps:
  Completion of Key Issues in January.
  Complete solution(s), evaluation and conclusion(s) for each Key Issue.
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNA_Ph2 | Study on Enablers for Network Automation for 5G - phase 2 | 0 > 15% | Mar, 20 | SP-190557

## Slide 43: 2.4) Rel-17 Study/Work (9/10)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN | Enhanced support of Non-Public Networks | 0 > 15% | Mar, 20 | SP-190453
Progress since SA#85:
  6 Key Issues have been agreed for inclusion in TR 23.700-07
  1 solution for KI#1 agreed.
  Revised WID submitted for Approval (SP-191100) adding one objective and changing target date
  RAN impacts and dependencies:
  For KI#5 RAN impacts assumed to be same as for equivalent PLMNs
  Unknown for other KIs
Next steps:
  Completion of Key Issues in January.
  Complete solution(s), evaluation and conclusion(s) for each Key Issue.

## Slide 44: 2.4) Rel-17 Study/Work (10/10)
WI Code | Title | Doc# | Target Date
5G_AIS | 5G System Enhancement for Advanced Interactive Services | SP-190564 | Mar-20
FS_eV2XARC_ph2 | Study on 3GPP support of advanced V2X services - Phase 2 | SP-190631 | Jun-20
Following items were not scheduled in Q4, 2019:

## Slide 45: Contents
1) General aspects (events since SA#84, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs and SIDs
  2.5) IETF and External SDO Normative Reference Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 46: 2.5) IETF and External SDO Normative Reference Update (1/1)
None identified

## Slide 47: Contents
1) General aspects (events since SA#84, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs and SIDs
  2.5) IETF Dependency Update
3) SA2 Work Planning
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 48: 3) SA2 Work Planning
SA2 endorsed work plan proposals (please see S2-1912781)
  SA2 July 2020 ad-hoc meeting was cancelled.
  Scheduling constraints continues to makes it difficult to schedule items in parallel.
  WT papers were agreed for all “in” and “in*” items providing more granular TU estimation.
  High Rel-16 maintenance load in Q4, 2019 and same anticipated in Q1, 2020. Given this, SA2 revised the maintenance TUs allocation for 2020 meetings.
  TUs for Rel-17 “In” Items were increased either due to increased in study scope, or due to better scheduling estimates.
Action to SA#86:
  SA#86 is requested to provide SA2 with list of Rel-17 study/work items to be prioritized in Rel-17 timeframe, taking SA2 endorsed work plan into consideration.

## Slide 49: Contents
1) General aspects (events since SA#84, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs and SIDs
  2.5) IETF Dependency Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 50: 4) Documents for Information and Approval (1/2)
TR/TS presentation for Approval
  SP-191094: TR 23.794 "Study on Enhanced IMS to 5GC Integration"
  SP-191095: TR 23.737 "Study on architecture aspects for using satellite access in 5G"

## Slide 51: 4) Documents for Information and Approval (2/2)
Rel-17 WID(s) for Approval
SA-TD | Type | WI Code | Title
SP-191096 | SID REVISED | FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS
SP-191097 | SID REVISED | FS_5GLAN_enh | Study on enhancement of support for 5G LAN-type service
SP-191098 | SID REVISED | FS_IIoT | Study on enhanced support of Industrial IoT - TSC/URLLC enhancements
SP-191099 | SID REVISED | FS_MPS2_St2 | Study on Multimedia Priority Service (MPS) Phase 2, Stage 2
SP-191100 | SID REVISED | FS_eNPN | Study on enhanced support of Non-Public Networks.
SP-191101 | WID NEW | 5GSAT_ARCH | Integration of satellite systems in the 5G architecture.

## Slide 52: Contents
1) General aspects (events since SA#84, statistics, next meetings)
2) SA Work Report
  2.1) Rel-14 and before Maintenance
  2.2) Rel-15 Maintenance and Work
  2.3) Rel-16 and later Work and Maintenance
  2.4) New and Updated WIDs and SIDs
  2.5) IETF Dependency Update
3) Action Items
4) Documents for Information and Approval
5) Collected Items requiring action from SA
è

## Slide 53: 5) Collected Items requiring action from SA
1) Approval of provided TR/TSs (please see slide 50)
2) Approval of new/revised WIDs (please see slide 51)
3) Provide SA2 with list of Rel-17 study/work items to be prioritized in Rel-17 timeframe, taking SA2 endorsed work plan into consideration (please see slide 48)

## Slide 54
Thank You!