## Slide 1: STF 576 Activity report
29.01.2020
ETSI Specialist Task Force 576
MTS #79

## Slide 2: Rationale and motivation
REST API specifications more and more relevant in ETSI Groups
  ISG Multi-access Edge Computing, ISG Network Function Virtualisation, ISG Zero-touch Service Management, ISG Cross-cutting Information Management, 3GPP CT & SA, OneM2M, …
Guidelines, methodologies and conventions needed
  Led to development of MEC 009, NFV-SOL 013 & 015, …
RESTful APIs specification
needs to be:
Fast;
Automatable;
Developer friendly.
An official ETSI guide on the topic
will support:
Consolidation of efforts
Delivery time
Standards quality (specification, testability, interoperability)

## Slide 3: DEG/MTS-203647: Methods for Testing and Specifications (MTS) Methodology for RESTful APIs specifications and testing
  Scope:
    The present document provide guidance and methodology for RESTful API specification and testing based on analysis of methods, languages and best practices used in the industry and in ETSI groups
  A work item in ETSI TC MTS Methods for Testing and Specification
  More information available here

## Slide 4: ETSI Specialist Task Force 576
“Survey of current work and definition of a methodology for specification and testing of RESTful APIs”
Experts:
    Martti Kaarik, Elvior
    Philip Makedonski, University Goettingen
    Sana Zulfiqar, xFlow Research
    Michele Carignani, ETSI Technical Expert

## Slide 5: Tasks and Time plan
Early Draft on 31/01/2020
Stable Draft on 15/05/2020
Final Draft on 30/06/2020
Phase 1
Phase 2
Phase 3

## Slide 6: Activity
4 Remote meetings held (since October 2019)
5 days F2F working session at ETSI
Autonomous research and analysis of base document
Prepared and conducted a Survey for ETSI groups
Results were presented in an open Webinar
October
November
December
January
Call #1
Call #2
F2F #1
Call #3
Survey launch
Webinar
Call #4
Survey end
MTS #79

## Slide 7: Ways of working
MS Team for coordination and general document sharing
  Teams, Sharepoint, OneNote
Drafting coordinated on ETSI Forge
  https://forge.etsi.org/rep/stf/stf-576/mts-203647-methodology-for-restful-apis-specifications-and-testing
  Sources in Markdown

## Slide 8: Achievements of “Phase 1”
Definition of methodology to collect info on the base documents
Analysis of base docs
Brief report in the draft
Structure of the document and indications on the content of each clause
Key decisions on the methodology

## Slide 9: Key decisions
Focus on the “standardization” use cases more than industry applicable practices
Serve as a “starting point” and a “collection of other guides and conventions”
Propose a methodology with a medium/long-term vision
  With some innovative choices
Keep Testing and Validation parts as first class citizens
  Specification methodology to enable sound testing
  Testing methodology and examples to enable reuse and speed-up testing specification development

## Slide 10: Highlights of the Survey
  Major challenges in the specification of REST API
    Inconsistency of and between documents
    Growing size of documents
  Important Topics to be covered in RESTful API Guide
    Validation of API specifications
    Selection and usage of tools
    Examples of standard deliverables (TPs, TDs, ATS)
  Importance of Interoperability and Conformance testing
Contributed as
MTS(20)079029

## Slide 11: Next steps
F2F #2 (02-05 March in Gottingen)
  To finalize key decisions and split drafting parts
  To plan dissemination and communication activities
ETSI Meetings attended
  MEC and NFV Plenaries in February

## Slide 12: MTS Feedback and STF proposals
Guidance and feedback from MTS is most welcome
  On the draft as well as on the activities for dissemination
Proposal 1 (for decision)
  Opening a rest.etsi.org portal to allow collaboration
Proposal 2 (for decision)
  Opening the STF workspace for public read access and ETSI delegates to report (more details in the Progress Report)

## Slide 13: How to collaborate with us
  Get in contact: https://portal.etsi.org/STF/STFs/STF-HomePages/STF576
  Email: stf576@groups.etsi.org
Thank you