## Slide 1: Discussion on Rel-17 Schedule
Huawei, HiSilicon
3GPP TSG-SA Meeting #89e SP-200811
Electronic Meeting, September 15 - 21, 2020
Agenda Item: 7.3

## Slide 2: Background
In SA#87E, it was decided (SP-200225) to shift the Rel-17 timeline by 3 months for all SA, RAN and CT working groups.
    Stage 2 freeze: December 2020 (originally planned for September 2020)
    Stage 3 freeze: September 2021 (9 months after stage 2 freeze)
    ASN.1 and OpenAPI specification freeze: December 2021
In SA#88E, there was no more discussion regarding the whole R17 timeline but SA2 chairman reported the high risk that SA WG2 Rel-17 study item conclusion by September 2020 (in order to meet current Sage-2 freeze of December 2020) is not feasible.
SA2 Q3 actual work and progress show that the R17 SIDs need more time to accomplish the conclusion in order to proceed the normative work.
RAN#88E also confirmed (RP-201361 TU management in Q3 2020, RAN1/RAN2/RAN3/RAN4/RAN chairmen) that “Timeline changes will be addressed once firm detailed planning will be possible. This planning is not expected to happen before December 2020.”

## Slide 3: Proposal
It is proposed SA to agree as following:
  Stage 2 freeze: December 2020 March 2021.
  SA2 Rel-17 study items should be concluded by Dec 2020.
  Keep the current SA2 SID/WID scope and no any further downscoping for Rel17.
  Keep Stage3/ASN.1 freeze unchanged for now and a checkpoint on the overall schedule in December 2020 as shifting of stage 3/overall R17 freeze can only be done by SA, RAN and CT together.