## Slide 1: <Acronym Work item> Status Report
Progress made at this meeting
  <list of items>
  Guide: Provide a short technical description of what was agreed. The text also serves as input for the SA1 report to SA plenary. No need to list tdoc numbers.
Controversial or Open issues from this meeting
  <list of topics where agreement are difficult to achieve, or general open issues, if any>
Planning for next meetings
  SA1#[n+1] (mm/yy): xx%
  Remarks: <e.g., last meeting for <e.g. new use cases>, …} >
  SA1#[n+2] (mm/yy): xx%
  Remarks: <see above>
  Actions before next meeting
  Email discussions, conference calls.
  Rapporteur: <Name, company>
UID | Name | Acronym | Target | Old % | SID/WID | New % | Change or comment
3GPP TSG SA WG 1 Meeting #102- Berlin, Germany, 22 - 26 May 2023 S1-231012

## Slide 2: FS_AmbientIoT Status Report
Planning for next meetings
  SA1#102 (May 2023): 85%
    Remarks: Sending TR for approval
  SA1#103 (Aug 2023): 100%
    Remarks: final clean up
  Actions before next meeting
  email discussion to be started 30.05, and Conf Call will be scheduled for late June to review inputs
  Rapporteur: Jose Almodovar, KPN
Example – DELETE SLIDE
UID | Name | Acronym | Target | Old % | SID/WID | New % | Change or comment
950004 | Study on Ambient power-enabled Internet of Things | FS_AmbientIoT | 06/06/2023 | 50% | SP-220085 | 75% | 
Copy-paste the 6 first fields from slide 3
If new target date, write “New target: dd/mm/yyyy”
If TR is sent to plenary: “TR for info/approval”
Provide a short technical description of what was agreed (on terminology, example of use cases, …). The text also serves as input for the SA1 report to SA plenary. No need to list tdoc numbers.
Progress made at this meeting
  Note: TR 22.840 already sent for information to SA plenary in December.
  7 new use cases introduced (e.g. among them: Electronic Shelf Label, Device permanent deactivation, Device acting as a controller in smart agriculture).
  Initial discussions on requirements and KPI consolidation.
Controversial or Open issues from this meeting
  Finish consolidated potential requirements.
  Agree conclusions.
  Resolve editor's notes.

## Slide 3: List of all SA1 ongoing Work Items
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
950003 | Study on Integrated Sensing and Communication | FS_Sensing | 06/06/2023 | 80% | SP-220717 |  | 
950004 | Study on Ambient power-enabled Internet of Things | FS_AmbientIoT | 03/03/2023 | 80% | SP-220085 |  | 
950005 | Study on Localized Mobile Metaverse Services | FS_Metaverse | 03/03/2023 | 75% | SP-220353 |  | 
950006 | Study on Network Sharing Aspects | FS_NetShare | 03/03/2023 | 80% | SP-220087 |  | 
950007 | Study on FRMCS Phase 5 | FS_FRMCS_Ph5 | 09/09/2023 | 50% | SP-220437 |  | 
950008 | Study on AI/ML Model Transfer Phase2 | FS_AIML_MT_Ph2 | 06/06/2023 | 75% | SP-220439 |  | 
960016 | Study on satellite access - Phase 3 | FS_5GSAT_Ph3 | 06/06/2023 | 80% | SP-220679 |  | 
960017 | Study on UAV Phase 3 | FS_UAV_Ph3 | 06/06/2023 | 65% | SP-220954 |  | 
960020 | Study on Network of Service Robots with Ambient Intelligence | FS_SOBOT | 09/09/2023 | 70% | SP-220447 |  | 
960019 | Study on Energy Efficiency as service criteria | FS_EnergyServ | 06/06/2023 | 70% | SP-230235 |  | 
960018 | Study on Upper layer traffic steering, switching and split over dual 3GPP access | FS_DualSteer | 06/06/2023 | 75% | SP-220445 |  | 
990053 | Study on Interconnect of SNPN | FS_ISN | 12/12/2023 | 0% | SP-230236 |  | 
990052 | Supporting UE Mobility for XR Services | XRMobility | 06/06/2023 | 50% | SP-230233 |  | 
990049 | PS Data Off for IMS Data Channel Service | IMSDCDataOff | 03/03/2023 | 0% | SP-230227 |  | 
DELETE SLIDE

## Slide 4: Guidance to write the Work Item Status Report
A Status Report shall be provided by the Rapporteur at the end of the SA1 meeting for all the ongoing (not-completed) WIDs
Only the first slide has to be provided. The other slides are supporting material.
About the table on the top of the template:
  The 6 first fields have to be a copy-paste of the information provided in the slide “List of all SA1 ongoing Work Items”
  The last 2 fields (in red) have to be completed by the Rapporteur
  This table is also used by all the other Working Groups in 3GPP
Other comments:
  In case both a Study and the corresponding Normative work are progressing in parallel, two Status Reports have to be provided: one for the Study, one for the Normative work
  If the target date is changed, use the same number for the day and the month (e.g. “09/09/yyyy” or “12/12/yyyy”) as to avoid confusion in day/month order. Or just write mm/yyyy.
DELETE SLIDE