## Slide 1: Template for Status Report
Output expected: a Status Report is only one slide
  Use ONLY slide 2 as template to report on only one SID or only one WID
  OR use ONLY slide 3 to report on both SID + corresponding WID
  THEN DELETE all other slides
Other info in these slides:
  Example to report on only one SID/WID on slide 4
  Example to report on both SID+WID on slide 5
  Work Plan extract on slide 6 – use this as baseline for the top lines (full Work Plan in https://ftp.3gpp.org/information/Work_Plan)
  Guidance to write the Work Item Status Report on slide 7
DELETE SLIDE

## Slide 2: <Acronym Work item> Status Report
Rapporteur: <Name, company>
Progress made at this meeting
  <list of items>
  Guide: Provide a short technical description of what was agreed. The text also serves as input for the SA1 report to SA plenary. No need to list tdoc numbers.
Controversial or Open issues from this meeting
  <list of topics where agreement are difficult to achieve, or general open issues, if any>
Planning for next meetings
  SA1#[n+1] (mm/yy): xx%
  Remarks: <e.g., last meeting for <e.g. new use cases>, …} >
  SA1#[n+2] (mm/yy): xx%
  Remarks: <see above>
  Actions before next meeting
  Email discussions, conference calls.
3GPP TSG SA WG 1 Meeting #104- Chicago, USA, 13 - 17 November 2023 S1-23xxxx
UID | Name | Acronym | Target | Old % | SID/WID | New % | Change or comment

## Slide 3: <Acronym Work item> Status Report
Rapporteur: <Name, company>
Progress made at this meeting
  SID:
    <list of items, if any new progress>
  WID :
    <list of items>
  Guide: Provide a short technical description of what was agreed. The text also serves as input for the SA1 report to SA plenary. No need to list tdoc numbers.
Controversial or Open issues from this meeting
  <list of topics where agreement are difficult to achieve, or general open issues, if any>
Planning for next meetings
  SA1#[n+1] (mm/yy): Study xx%, Normative xx%
  Remarks: e.g., last meeting for <e.g. new use cases>, …
  SA1#[n+2] (mm/yy): Study xx%, Normative xx%
  Remarks: <see above>
  Actions before next meeting
  Email discussions, conference calls.
UID | Name | Acronym | Target | Old % | SID/WID | New % | Change or comment
3GPP TSG SA WG 1 Meeting #104- Chicago, USA, 13 - 17 November 2023 S1-23xxxx

## Slide 4: FS_AmbientIoT Status Report
Controversial or Open issues from this meeting
  Finish consolidated potential requirements.
  Agree conclusions.
  Resolve editor's notes.
Planning for next meetings
  SA1#102 (May 2023): 85%
    Remarks: Sending TR for approval
  SA1#103 (Aug 2023): 100%
    Remarks: final clean up
  Actions before next meeting
  email discussion to be started 30.05, and Conf Call will be scheduled for late June to review inputs
Example “FS only” – DELETE SLIDE
UID | Name | Acronym | Target | Old % | SID/WID | New % | Change or comment
950004 | Study on Ambient power-enabled Internet of Things | FS_AmbientIoT | 06/06/2023 | 50% | SP-220085 | 75% | 
Copy-paste the 6 first fields from slide 6
If new target date, write “New target: dd/mm/yyyy”
If TR is sent to plenary: “TR for info/approval”
Provide a short technical description of what was agreed (on terminology, example of use cases, …). The text also serves as input for the SA1 report to SA plenary. No need to list tdoc numbers.
Rapporteur: Jose Almodovar, KPN
Progress made at this meeting
  Note: TR 22.840 already sent for information to SA plenary in December.
  7 new use cases introduced (e.g. among them: Electronic Shelf Label, Device permanent deactivation, Device acting as a controller in smart agriculture).
  Initial discussions on requirements and KPI consolidation.

## Slide 5: <AmbientIoT Status Report
Rapporteur: Jose Almodovar, KPN
Progress made at this meeting
  SID:
    20+ pCR to update the use cases have been agreed, focusing on update of KPI values, removal of the brackets/FFS/EN and further polish of the potential requirement
    The TR conclusion part is added
    7 pCR on CPR consolidation and KPI consolidation have been agreed
    The new WID is agreed.
  WID :
    The WID is agreed
    The Skeleton of the TS is agreed
    Scope, overview of the TS added
    Functional service requirements of Ambient IoT added
    Functional performance requirements of Ambient IoT added.
Controversial or Open issues from this meeting
  None
Planning for next meetings
  SA1#104 (11/2023): 100%
  Remarks: Finalize CPR and KPI consolidation
  Actions before next meeting
  Email discussions, conference calls.
UID | Name | Acronym | Target | Old % | SID/WID | New % | Change or comment
950004 | Study on Ambient power-enabled Internet of Things | FS_AmbientIoT | 12/12/2023 | 90% | SP-220085 | 95% | TR for approval
1010024 | Ambient power-enabled Internet of Things | AmbientIoT | 12/12/2023 | - | SP-231016 | 80% | TS for information
Provide a short technical description of what was agreed (on terminology, example of use cases, …). The text also serves as input for the SA1 report to SA plenary. No need to list tdoc numbers.
Copy-paste the 6 first fields from slide 6
If new target date, write “New target: dd/mm/yyyy”
If TR is sent to plenary: “TR for info/approval”
Example “FS + Norm” – DELETE SLIDE

## Slide 6: List of all SA1 ongoing Work Items (1/2)
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
950003 | Study on Integrated Sensing and Communication | FS_Sensing | 09/09/2023 | 100% | SP-220717 |  | 
1000026 | Integrated Sensing and Communication | Sensing | 12/12/2023 | 80% | SP-230750 |  | 
950004 | Study on Ambient power-enabled Internet of Things | FS_AmbientIoT | 12/12/2023 | 95% | SP-220085 |  | 
950005 | Study on Localized Mobile Metaverse Services | FS_Metaverse | 09/09/2023 | 90% | SP-220353 |  | 
1000028 | Mobile Metaverse Services | Metaverse | 12/12/2023 | 80% | SP-230509 |  | 
950006 | Study on Network Sharing Aspects | FS_NetShare | 09/09/2023 | 100% | SP-220087 |  | 
1000029 | Indirect Network Sharing | NetShare | 12/12/2023 | 100% | SP-230511 |  | 
950007 | Study on FRMCS Phase 5 | FS_FRMCS_Ph5 | 12/12/2023 | 90% | SP-220437 |  | 
1000031 | FRMCS Phase 5 | FRMCS_Ph5 | 12/12/2023 | 50% | SP-230512 |  | 
950008 | Study on AI/ML Model Transfer Phase2 | FS_AIML_MT_Ph2 | 09/09/2023 | 100% | SP-220439 |  | 
1000030 | AI/ML Model Transfer Phase 2 | AIML_MT_Ph2 | 12/12/2023 | 80% | SP-230514 |  | 
960016 | Study on satellite access - Phase 3 | FS_5GSAT_Ph3 | 09/09/2023 | 100% | SP-220679 |  | 
1000024 | Satellite access Phase 3 | 5GSAT_Ph3 | 12/12/2023 | 95% | SP-230516 |  | 
960017 | Study on UAV Phase 3 | FS_UAV_Ph3 | 09/09/2023 | 100% | SP-220954 |  | 
1000032 | Uncrewed Aerial System Phase 3 | UAS_Ph3 | 12/12/2023 | 95% | SP-230518 |  | 
960018 | Study on Upper layer traffic steering, switching and split over dual 3GPP access | FS_DualSteer | 09/09/2023 | 95% | SP-220445 |  | 
DELETE SLIDE

## Slide 7: List of all SA1 ongoing Work Items (2/2)
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
960019 | Study on Energy Efficiency as service criteria | FS_EnergyServ | 09/09/2023 | 95% | SP-230235 |  | 
1000033 | Energy Efficiency as Service Criteria | EnergyServ | 12/12/2023 | 75% | SP-230520 |  | 
960020 | Study on Network of Service Robots with Ambient Intelligence | FS_SOBOT | 12/12/2023 | 90% | SP-220447 |  | 
960015 | Study on roaming value added services | FS_RVAS | 12/12/2022 | 100% | SP-220442 |  | 
990051 | Roaming Value-Added Services | RVAS | 03/03/2023 | 100% | SP-230231 |  | 
850044 | Study on Supporting of Railway Smart Station Services | FS_RAILSS | 08/09/2022 | 100% | SP-190838 |  | 
990053 | Study on Interconnect of SNPN | FS_ISN | 12/12/2023 | 60% | SP-230236 |  | 
990052 | Supporting UE Mobility for XR Services | XRMobility | 06/06/2023 | 100% | SP-230233 |  | 
990050 | Edge Computing for Industrial Scenarios | EDGINDUS | 03/03/2023 | 100% | SP-230229 |  | 
990049 | PS Data Off for IMS Data Channel Service | IMSDCDataOff | 03/03/2023 | 100% | SP-230227 |  | 
970044 | Multi-path relay | MultiRelay | 19/09/2022 | 100% | SP-220943 |  | 
970043 | Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services | DTT4MBS | 19/09/2022 | 100% | SP-220941 |  | 
970042 | MPS for Messaging services | MPS4msg | 19/09/2022 | 100% | SP-220939 |  | 
970041 | Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | 19/09/2022 | 100% | SP-220992 |  | 
980108 | Measurement Data Collection | MeasureData | 20/12/2022 | 100% | SP-221263 |  | 
1000025 | UE-to-UE multi-hop relay | UEMHopRelay | 06/06/2023 | 100% | SP-230521 |  | 
1010025 | Local traffic routing for multi-access UE | LTR_MA | 09/09/2023 | 100% | SP-231035 |  | 
1010022 | Edge Computing Considering the Operational Needs of Service Hosting Environment | EdgeOpNeeds | 09/09/2023 | 100% | SP-231037 |  | 
1000027 | NPN security considerations | SecNPN | 06/06/2023 | 100% | SP-230523 |  | 
DELETE SLIDE
For more information, see the full Work Plan at: https://ftp.3gpp.org/information/Work_Plan

## Slide 8: Guidance to write the Work Item Status Report
A Status Report shall be provided by the Rapporteur at the end of the SA1 meeting for all the ongoing (not-completed) WIDs
Only the first slide has to be provided. The other slides are supporting material.
About the table on the top of the template:
  The 6 first fields have to be a copy-paste of the information provided in the slide “List of all SA1 ongoing Work Items”
  The last 2 fields (in red) have to be completed by the Rapporteur
  This table is also used by all the other Working Groups in 3GPP
Other comments:
  In case both a Study and the corresponding Normative work are progressing in parallel, two Status Reports have to be provided: one for the Study, one for the Normative work
  If the target date is changed, use the same number for the day and the month (e.g. “09/09/yyyy” or “12/12/yyyy”) as to avoid confusion in day/month order. Or just write mm/yyyy.
DELETE SLIDE