## Slide 1: MCVideo Status Update Mission Critical Video Services over LTE
Emmanuelle Villebrun
Ministry of Interior, France
MCVideo Rapporteur
3GPP TSG-SA WG1 Meeting #74
Venice, Italy, 9-13 May 2016
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: MCVideo Status
Is this a new WI? no
This WI has been approved at SP#70
  Approved WID is in tdoc SP-150849
Notes: 1

## Slide 3: MCVideo Progress
Progress made at this meeting
  Service description
  Final rewording
  Alignment with MCCoRe
Work/Study Item Completion: 90%
Draft TS 22.281 Completion: 90%
Controversial issues
  None, need for email approval to terminate
S1-161291
Notes: 1

## Slide 4: MCVideo Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 10 for MC
Number of slots requested for next meeting
  0
  Guide: remove bullet above if WID is 100% complete
Number of Drafting session participants: 20
  Guide: remove bullet above if no Drafting sessions held
S1-161291
Notes: 1

## Slide 5: MCVideo Completion Date
Target completion date in WID: 03/2016 SP#71
Is current completion date the same as above? No
Will target completion date be met? Yes
Expected date to send SA1 to SA plenary:
  For information: SA1#73 (02/2016)
  For approval: SA1#74 (05/2016)
S1-161291
Notes: 1

## Slide 6: MCVideo Planning/Progress
Topics to focus on at next SA1 meeting:
  None
Planning for subsequent meetings: none
S1-161291
Notes: 1

## Slide 7: Work plan between meetings
Post meeting email approval to terminate
S1-161291
Notes: 1

## Slide 8: MCVIdeo Progress Estimate
Estimated percentage completion:
  now: 90%
  After post meeting email approval: 100%
S1-161291
Notes: 1

## Slide 9: MCVideo Agreed documents
List of agreed documents at this meeting:
S1-161291
Notes: 1