## Slide 1: FS_MMTELin5G Status Update Study on evolution of IMS multimedia telephony service
Yan Di
China Mobile
FS_MMTELin5G Rapporteur
3GPP TSG-SA WG1 Meeting #94e
Electronic Meeting, 10-20 May 2021
Notes: 1

## Slide 2: FS_MMTELin5G Progress
Progress made at this meeting
  1 existing use cases updated
  1 new use cases agreed
  Clean up of editor’s notes
  Finalisation of Consolidated potential requirements
Work/Study Item Completion: 95%
Controversial issues
  No.
Notes: 1

## Slide 3: FS_MMTELin5G Planning
Planning for subsequent meetings
  SA1#95e (08/2021): 100%
    Final TR cleanup.
Notes: 1

## Slide 4: Work plan between meetings
Email discussion
  No.
Notes: 1

## Slide 5: FS_MMTELin5G Completion Date
Current expected completion dates:
  For information: SA#92 (06/2021)
  For approval: SA#93 (09/2021)
Have these dates been changed at this meeting? N
Notes: 1

## Slide 6: FS_MMTELin5G History
This WI has been approved at SA1#87
  Approved SID is in tdoc S1-192827
History of completion rates
  SA1#88 (11/2019): 10%
  SA1#91e (09/2020): 15%
  SA1#92e (11/2020):40%
  SA1#93e (02/2021):75%
  SA1#94e (05/2021):95%
Notes: 1