## Slide 1: FS_Metaverse Status Update Study on Localized Mobile Metaverse Services
Erik Guttman
Samsung
FS_Metaverse Rapporteur
3GPP TSG-SA WG1 Meeting #99-e
Electronic Meeting, 22 August – 1 September 2022
Notes: 1

## Slide 2: FS_Metaverse Progress
Progress made at this meeting
  At SA1#98e
    S1-222032 Pseudo-CR on Update to 5.1
    S1-222381 pCR- 22856-Scope modification
    S1-222382 pCR on update to 5.2
    S1-222383 Update to the Use Case on Localized Mobile Metaverse Service
    S1-222032 Pseudo-CR on Update to 5.1
    S1-222384 Pseudo-CR on updates to clause 5.3
    S1-222385 Pseudo-CR on Mobile Metaverse for immersive gaming and live shows
    S1-222386 Pseudo-CR on Use Case of Spatial Anchor Enabler
    S1-222387 Pseudo-CR on Spatial Mapping and Localization Service Enabler Use Case
    S1-222388 Pseudo-CR on Use Case Immersive AR Interactive Experience
    S1-222389 pCR Metaverse use case on supporting multi-application coordination in metaverse
    S1-222390 New use case on synchronized predictive avatars
    S1-222391 FS_Metaverse Use Case: Mission Critical Metaverse HealthCare- Surgeries, Education, Consultation and Body scans/vitals.
Work/Study Item Completion: 15% => 40%
Controversial issues
  none
Notes: 1

## Slide 3: FS_Metaverse Planning
Planning for subsequent meetings
  SA1#100 (Nov 2022): 65%
    New/Updated use cases and potential requirements
    Start consolidation
  SA1#100ah (Jan 2023): 80%
    Final work on use cases and potential requirements
    Progress / completion of consolidation.
  SA1#101 (Feb 2023): 100%
    Updated use cases and potential requirements
    Complete consolidation and conclusions
    Final TR clean-up
Notes: 1

## Slide 4: Work plan between meetings
Email coordination
  Coordination among interested/contributing companies, about planned inputs, use cases, etc.
  Before SA1 100
    2 [~1.5 hour] calls proposed, to be moderated by the SA1 chairman [to be confirmed]
    Proposed agenda (in order)
      Discuss terminology as a result of SA1 99e
      Open issues from use cases for SA1 99e
      Discuss new use cases for SA1 100
    Proposed times [exact dates tbd, doodle to follow]:
      Call 1: OCT 4 with submission by SEP 30
      Call 2: OCT 18 with submission by OCT 14
Notes: 1

## Slide 5: FS_Metaverse Completion Date
Current expected completion dates:
  For approval: SA#99 (03/2023)
Have these dates been changed at this meeting? No
Notes: 1

## Slide 6: FS_Metaverse History
This Study Item was agreed at SA1#97e
  Approved WID is in tdoc SP-220353
  SA1#96e – SID in tdoc S1-214247 was noted
  SA1#97e – SID in tdoc S1-220195 was agreed
  SA1#98e – TR skeleton and 5 pCRs were agreed
  SA1#99e – 12 pCRs were agreed
Notes: 1