## Sheet1
| SA WG2 Meeting #113 | [11 empty] | S2-160824
25-29 January 2016, St. Kitts
Source: SA WG2 Chairman
Title: SA2 Work Planning Worksheet
Document for: Discussion
Agenda Item: 7.2
Work Item / Release: All / Rel-13 and later
Abstract of the contribution: A revision of this document will capture agreements during work planning as SA2 preparations for TSG SA and/or for future SA2 meetings.
1. Introduction
This paper provides the overview of the work item status at the time of the work planning session.
The budget figures show the estimates for the expected work or show the status reached so far.
Any shown budget figures may require further consolidation.
|  | previous | [5 empty] | Oct 15 |  | Nov 15 |  | Jan 16 |  | Feb 16 |  | Apr 16 |  | May 16 |  | Jul 16 |  | Oct 16 |  | Nov 16
|  | quarter | current | Target |  | original | accumul. | SA2#111 |  | SA2#112 |  | SA2#113 |  | SA2#113AH |  | SA2#114 |  | SA2#115 |  | SA2#116 |  | SA2#117 |  | SA2#118
Track | Work Item | status | status | date |  | plan TUs | TUs | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan |  | Plan | Actl. | Plan | Actl.
3GPP | FS_AE_CIoT | 65% | 95% | Dec 15 |  | 7 | 5 | 4 | 4 | 1 | 1
3GPP | CIOT_stage2 | 0% / unstarted |  |  |  |  | 3 |  |  | 3 | 3 | 3 |  | 5
3GPP | FS_eDECOR | 70% | 80% | Mar 16 |  | 3 | 2 | 1 | 1 | 1 | 1 | 1 |  |  |  | 1
3GPP | FS_CUPS | 20% | 40% | Jun 16 |  | 9 | 4 | 1 | 2 | 2 | 2 | 2 |  |  |  | 2 |  | 2
3GPP | FS_NexGen | 5% | % | Sep 16 | many |  | 2 |  |  | 1 | 2 | 4 |  | 9 |  | 4 |  | 4 |  | 4
3GPP | FS_V2XARC | 10% | 22% | Jun 16 | O9 V18 |  | 1 |  |  | 1 | 1 | 2 |  |  |  | 2 |  | 2
3GPP | FS_GENCEF | 0% / unstarted | 10% | Jun 16 | O3 V7 |  | 0 |  |  |  |  | 1 |  |  |  | 1 |  | 1
3GPP | eDRX | 95% | 99% | Dec 15 |  |  | 3.5 | 1 | 1.5 | 1 | 2
3GPP | eProse | 90% | 100% | Dec 15 |  |  | 6 | 3 | 3 | 3 | 3
3GPP | Maint 5.1 | [5 empty] | 3 | 2 | 3 | 2 |  | 3 |  |  |  | 5 |  | 3 |  | 3
3GPP | TEI14 3GPP acc | [5 empty] | 1 | 1 | 1
Sum | [7 empty] | 13 | 15.5 | 15 | 15 | 16 | 0 | 14 | 0 | 15 | 0 | 12 | 0 | 7 | 0 | 0 | 0 | 0 | 0
|  | previous | [5 empty] | Oct 15 |  | Nov 15 |  | Jan 16 |  | Feb 16 |  | Apr 16 |  | May 16 |  | Jul 16 |  | Oct 16 |  | Nov 16
|  | quarter | current | Target |  | original | accumul. | SA2#111 |  | SA2#112 |  | SA2#113 |  | SA2#114 |  | SA2#114 |  | SA2#115 |  | SA2#116 |  | SA2#117 |  | SA2#118
Track | Work Item | status | status | date |  | plan TU | TUs | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl.
other | FS_V8 | 70% | 80% | Mar 16 |  | 9 | 4 | 2 | 2 | 2 | 2 | 2 |  |  |  | 1
other | FS_SEW2 | 60% | 75% | Jun 16 |  | 10 | 2.5 | 2 | 1.5 | 2 | 1 | 1 |  |  |  | 2 |  | 2
other | FS_AULC | 40% | 70% | Jun 16 |  | 5 | 2 | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 |  | 1
other | FS_SeDoC | 0% / unstarted | 30% | Jun 16 | O5 V3 |  | 0 |  |  | 1 |  | 1 |  |  |  | 1 |  | 1
other | FS_SDCI | 10% | 40% | Jun 16 | O6 V7 |  | 1 |  |  | 1 | 1 | 1 |  |  |  | 1 |  | 1
other | EIEI | 0% / unstarted | 20% | Jun 16 |  |  | 0 |  |  |  |  | 1 |  |  |  | 1 |  | 1
other | EWE | 45% | 60% | Jun 16 |  |  | 0.5 |  |  | 1 | 0.5 | 1 |  |  |  | 1 |  | 0.5
other | FS_RobVoLTE | 0% / unstarted | 20% | Jun 16 | O6 V8 |  | 0 |  |  |  |  | 1 |  |  |  | 1 |  | 1
other | Maint 5.2 | [10 empty] | 1
other | Maint 5.3 | [5 empty] | 7 | 2 | 3.5 | 2 | 3.5 | 3 |  |  |  | 2 |  | 2 |  | 2
other | Maint 5.4 | [5 empty] | 1.5 | 1 | 0.5 | 1 | 1 | 1 |  |  |  | 0.5 |  | 0.5 |  | 0.5
other | TEI14 PCC/QoS | [5 empty] | 0.5 | 0.5 | 0.5
other | TEI14 IMS/rel. | [5 empty] | 0 | 0.5 | [7 empty] | ?
Sum | [7 empty] | 9 | 9 | 11 | 10 | 14 | 0 | 0 | 0 | 11.5 | 0 | 10 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0