## Sheet1
|  |  | SA WG2 Meeting #118 | [15 empty] | S2-166668
|  |  | Nov 14 – 18, 2016, Reno, Nevada, USA | [13 empty] | update of S2-16
Source: SA WG2 Chairman
Title: SA2 Work Planning Worksheet
Document for: Information
Agenda Item: 7.2
Work Item / Release: All / Rel-13 and later
Abstract of the contribution: A revision of this document will capture agreements during work planning as SA2 preparations for TSG SA and/or for future SA2 meetings.
1. Introduction
This paper provides the overview of the work item status at the time of the work planning session.
The budget figures show the estimates for the expected work or show the status reached so far.
Any shown budget figures may require further consolidation.
[11 empty] | Oct 15 |  | Nov 15 |  | Jan 16 |  | Feb 16 |  | Apr 16 |  | May 16 |  | Jul 16 |  | Aug 16 |  | Oct 16 |  | Nov 16 |  | Jan 17 |  | Feb 17
status estimation (%) | [5 empty] | Target |  | acc./plan. | planned | accumul. | SA2#111 |  | SA2#112 |  | SA2#113 |  | SA2#113AH |  | SA2#114 |  | SA2#115 |  | SA2#116 |  | SA2#116bis |  | SA2#117 |  | SA2#118 |  | SA2#118bis |  | SA2#119
Q3/16 |  |  |  |  | Work Item | date |  | TUs (%) | TUs | TUs | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Update during SA#116 | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl.
80 |  |  |  |  | CUPS | 2016-09-16 | O7 V13 | 107.7778 | 9 | 9.7 | [12 empty] | 3 | 4 | 2 | 3.7 | 2 | 2 | 2
64 |  |  |  |  | FS_NextGen | 2016-09-16 | many | 95.8333 | 84 | 80.5 |  |  | 1 | 2 | 4 | 4 | 9 | 9 | 6 | 6 | 7 | 10.8 | 10 | 14.4 | 14 | 16.3 | 16 | 18 | 17
[5 empty] | NextGen | [25 empty] | 16 |  | 16
85 |  |  |  |  | V2XARC | 2016-09-16 | O9 V18 | 66.6667 | 6 | 4 | [12 empty] | 1 |  | 3 | 3 | 1 | 1 | 1
90 |  |  |  |  | GENCEF | 2016-09-16 | O3 V7 | 56.6667 | 3 | 1.7 | [12 empty] | 1 | 0.5 | 1 | 0.7 | 0.5 | 0.5 | 0.5
6 |  |  |  |  | FS_IOPS_LB |  | O7 V5 | 16 | 5 | 0.8 | [8 empty] | 1 | 0.3 | 2 | 0 |  |  |  |  | 1 | 0.5 | 1 |  | 1 |  | 1
85 |  |  |  |  | AE_enTV |  | O4 V5 | 50 | 2 | 1 | [14 empty] | 1 | 1 |  |  | 1
95 |  |  |  |  | V8 | 2016-09-16 |  | 50 | 2 | 1 | [10 empty] | 1 | 0.5 | 1 | 0.5 | 0
60 |  |  |  |  | FS PS data off | 2016-12-16 |  | 174 | 5 | 8.7 | [12 empty] | 1 | 2 | 2 | 2.7 | 1 | 4 | 1
0 |  |  |  |  | PS_data_off | [21 empty] | 1 |  | 1
70 |  |  |  |  | FS_CIOT_ext | 2016-12-16 |  | 141.6667 | 6 | 8.5 | [12 empty] | 2 | 2 | 2 | 3.5 | 1 | 3 | 1
[5 empty] | CIOT_ext | [21 empty] | 2 | 2 | 2
[5 empty] | FS VoWLAN | 2016-12-16 |  | 25 | 2 | 0.5 | [16 empty] | 1 | 0.5 | 1 |  |  |  | 1
[5 empty] | FS_eVoLP | 2017-09-01 |  | 0 | 1 | 0 | [18 empty] | 1 |  | 1 |  | 1
[5 empty] | FS_USOS | 2017-06-01 | [22 empty] | 1 |  |  |  | 1
[5 empty] | FS_eProSe-Relay | 2017-09-01 |  | 0 | 1 | 0 | [18 empty] | 1 |  | 1 |  | 1
[5 empty] | Maint 5.1 / 6.1 |  |  |  |  | 36.5 | 2 | 3 | 2 | 3 | 3 | 3 |  |  | 4.7 | 10 | 4 | 8 | 4 | 3.5 | 3.5 | 4 | 5 | 2 | 2 |  | 2 |  | 2
[5 empty] | Maint 5.2 / 6.2 |  |  |  |  | 5.8 |  |  |  |  | 1 | 1 |  |  | 1.3 | 1 | 1 | 1 | 1 | 0.8 | 0.5 | 1 | 2 | 1 | 1 |  | 1 |  | 1
[5 empty] | Maint 5.3 / 6.3 |  |  |  |  | 13.8 | 2 | 3.5 | 2 | 3.5 | 3 | 2.5 |  |  | 2.7 | 2 | 2 | 0.1 | 1 | 0.7 | 1 | 0.5 | 2 | 1 | 1 |  |  |  | 1
[5 empty] | Maint 5.4 / 6.4 |  |  |  |  | 7 | 1 | 0.5 | 1 | 1 | 1 | 0.5 |  |  | 1 | 1 | 0.5 | 1 | 1 | 1 | 0.5 | 1 | 2 | 1 | 1 |  |  |  | 1
[5 empty] | TEI15 3GPP acc |  |  |  |  | 1.5 | 1 | 1 | [13 empty] | 0.5
[5 empty] | TEI15 PCC/QoS |  |  |  |  | 1.5 | 0.5 | 0.5 | [13 empty] | 1
[5 empty] | TEI15 n3GPP | [15 empty] | 0.5
[5 empty] | TEI15 IMS/rel. |  |  |  |  | 1.5 | 0.5 | [9 empty] | 1 |  |  | 0.5 |  | 1
[5 empty] | sum | [5 empty] | 7 | 6 | 6 | 9.5 | 12 | 11 | 9 | 9 | 16.7 | 20.3 | 19 | 21.4 | 26 | 29.9 | 30.5 | 39.9 | 37.5 | 36.5 | 36.5 | 0 | 22 | 0 | 26 | 0
[11 empty] | Oct 15 |  | Nov 15 |  | Jan 16 |  | Feb 16 |  | Apr 16 |  | May 16 |  | Jul 16 |  | Aug 16 |  | Oct 16 |  | Nov 16
status (%) | [8 empty] | planned | accumul. | SA2#111 |  | SA2#112 |  | SA2#113 |  | SA2#113AH |  | SA2#114 |  | SA2#115 |  | SA2#116 |  | SA2#116bis |  | SA2#117 |  | SA2#118
Q4/15 | Q1/16 | #114 | Q2/16 | Q3/16 |  |  |  |  | TUs | TUs | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl.
|  |  | 85 |  | common aspects |  |  |  | 19 | 19.5 |  |  | 1 | 2 | 4 | 4 | 9 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
|  |  | 30 |  | KI1: Support of network slicing |  |  |  | 6.5 | 9 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1.3 | 1.5 | 3 | 2 | 2.7
|  |  | 60 |  | KI2: QoS framework |  |  |  | 6 | 8.5 | [8 empty] | 1 | 1 | 1 | 2 | 1 | 1.5 | 1.5 | 2 | 1.5 | 2
|  |  | 50 |  | KI3: Mobility framework |  |  |  | 7 | 11.8 | [8 empty] | 1 | 1 | 1 | 3 | 1 | 2.5 | 2 | 2.3 | 2 | 3
|  |  | 50 |  | KI4: Session management |  |  |  | 6 | 8 | [8 empty] | 0.5 | 0.5 | 1 | 1 | 1 | 2.5 | 2 | 2 | 1.5 | 2
|  |  | 60 |  | KI5: Enabling (re)selection of efficient UP paths |  |  |  | 1.3 | 0.9 | [10 empty] | 0.3 | 0.3 | 1 | 0.6
|  |  | 60 |  | KI6: session/service continuity |  |  |  | 4.2 | 5 | [10 empty] | 0.7 | 1 | 1 | 0.7 | 1 | 2 | 1.5 | 1.3
|  |  | 30 |  | KI7: Network function granularity and interactions between them |  |  |  | 3.2 | 2.2 | [10 empty] | 0.7 | 0.7 | 1 | 0.5 | 0.5 |  | 1 | 1
|  |  | 30 |  | KI8: core - access - functional division and interface |  |  |  | 4.1 | 4 | [8 empty] | 1 | 1 | 0.3 | 0.5 | 1 | 0.5 | 0.8 | 0.7 | 1 | 1.3
KI9: network capability exposure
|  |  | 0 |  | KI10: Policy Framework | [18 empty] | 0.5 | 0.5 | 0.5 | 1 | 0.5
KI11: Charging
|  |  | 50 |  | KI12: Authentication framework |  |  |  | 2.2 | 1.6 | [8 empty] | 0.5 | 0.5 | 0.7 | 0.3 | 0 | 0.5 | 0.5 | 0.3 | 0.5
KI13: Broadcast/Multicast Capabilities
KI14: Support for Off-Network Communication
KI15: NextGen core support for IMS
KI16: connectivity via a relay UE
|  |  | 0 |  | KI17: network discovery and selection | [18 empty] | 0.3 | 0.5 |  | 0.5
|  |  | 0 |  | KI18: Interworking and Migration | [18 empty] | 1 | 1 | 1 | 1 | 1
|  |  | 0 |  | KI19: using virtual environments | [19 empty] | 0.5 | 0.5 | 1 | 0.5
|  |  | 0 |  | KI20: Traffic steering | [18 empty] | 0.5
KI21: Extrem rural
|  |  | 10 |  | TR clause 7 / overall architecture | [18 empty] | 0.5 | 0.5 | 1 | 1 | 2
|  |  | 32.1875 | 64 | <- Average ¦ SUM -> | [5 empty] | 0 | 0 | 1 | 2 | 4 | 4 | 9 | 9 | 6 | 6 | 7.7 | 10.8 | 9 | 14.4 | 13.8 | 16.3 | 16.5 | 17.8 | 0 | 0