## Sheet1
SA WG2 Meeting #119
|  |  | Feb 13 – 17, 2017, Dubrovnik, Croatia | [12 empty] | S2-171146
Source: SA WG2 Chairman
Title: SA2 Work Planning Worksheet
Document for: Information
Agenda Item: 7.2
Work Item / Release: All / Rel-15 and later
Abstract of the contribution: A revision of this document will capture agreements during work planning as SA2 preparations for TSG SA and/or for future SA2 meetings.
1. Introduction
This paper provides the overview of the work item status at the time of the work planning session.
The budget figures show the estimates for the expected work or show the status reached so far.
Any shown budget figures may require further consolidation.
[10 empty] | Jan 17 |  | Feb 17 |  | Mar 17 |  | May 17 |  | Jun 17 |  | Aug 17 |  | Okt 17 |  | Nov 17
status estimation (%) | [5 empty] | Target | acc./plan. | planned | accumul. | SA2#119bis |  | SA2#112 |  | SA2#113 |  | SA2#113AH |  | SA2#114 |  | SA2#115 |  | SA2#116 |  | SA2#116bis
Q4/16 | Q1/17 | Q2/17 | Q3/17 | Q4/17 | Work Item | date | TUs (%) | TUs | TUs | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Update during SA#116 | Plan | Actl. | Plan | Actl.
[5 empty] | 5GS_Ph1 | 2017-12-12 | 54.5455 | 33 | 18 | 16 | 18 | 17
15 |  |  |  |  | FS_IOPS_LB | 2016-12-16 | 25 | 2 | 0.5 | 1 | 0.5 | 1
10 |  |  |  |  | FS_VoWLAN | 2017-03-17 | 0 | 1 | 0 |  |  | 1
10 |  |  |  |  | FS_USOS | 2017-06-17 | 0 | 1 | 0 |  |  | 1
5 |  |  |  |  | FS_REAR | 2017-09-17 | 100 | 2 | 2 | 1 | 2 | 1
5 |  |  |  |  | FS_eVoLP | 2017-09-17 | 0 | 1 | 0 |  |  | 1
[5 empty] | Prose_WLAN_DD | 2016-09-16 | 0 | 1 | 0 |  |  | 1
[5 empty] | NAPS | 2017-09-17 | 0 | 1 | 0 |  |  | 1
[7 empty] | #DIV/0! | 0 | 0
[7 empty] | #DIV/0! | 0 | 0
[7 empty] | #DIV/0! | 0 | 0
[7 empty] | #DIV/0! | 0 | 0
[7 empty] | #DIV/0! | 0 | 0
[5 empty] | Maint 5.1 / 6.1 |  |  |  | 4 | 4 | 4 | 4
[5 empty] | Maint 5.2 / 6.2 |  |  |  | 1 | 1 | 1 | 1
[5 empty] | Maint 5.3 / 6.3 |  |  |  | 0 |  |  | 1
[5 empty] | Maint 5.4 / 6.4 |  |  |  | 0 |  |  | 1
[5 empty] | TEI14 3GPP acc |  |  |  | 0
[5 empty] | TEI14 PCC/QoS |  |  |  | 0
TEI14 n3GPP
[5 empty] | TEI14 IMS/rel. |  |  |  | 0
[5 empty] | sum |  |  |  |  | 23 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0