## Slide 1: 5GS Status and Plan Tracking
Rapporteurs and Volunteers

## Slide 2: Goal
Provide timely output to meet the WID plan and serve as basis for related groups (e.g., CT1, CT3, CT4…) to start their work
NOTES:
The assessment of the 5GS agenda item progress in this document is used to estimate the work item progress and help companies in preparing contributions.
It is intended to be updated after each SA2 meeting.
It is drafted by rapporteurs and volunteers and does not imply an agreement of the SA2 group.

## Slide 3: TS 23.501 Estimation and Planning
AI | #118bis | #119 | #120 (March) | #121 (May) | #122 (June) | #122bis (Aug) | #123 (Oct) | #124 (Nov.)
6.5.1 General |  |  |  |  |  |  |  | 
6.5.2 AC, RM and CM |  | 40% |  |  |  |  |  | 
6.5.3 SM and continuity |  | 40% |  |  |  |  |  | 
6.5.4 Security related |  | 10% |  |  |  |  |  | 
6.5.5 QoS |  | 50% |  |  |  |  |  | 
6.5.6 Policy, charging, control |  | 30% |  |  |  |  |  | 
6.5.7 3GPP access specific |  | 40% |  |  |  |  |  | 
6.5.8 Specific services support |  | 30% |  |  |  |  |  | 
6.5.9 Interworking and Migrat. |  | 50% |  |  |  |  |  | 
6.5.10 Non-3GPP specific |  | 40% |  |  |  |  |  | 
6.5.11 Framework functions |  | 65% |  |  |  |  |  | 
6.5.12 Support of RRC inactive |  |  |  |  |  |  |  | 
For Information
For Approval

## Slide 4: TS 23.502 Estimation and Planning
AI | #118bis | #119 | #120 (March) | #121 (May) | #122 (June) | #122bis (Aug) | #123 (Oct) | #124 (Nov.)
6.5.1 General |  |  |  |  |  |  |  | 
6.5.2 AC, RM and CM |  | 45% |  |  |  |  |  | 
6.5.3 SM and continuity |  | 40% |  |  |  |  |  | 
6.5.4 Security related |  | 10% |  |  |  |  |  | 
6.5.5 QoS |  | 10% |  |  |  |  |  | 
6.5.6 Policy, charging, control |  | 5% |  |  |  |  |  | 
6.5.7 3GPP access specific |  | 40% |  |  |  |  |  | 
6.5.8 Specific services support |  | 20% |  |  |  |  |  | 
6.5.9 Interworking and Migrat. |  | 35% |  |  |  |  |  | 
6.5.10 Non-3GPP specific |  | 30% |  |  |  |  |  | 
6.5.11 Framework functions |  | 15% |  |  |  |  |  | 
6.5.12 Support of RRC inactive |  |  |  |  |  |  |  | 
For Information
For Approval

## Slide 5: 6.5.2 Access Control, RM and CM functions and flows
TS | Work to do | Progress
23.501 | 1. The usage of defining both RM state and CM for non-3GPP access. 2. The usage of the allocated TA for non-3GPP access. 3. The concept of unified access control in NG-RAN. 4. Network initiated Service Request in a Non-allowed area. 5. How long to maintain the MICO UE in CM-CONNECTED. | 40%
23.502 | 1. Registration procedure is performed with PDU session establishment. 2. Notify the CN information, i.e. MICO mode, RRC inactive allowed, and TA-list, to RAN for RAN’s MM optimization. 3. What procedure is used to update the mobility restriction of UE in non-allowed area. | 45%
Related to high level function descriptions, state models, system procedure flows, and service based procedures. In addition, slice related aspects of AC, RM and CM. Access control, Registration Management and Connection Management functionality, i.e. mainly access independent functionality, includes Attach/Registration, Detach/Deregistration, and also (periodic) Re-registration. Plus Mobility triggered re-registration. Any impacts from virtual environments that affect RM/CM might be addressed.

## Slide 6: 6.5.3 Session management and continuity functions and flows
TS | Work to do | Progress
23.501 | Clarify the impact of slice to SM Definition of DNN and relationship with APN Refine the interaction between AMF and SMF Support the DN within specific area Refine the application influence on traffic routing Selective PDU session (de)activation mgmt Others | 40%
23.502 | PDU release call flow Impacts of ULCL/BP UPF on SM call flows Impacts of QoS on SM call flows Adopt service based interfaces based on SBA discussion | 40%
Related to high level function descriptions, state models, system procedure flows, and service based procedures. In addition, slice related aspects of SM.

## Slide 7: 6.5.4 Security related functions and flows
TS | Work to do | Progress
23.501 | User identity confidentiality protection; UP security end point; Detailed description for the security functions. | 10%
23.502 | The content of the Security parameters; The description of authentication and security procedures; Whether existing UE security context in AMF can be reused. | 10%
Related to high level function descriptions, system procedure flows, and service based procedures.

## Slide 8: 6.5.5 QoS concept and functionality
TS | Work to do | Progress
23.501 | Clean up A/B type QoS flow; More detailed description for the Reflective QoS; The QoS handling for the IWK between 5G and 4G; QoS support for the Non-3GPP access; | 50%
23.502 | QoS Flows handling during Handover; Session management with QoS related; QoS Mapping for the IWK between between 5G and 4G; | 10%
Related to high level function descriptions, system procedure flows, and service based procedures.

## Slide 9: 6.5.6 Policy and charging control
TS | Work to do | Progress
23.501 | More description and handling for the new added Policy (e.g. SSCMP,NSSP,); Solutions to use the big data to improve the policy; Solutions for the policy to support slicing ; Solutions to provide policy rule to different network node; Solutions to enforce the different policy; | 30%
23.502 | SM procedure with Policy MM procedure with Policy | 5%
Related to high level function descriptions, system procedure flows, and service based procedures.

## Slide 10: 6.5.7 3GPP access specific functionality and flows
TS | Work to do | Progress
23.501 | For Mobility pattern, the concept shall be more detailed, i.e. what parameters, where from, what use. Control plane protocol stack between UE and AMF/SMF, and between RAN and AMF/SMF. | 40%
23.502 | How UE in MICO mode transmit from idle to connected. What Mobility optimization can get based on mobility pattern. The procedure of N2-based handover. Service type indication in Service request, e.g. user data, signalling. | 40%
Related to high level function descriptions, system procedure flows, and service based procedures. Including handover and MO/UE-initiated as well as MT/network-initiated Service Request. Also on radio and CN idle related aspects.

## Slide 11: 6.5.8 Specific services support
High level function descriptions related to IMS, emergency services, PWS, Location Services, SMS over NAS, MPS. Related system procedure flows. Related service based procedures.
TS | Work to do | Progress
23.501 | Clarify the ENs of IMS voice supporting Support for Public Warning System Support for Multimedia Priority Services | 30%
23.502 | Refine the SMS call flow Call flows for identified services | 20%

## Slide 12: 6.5.9 Interworking and Migration
Related to high level function descriptions, system procedure flows, and service based procedures.
TS | Work to do | Progress
23.501 | Refine the registration and how to converge on one mode. single registration mode based interworking with no Nx support Clarify the dual-registration mode and IMS voice. | 50%
23.502 | whether the 5G RAN needs to be aware of the EPS bearer ID. QoS parameters mapping from 5GC to EPC and EPS bearer ID allocation. How TFT is created/allocated. | 35%

## Slide 13: 6.5.10 Non-3GPP access specific functionality and flows
TS | Work to do | Progress
23.501 | RM management of non-3GPP access, including registration timer, periodic registration procedure, etc; CM management of non-3GPP access, e.g. mobility restriction for non-3GPP; Handover of PDU session between 3GPP and non-3GPP access. | 40%
23.502 | Periodic registration procedure definition; UE initiated service request procedure; NW initiated service request procedure; Handover procedure between 3GPP and non-3GPP access. | 30%
Related to high level function descriptions, system procedure flows, and service based procedures.

## Slide 14: 6.5.11 Framework functions
Related to high level function descriptions, system procedure flows, and service based procedures. Includes function/service registration, discovery, authorisation of usage, ...
TS | Work to do | Progress
23.501 | Capture the agreed services, including service name and service description; Complete service framework related functional descriptions, e.g. service discovery, authorization and registration; | 65%
23.502 | Convert the end to end call flow in section 4 into services presentation as much as possible; Based on 1, evaluate the services described in section 5; | 15%