SA WG2 Meeting #136	S2-1912483

18-22 November, 2019, Reno, NV, USA	(revision of S2-19xxxxx)

Source:	Nokia, Nokia Shanghai Bell (Rapporteur)

Title:	FS_IIoT Work Tasks

Document for:	Discussion and Agreement

Agenda Item:	N/A

Work Item / Release:	FS_IIoT / Rel-17

Abstract of the contribution: This paper proposes the break-down of objectives of FS_IIoT into a set of Work Tasks with granular TU estimate per Work Task.

# 1	Background

At SA #85, it was agreed to breakdown objectives of FS_IIoT into Work Tasks with TU estimates (study phase and normative phase) for each work task (see SP-190949).

The FS_IIoT TSG SA#85 SID can be found in SP-190932, SA2#135 approved SID can be found in S2-1910756.

# 2.	Discussion

Editor’s Note: Work Task Description should correspond to objectives in SID. One objective may be further broken into Work Tasks.

Editor’s Note: Work Task may or may not directly translate into a Key Issue in a TR.

NOTE 1: 	Total SA2 TU estimates originally reported for FS_IIoT were 6+3 (see S2-1908590).  These estimates have now been increased to 8+5, based on revised SID objectives to include support for IEEE TSN distributed configuration model.

Table 2-1: Work Tasks for FS_IIoT

| Work Task ID | Work Task Title | Work Task Description | RAN Dependency | TU Estimate (Study + Normative) | Inter Work Tasks Dependency Editor’s Note: This column should highlight if WT#x is self-contained, or is depended on completion of other WTs |
| --- | --- | --- | --- | --- | --- |
| Total TU = 8 + 5 (13) |  |  |  |  |  |
| WT#1 | Support for Uplink Synchronization for single and multiple clock domains | Support for Uplink Synchronization with 5GS with master GM on the device side, for single and multiple clock domains. | Don’t know | 1.0 + 1.0 | Self-contained |
| WT#2 | Enhanced support of deterministic applications (including AV service production/VIAPA), exposure of network capability to support deterministic QoS and Time Sync. | TSC support as per TS 22.263 outside of factory (incl. live news-gathering, sports events, music festivals), reduced connection setup procedures to <20ms, and large scale TSC multi-cast up to 50,000 UE. Exposure of network capability and ability for AF to provide input to support Time sensitive communication –deterministic QoS as defined in TS 23.501. Includes exposure for deterministic QoS and Time Sync related to VIAPA (Video, Imaging and Audio for Professional Applications) | No | 2.0 + 1.5 | Self-contained |
| WT3 | TSC communication via same UPF (e.g. UE-UE) | Bridge delay determination, QoS parameters determination considering communication via same UPF (e.g. UE-UE) | Don’t know | 1.0 + 1.0 | Self-contained |
| WT4 | Support for fully distributed configuration model for IEEE TSN | Supporting fully distributed configuration model for TSN by adding support of 5GS for Multiple Stream Registration Protocols for example as defined in IEEE 802.1Q, subclause 35.1 and IEEE P802.1CS Link-local Registration Protocol. | Don’t know | 4.0 + 2.0 | Self-contained |