## Slide 1: FS_enh_EC Status Report
Hui Ni
Huawei

## Slide 2: 2.4) Rel-17 Study (1/11)
Progress since SA#86:
  7 new Solutions for KI#1 (Edge application server discovery ) were agreed.
  Key Issue #4 and Deployment guideline are not to be progressed in R17 as a result of downscoping exercise.
RAN impacts or dependencies:
  None
Next steps:
  Collect solutions for key issues
  Resolve Editor’s Notes of solutions and evaluation.
WI Code | Work Item Title | WP | Target Date | WID#
FS_enh_EC | Study on enhancement of support for Edge Computing in 5GC | 20 > 40% | June, 20 | SP-190185

## Slide 3: FS_enh_EC status after SA2#136AH (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_enh_EC | Study on enhancement of support for Edge Computing in 5GC | 20 > 40% | June, 20 | SP-190185
General
  FS_enh_EC TR 23.748 v0.3.0 is available here.
  Total TUs requested for Study Phase in 2020 is 4. 1 TU is used and 3 TUs are remaining.
Key issue 1 (Discovery of Edge Application Server)
  7 new solutions are agreed for this key issue.
  Next steps: Resolve ENs in the solutions; Solution evaluations; Way forwards towards conclusion.
Key issue 2 (Edge relocation)
  No solution discussed yet.
Key issue 3 (Network Information Provisioning to Local Applications with low latency)
  No solution discussed yet.
Key issue 4 (Consecutive traffic steering in different N6-LAN)
  Downscoped. Will not be studied in Rel-17.
Key issue 5 (Activating the traffic routing towards Local Data Network per AF request)
  No solution discussed yet.

## Slide 4: FS_enh_EC status after SA2#136AH (2/2)
  RAN impacts and dependencies:
  None identified.
Contentious Issue:
  None identified.
Focus for the Next Meeting (SA2#138):
  Solution collection for all Key issues. No new key issue will be discussed.
  Initial evaluation on key issue #1.
Overall Plan:
  SA2#138 (Apr): Finish solution collection for all key issues. Start initial evaluation. New solutions should be proposed with all details, including impacts on existing NFs and services.
  SA2#139 (May): Aim to conclude most Key issues. Submit TR 23.748 to SA#88 plenary for approval. Agree a WID.