## Slide 1
Puneet Jain
SA2 Chairman, Intel
SA2 Work Planning
for 2020

## Slide 2: SA2 Work Planning (1/3)
Background
  SA2#138 and SA2#139 F2F meetings has been cancelled due to coronavirus concern.
  Rel-17 stage-2 timelines have been delayed by 3 months, i.e. new stage-2 completion date is Dec 2020.
Q2 Planning, organize 2 e-meeting
  SA2#138E: Focus on pre-Rel-17 topics + new TEI-17 proposals
  SA2#139E: Focus on selected Rel-17 topics + Urgent LSs
    Proposed Topics – FS_eNA_ph2, FS_eNPN, FS_enh_EC, FS_eNS_ph2, FS_IIoT, FS_eATSSS, FS_ID_UAS-SA2.
    Why Selected topics?
      Selected topics have minimal RAN dependency. Please note RAN won’t start Rel-17 work before Q3, 2020. We will have better understanding of RAN schedule at June Plenary.
      Keeping e-meeting manageable: Total tdoc is expected to be around 250 – 300 for these topics. Email traffic is expected to be even more than SA2#137E due to Rel-17 nature of the topics.
Endorsed

## Slide 3: SA2 Work Planning (2/3)
Additional Considerations
  New stage-2 freeze date of Dec 2020 gives 3 F2F meetings in 2020 to finalize Rel-17 in SA2.
  Big topics and topics having RAN dependency may be at risk - FS_5MBS, FS_5G_Prose, FS_MUSIM.
  Options to mitigate risk :
    Option #1: Re-instate July F2F ad-hoc meeting.
    Option #2: Add 3 additional F2F days to SA2#140 (August, 2020) F2F meeting.
    Option #3: Additional e-meeting may be organized in July, 2020 (July 6 week) focusing on remaining selected topics – FS_5MBS, FS_5G_ProSe, FS_MUSIM, FS_5GSAT_ARCH, FS_V2XARC_Ph2 + urgent LSs.
    Option #4: SA2 Ad-hoc meeting in Jan 2021 can be confirmed to stabilize Rel-17 topics. Decision to be taken at SA2#140 F2F (August, 2020) meeting.
  Option#1 and Option#2 poses serious scheduling and meeting hosting risk due to ongoing coronavirus situation. We may not find meeting host, or end up cancelling F2F meeting as well.
  Proposal: Agree on Option#3, and tentatively Option#4 (Final decision at Aug F2F). Option#3 and Option#4 would also require MCC support which needs to be confirmed.
Option#3, and tentatively Option#4 Endorsed

## Slide 4: SA2 Work Planning (3/3)
Handling of TEI17 (resulting in CAT B/C CRs)
  SA2#138E e-meeting will be last meeting to submit new TEI-17 proposals. TEI17 proposal should also contain WID for approval at SA2#138E.
  TEI17 work will commence in Q4, 2020.
  Total 4 TUs (2 TUs each at SA2#141 and SA2#142 meeting) will be allocated for TEI17 work.
    4 TUs will be used from Buffer TUs and will not impact Rel-17 study/work items TUs
  TEI17 work must finish in one plenary cycle.
  Minimum TU allocation will be 0.5 TU.
  If we have more TEI17 items than available TUs, then SA2 would need to prioritize (e.g. using show of hands) at SA2#140 (Aug).
Endorsed

## Slide 5: SA2# 138E e-meeting
Deadlines
  Docs request: 10 April 2020 (Friday) 2400 UTC
  Docs submission: 10 April 2020 (Friday) 2400 UTC
  Start of e-meeting: 20 April 2020 (Monday) 0000 UTC
  Revisions by: 22 April 2020 (Wednesday) 1600 UTC
  Final deadline: 23 April 2020 (Thursday) 1600 UTC
  Close of e-meeting: 24 April 2020 (Friday) 1600 UTC
  Upload Approved docs: 27 April 2020 (Monday) 1600 UTC
  NOTE: Final Chairman’s Notes will be made available shortly after the close of e-meeting deadline.
Agenda
  Same as SA2#137E e-meeting (i.e. pre-Rel-17 topics + new TEI-17 proposals). Detail agenda will be sent later.
Endorsed

## Slide 6: SA2# 138E e-meeting
Guidance on conference calls
  CCs can be scheduled until e-meeting start date. They can be chaired by anyone and output should be shared over the SA2 DISCUSSION list. These CCs will continue to have NO approval power.
  Email discussion may also take place over SA2 DISCUSSION list prior to start of e-meeting e.g. to merge documents.
  NO conference calls during e-meetings (see exception below)
  Following CC (Chaired by SA2 leadership) may be organized during SA2#138E e-meeting, if needed –
    CC#1: 20 April 2020 (Monday) 1300 - 1500 UTC (Subjected to change)
    CC#2: 24 April 2020 (Friday) 1300 - 1500 UTC
    Objective of these conference calls would be to find way forward on any controversial topics. They won’t be used to discuss/process documents.
    These CC during e-meeting will have approval power.
    No recording of CC is allowed, similar to 3GPP rules for the F2F meeting.
    Participation would be limited to SA2#138E e-meeting registered delegates only.
    For CC#2, there will be flexibility to generate new revisions after Final-deadline (e.g. if small change can remove certain objection).
Endorsed. New learning will be applied to the future e-meeting.

## Slide 7: SA2# 138E e-meeting
E-meeting Process
  Same as SA2#137E e-meetings with following enhancements.
  Comments should be provided as per email template. Example -
      Revision provided: <List new revision#, else leave blank>
      Link to revision: <Link to revision# in revision folder, else leave blank>
      Objection to: <List revision #s that you cannot accept and have objection, otherwise leave blank>
      Acceptable revisions: <List revision #s that are acceptable, or leave blank>
      Comments: <new comments or response to previous comments>
    Final Email template will be distributed later.
  Emails not following email template will be discarded.
  Only Emails from people registered for SA2#138E e-meeting will be considered.
  SA2 leadership will provide document with detail instructions on overall e-meeting process.
IT improvements (To be discussed with MCC)
  How to avoid over-writing revision already available in the revisions folder?
  Auto generation of Chairman’s Notes from email template.
E-meeting Process endorsed

## Slide 8: SA2# 139E e-meeting
Deadlines
  Docs request: 15 May 2020 (Friday) 2400 UTC
  Docs submission: 15 May 2020 (Friday) 2400 UTC
  Merge doc submission: 21 May 2020 (Thursday) 2400 UTC
  Start of e-meeting: 25 May 2020 (Monday) 0000 UTC
  Revisions by: 27 May 2020 (Wednesday) 1600 UTC
  Final deadline: 28 May 2020 (Thursday) 1600 UTC
  Close of e-meeting: 29 May 2020 (Friday) 1600 UTC
  Upload Approved docs: 01 June 2020 (Monday) 1600 UTC
  NOTE: Final Chairman’s Notes will be made available shortly after the close of e-meeting deadline.
  Agenda
  Selected Rel-17 topics - FS_eNA_ph2, FS_eNPN, FS_enh_EC, FS_eNS_ph2, FS_IIoT, FS_eATSSS, FS_ID_UAS-SA2.
  No new Key Issues (except for FS_eATSSS, FS_ID_UAS-SA2). Details will be sent later. This meeting would be last meeting to submit new KIs for FS_ID_UAS-SA2.
Endorsed

## Slide 9: SA2# 139E e-meeting
New deadline for Merged document submission is added. Objective is to allow merges/revisions after submission deadline based on discussion on conference calls/emails. Some examples –
  Merge similar solution to specific KI
  To address revision based on the comments during CC, or over SA2 DISCUSSION list
Guidance on conference calls
  Same as SA2#138E. Any new learnings may be applied.
Process
  Same as SA2#138E. Any new learnings may be applied.
IT improvements
  Same as SA2#138E. Any new learnings may be applied.

## Slide 10
Thank You!