## Slide 1: FS_5G_ProSe Status Report
Deng Qiang (CATT), Jianhua Liu (OPPO)
3GPP TSG SA WG2 Meeting #139E
Electronic meeting, June 01 – 12 2020

## Slide 2: FS_5G_ProSe Status at SA#87
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 30% > 55% | Jun, 20 | SP-190443
Progress since SA#86:
  Only one SA2 WG meeting in Q1
  Total TUs requested for Study Phase in 2020 is 7. 2 TUs are used and 5 TUs are remaining.
  New solutions and solution updates are captured into TR 23.752, and for all key issues we have solutions on table.
  RAN impacts and dependencies:
  All the key issues may have RAN impact and coordination with RAN may be necessary.
Contentious Issue:
  Whether support of service continuity for UE-to-Network Relay in Release 17 needs SA#87 decision..
Next steps:
  Consolidate the solutions, make overall evaluation and conclusions for each key issue at Q2.
  For UE-to-Network Relay and UE-to-UE Relay, consolidate technical issues and conclusions on SA2 aspect, pending RAN-related issues and wait for RAN progress.

## Slide 3: FS_5G_ProSe status after SA2#136AH (1/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 30% > 55% | Jun, 20 | SP-190443
General
  FS_5G_ProSe TR 23.752 v0.3.0 is available here.
  Total TUs requested for Study Phase in 2020 is 7. 2 TUs are used and 5 TUs are remaining.
  New solutions and solution updates are captured into TR 23.752, and for all key issues we have solutions on table.
Key Issue 4 (UE-to-UE Relay):
  4 new solutions were agreed for inclusion in the TR. Total number of solutions for KI#4 is 4.
  Next Steps: Consolidate the solutions and make overall evaluation and conclusions on SA2 aspect, wait for RAN NR sidelink relay SI progress.
Key Issue 5 (Path Selection):
  1 new solution was agreed for inclusion in the TR. Total number of solutions for KI#5 is 1.
  Next Steps: Resolve the ENs in this solution, discuss other solutions if available and make evaluation and conclusion.
Key Issue 7 (Charging):
  3 new solutions were agreed for inclusion in the TR. Total number of solutions for KI#7 is 3.
  Solutions can be categorized as AMF-based and SMF-based solutions.
  Next Steps: Resolve the ENs in these solutions, discuss other solutions if available and make overall evaluation and conclusion.
Key Issue 8 (Service Authorization):
  2 new solutions were agreed for inclusion in the TR. Total number of solutions for KI#8 is 2.
  Next Steps: Resolve the ENs in these solutions, discuss other solutions if available and make overall evaluation and conclusion.

## Slide 4: FS_5G_ProSe status after SA2#136AH (2/3)
Key Issue 1 (Direct Discovery):
  For DDNMF location, UP-based and CP-based were agreed for inclusion in the TR.
  For UE-to-Network discovery, 1 solution was agreed for inclusion in the TR.
  Total number of (related) solutions for KI#1 are 7.
  Next Steps: Consolidate the solutions and make overall evaluation and conclusions.
Key Issue 2 (Direct Communication):
  2 new solutions on ProSe QoS were agreed for inclusion in the TR.
  1 new solution on group communication was agreed for inclusion in the TR.
  Total number of (related) solutions for KI#2 is 5.
  Next Steps: Consolidate the solutions and make overall evaluation and conclusions.
Key Issue 3 (UE-to-Network Relay):
  Solutions for Layer-3 Relay (sol#6) and Layer-2 Relay (sol#7) were captured in the TR.
  Next Steps: Consolidate technical issues and conclusions on SA2 aspect, pending RAN-related issues and wait for RAN progress.

## Slide 5: FS_5G_ProSe status after SA2#136AH (3/3)
  RAN impacts and dependencies:
  All the key issues may have RAN impact and coordination with RAN may be necessary.
Contentious Issue:
  UE-to-Network Relay and UE-to-UE Relay regarding Layer-2 or Layer-3 Relay depends on RAN decision.
Focus for the Next Meeting (SA2#138):
  Consolidate the solutions, make overall evaluation and conclusions for key issues whose solutions are deemed stable at SA2#138.
  For UE-to-Network Relay and UE-to-UE Relay, consolidate technical issues and conclusions on SA2 aspect, pending RAN-related issues and wait for RAN progress.
Overall Plan:
  SA2#138 (Apr) & SA2#139 (May): Consolidate the solutions, make overall evaluation and conclusions for each key issue. Submit TR 23.752 to SA#88 plenary (June 2020) for one-stop approval. Agree a WID.

## Slide 6: FS_5G_ProSe status after SA2#139e (1/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 55% > 65% | Jun, 20 -> Sep, 20 | SP-190443
General
  FS_5G_ProSe TR 23.752 v0.4.0 is available here.
  There is only one e-meeting for Rel-17 SIDs in Q2 and all FS_5G_ProSe documents were handled at SA2#139e.
  16 new solutions and 21 solutions update agreed for inclusion in TR 23.752, there are now 38 solutions in TR 23.752 on all the 7 prioritized key issues.
  LS out was sent to SA3 to ask about security requirements on UE-to-Network Relay and UE-to-UE Relay.
Key Issue 1 (Direct Discovery):
  4 solutions updates (sol#1, #2, #3, #18) were agreed for inclusion in the TR.
  1 new solution for UE-to-Network Relay discovery and 1 new solution for UE-to-UE Relay discovery were agreed for inclusion in the TR.
  Total number of solutions for KI#1 are 9.
  Next Steps: Complete and consolidate the solutions. Start solution evaluation and (interim) conclusion(s).
Key Issue 2 (Direct Communication):
  1 new solution and 4 solutions updates (sol#4, #5, #22) were agreed for inclusion in the TR.
  Total number of solutions for KI#2 is 6.
  Next Steps: Complete and consolidate the solutions. Start solution evaluation and (interim) conclusion(s).

## Slide 7: FS_5G_ProSe status after SA2#139e (2/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 55% > 65% | Jun, 20 -> Sep, 20 | SP-190443
Key Issue 3 (UE-to-Network Relay):
  9 new solutions (addressing security, service continuity, authentication/authorization etc.) and 5 solutions updates (sol#6, #7) were agreed for inclusion in the TR.
  Total number of solutions for KI#3 are 12.
  Next Steps: Complete and consolidate the solutions and starting self-evaluation and self-conclusion(s) for L2-based Relay and L3-based Relay respectively from SA2 point of view. Communicate with RAN WGs on the TR and pend RAN/SA3-related issues, wait for RAN/SA3 progress.
Key Issue 4 (UE-to-UE Relay):
  2 new solutions and 5 solutions updates were agreed for inclusion in the TR.
  Total number of solutions for KI#4 is 6.
  Next Steps: Complete and consolidate the solutions and starting self-evaluation and self-conclusion(s) for L2-based Relay and L3-based Relay respectively from SA2 point of view. Communicate with RAN WGs on the TR and pend RAN/SA3-related issues, wait for RAN/SA3 progress.

## Slide 8: FS_5G_ProSe status after SA2#139e (3/5)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 55% > 65% | Jun, 20 -> Sep, 20 | SP-190443
Key Issue 5 (Path Selection):
  1 solution update (sol#12) was agreed for inclusion in the TR. Total number of solutions for KI#5 is 1.
  Next Steps: Complete and consolidate the solutions. Start solution evaluation and (interim) conclusion(s).
Key Issue 7 (Charging):
  1 new solution and 3 solutions updates (sol#13, #14, #15) were agreed for inclusion in the TR. Total number of solutions for KI#7 is 4.
  Solutions can be categorized as CP-based and UP-based solutions.
  Next Steps: Complete and consolidate the solutions. Start solution evaluation and (interim) conclusion(s).
Key Issue 8 (Service Authorization):
  2 new solutions were agreed for inclusion in the TR. Total number of solutions for KI#8 is 4.
  Next Steps: Complete and consolidate the solutions. Start solution evaluation and (interim) conclusion(s).

## Slide 9: FS_5G_ProSe status after SA2#139e (4/5)
  RAN impacts and dependencies:
  Solutions for KI#1, #2, #7 and #8 has minimal RAN impact.
  Solutions for KI#5 may have RAN impact and depends on the solution discussion.
  Solutions for KI#3 (UE-to-Network Relay) and #4 (UE-to-UE Relay) have dependencies on RAN and SA3. RAN/SA3 plan to start corresponding study work in August, this makes final conclusions on these two KIs in August meeting at high risk.
Contentious Issue:
  UE-to-Network Relay and UE-to-UE Relay regarding Layer-2 or Layer-3 Relay depending on RAN decision.
Focus for the Next Meeting (SA2#140e):
  No new KI, and last meeting to bring any new solutions. New solution proposals should be reasonably complete.
  For KI#1, #2, #7 and #8, complete and consolidate the solutions, and start solution evaluation and conclusion(s).
  For KI#5, complete and consolidate the solutions, make ready for evaluation and conclusion and identify RAN impact if any.
  For KI#3 and #4, complete and consolidate the solutions, and starting self-evaluation and self-conclusion(s) for L2-based Relay and L3-based Relay respectively from SA2 point of view. Communicate with RAN WGs on the TR and pend RAN/SA3-related issues, wait for RAN/SA3 progress.
  Draft LS to other WGs (e.g. RAN2/3) for feedback.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 55% > 65% | Jun, 20 -> Sep, 20 | SP-190443

## Slide 10: FS_5G_ProSe status after SA2#139e (5/5)
Overall Plan:
  SA2#140e (August):
    For Key Issues #1, #2, #7 and #8, complete and consolidate the solutions, and start solution evaluation and conclusion(s).
    For KI#5, complete and consolidate the solutions, make ready for evaluation and conclusion and identify RAN impact if any.
    For Key Issues #3, #4, complete and consolidate the solutions.
    Draft LS to other WGs (e.g. RAN2/3) for feedback.
  SA2#141e (October)/SA2#142e (November):
    Continue solution evaluation and conclusion for KI#1, #2, #5, #7 and #8 if not finished at SA2#140e.
    New WID proposal based on agreed conclusion(s).
    For KI#3, KI #4, self-evaluation and self-conclusion(s) for L2-based Relay and L3-based Relay respectively from SA2 point of view.
    Draft any additional LS to other WGs (e.g. RAN2/3) for feedback.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe | Study on System enhancement for Proximity based Services in 5GS (FS_5G_ProSe) | 55% > 65% | Jun, 20 -> Sep, 20 | SP-190443